# Biweekly Status Report to Workgroup

| Project: | CSTE Data Standardization Workgroup |
| --- | --- |

| To: | Shaily Krishan, Meredith Lichtenstein, Shannon Harney, and Molly Crockett |
| --- | --- |
| CC: | Workgroup Members |
| From: | Emily Augustini and Elizabeth Sprouse |
| Date: | 6-1-18 |

# Overall Status for June 1, 2018

| Status | Comments |
| --- | --- |
| On Track | On track according to adjusted timeline after the extended Date of Illness Onset discussion |

# Activities Performed and Accomplishments This Period

The CSTE Data Standardization Workgroup has convened one time this reporting period, during which we discussed the membership’s comments on the proposed Date of Illness Onset definition, as well as some continued discussion of Diagnosis Date. Below is a summary of the sources of variation and other input from this meeting:

- Diagnosis Date

  - Presumptive v. Confirmatory Diagnosis: The Diagnosis Date field is populated with both, depending on the disease and available data. Both types of diagnosis provide useful information, so we must find a way to capture both while standardizing the field to allow comparisons between jurisdictions and programs.

    - Some options include:

      - Categorizing by disease

      - In the future, requesting an additional field be added to the MMG specifying if the diagnosis is presumptive or confirmatory

- Date of Illness Onset Proposed Definition

  - Decided to specify which MMGs to which the definition applies

  - Clarified that the data element is intended to capture “onset of symptoms” not “beginning of illness”

  - Discussed providing additional guidance around Event Date

In addition, we broached the topic of the Data Standardization Workgroup’s presentation during the Surveillance/Informatics Sunday Workshop at the 2018 CSTE Annual Conference. Members expressed interest in:

- Using the presentation to garner interest in the workgroup

- Discussing implementation of proposed definitions

- Creating a survey to distribute to workshop attendees

Finally, we distributed the long-term roadmap survey to workgroup members. This survey will allow members to provide feedback on the consensus process and future directions for the workgroup. This survey is due by June 4, 2018.

# Status of Data Elements under Discussion

| Data Element | Solicit Initial Input | Discussion on Workgroup Call | Distribute Sample Definitions | Vote on Definitions | Discuss Results on Workgroup Call | Develop Consensus Definition | Present Definition to CSTE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Date of Illness Onset | √ | √ | √ |  |  |  |  |
| Diagnosis Date | √ | √ |  |  |  |  |  |
| Date First Reported to PHD |  |  |  |  |  |  |  |

# Activities Planned For The Next Reporting Period

- Long-term roadmap assessment: The survey was distributed to members. The co-chairs, JMC, and CSTE will be collecting and analyzing the responses, and discussing the results at the CSTE Annual Conference.

- CSTE Annual Conference: The Data Standardization Workgroup will be a topic of discussion at the CSTE Annual Conference Surveillance/Informatics Sunday Workshop. There will be a presentation about the workgroup’s progress and a guided discussion. The session is 3:30 – 4:15 pm on Sunday, June 10. We look forward to seeing you there and around the conference!

- NOTE: The June 8, 2018 workgroup meeting has been cancelled due to many members traveling to the CSTE Annual Conference. The next workgroup meeting will be June 22, 2018.