# Biweekly Status Report to Workgroup

| Project: | CSTE Data Standardization Workgroup |
| --- | --- |

| To: | Shaily Krishan, Meredith Lichtenstein, Shannon Harney, and Molly Crockett |
| --- | --- |
| CC: | Workgroup Members |
| From: | Emily Augustini and Elizabeth Sprouse |
| Date: | 6-15-18 |

# Overall Status for June 15, 2018

| Status | Comments |
| --- | --- |
| On Track | On track |

# Activities Performed and Accomplishments This Period

During this reporting period, the CSTE Data Standardization Workgroup leadership prepared for the CSTE Annual Conference. A workgroup update was presented at the Surveillance/Informatics Sunday Workshop, and a discussion was held with the group present at the workshop. This conversation will be addressed in-depth on the next workgroup call, but below is a summary of the presentation and discussion:

- The co-chairs presented on:

  - Workgroup charge and mission

  - Consensus framework

  - Collaboration tools

  - Long-term roadmap survey

  - Date of Illness Onset progress and proposed definition

  - Diagnosis Date progress

  - Lessons Learned

- Topics broached in discussion:

  - Next steps for the workgroup, including data elements and reporting processes

  - What level of granularity is valuable in the definitions

  - Thoughts on the consensus framework

In addition, during the last reporting period, we distributed the long-term roadmap survey to workgroup members. This survey allowed members to provide feedback on the consensus process and future directions for the workgroup. Responses will be discussed on a future call.

# Status of Data Elements under Discussion

| Data Element | Solicit Initial Input | Discussion on Workgroup Call | Distribute Sample Definitions | Vote on Definitions | Discuss Results on Workgroup Call | Develop Consensus Definition | Present Definition to CSTE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Date of Illness Onset | √ | √ | √ |  |  |  |  |
| Diagnosis Date | √ | √ |  |  |  |  |  |
| Date First Reported to PHD |  |  |  |  |  |  |  |

# Activities Planned For The Next Reporting Period

- Long-term roadmap assessment: The survey was distributed to members. The co-chairs, JMC and CSTE will discuss the results on a future workgroup call.

- Date of Illnes Onset and Diagnosis Date: The group will continue discussion of the Date of Illness Onset proposed definition and Diagnosis Date.