
Disaster Epidemiology Guidance Document Call Notes
June 6, 2016 at 1pm ET

Attendees: Josephine Malilay, Michael Heumann, Tess Konen, Jessica Wurster, Svetlana Smorodinsky, Jennifer Beggs 

Draft Outline Updates
Michael added recovery assessments to the outline for the disaster epidemiology guidance document. Michael will follow up with Natalie Grant who presented at the Disaster Epi Workshop to see if she is interested in participating in developing a section on the role of disaster epidemiology in recovery. 
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As far as next steps, we’d like to ask all authors/section leaders to develop an expanded outline on their section(s) and identify colleagues/co-authors as needed by September 2016.  

Timeline
The group discussed the overall timeline and discussed that everyone who is an author/contributor will likely have to go through agency clearance.  We probably should allocate at least 2 months for the clearance process. 

September 2016– Outline for each section completed by various authors
January 2017– Advanced drafts of each section completed 
February 2017– Compile drafts of various sections and send to agencies for clearance
April 2017 – Completion Date

Document Editing Process 
We discussed how we are going to go about the document editing process since emails can become burdensome to manage during an extensive editing process. CSTE has recently started using Basecamp which is a project management software and may assist with the editing process. Jessica will further explore this over the summer.  Google Drive could also be an option but some agencies have access issues with that. 

We also discussed that a few folks will need to revise all the sections to match writing styles across the different sections. Joel Greenspan, Michael Heumann, and Josephine Malilay assisted with this process on the AJPH article.  CSTE also contracts with a couple editors so we could send this to a CSTE editor if needed but that likely will add about a month to the timeline. 

Michael will write an email to everyone to sum up today’s call and next steps. 

