# Disaster Epidemiology Resource Guide – Status as of August 30, 2018

A few updates:

- Aiming to have complete drafts of all chapters by late August/early September

- Betsy Kagey (cc’d here) has drafted the guide’s “floating article” (attached) – however, the group decided to have this act as an “introduction/objectives of the guide/how to use it/what to expect” chapter instead

- For the “introduction” chapter, need 2-3 sentences concerning each chapter

With that being said, I have compiled a few helpful lists to identify which chapters need what done/who should do them, which include: action items from the August 2018 call, authors by chapter, chapter completion/review status, and chapter summary points status. Please let me know if any of the below points are incorrect/need to be updated. All can be found below.

ACTION ITEMS

- Review the attached floating introduction/overview (send edits/feedback to Hayleigh & Betsy by COB Friday, August 24th)

- Draft/send in your chapter’s summary points (send to Hayleigh & Betsy by COB Friday, August 24th)

- For chapters in development/review*

  - Send in timeline for chapter completion (upload completed draft to Basecamp & send to Michael by late August/early September)

  - Finalize chapter

  - Begin chapter internal review

*See below tables for chapter statuses

CHAPTER AUTHORS

- Introduction/Background – Authors: Betsy Kagey, Michael Heumann, David Zane

- Mortality Surveillance – Author: Rebecca Noe

- Syndromic Surveillance – Authors: Meredith Jagger, Michael Heumann

- Rapid Needs Assessment/CASPER – Authors: Svetlana Smorodinsky, David Zane, Tesfaye Bayleyegn

- ERHMS – Authors: Lisa Delaney, Jill Shugart, Angela Weber, Beth Whelan, Michael Heumann

- Shelter Surveillance – Authors: Miguel Cruz, Josephine Malilay, Doug Thoroughman, Ashley Conley

- Chemical Release Assessments/ACE – Authors: Svetlana Smorodinsky, Jason Wilken, Tracy Barreau, Mary Anne Duncan, Alice Shumate, Kimberly Brinker, Erica Thomasson, Joy Hsu

- Disaster Behavioral Health – Authors: Jennifer Beggs, Akiko Saito, David Dickinson

- Rostering and Post-Disaster Surveillance – Author: Tess Konen

- Descriptive Epidemiology – Author: David Zane

- Disaster Epidemiology Tool Repositories – Authors: Hayleigh McCall, Nicole Nakata, New NCEH DE Representative, Steve Ramsey

CHAPTER COMPLETION/REVIEW STATUS

| Complete and reviewed | Complete but in institutional review | In development/pending internal review |
| --- | --- | --- |
| Rapid Needs Assessment/CASPER | Disaster Epidemiology Tool Repositories (needs CSTE and DECoP review) | Mortality Surveillance |
| Chemical Release Assessments/ACE |  | Shelter Surveillance |
| Disaster Behavioral Health |  |  |
| Descriptive Epidemiology |  |  |
| Rostering and Post-Disaster Surveillance |  |  |
| ERHMS |  |  |
| Syndromic Surveillance |  |  |

CHAPTER SUMMARY POINT STATUS

| Summary points provided | Need partial summary points | Need summary points |
| --- | --- | --- |
| Disaster Behavior Health | Disaster Epidemiology Tool Repositories (needs CSTE and DECoP summary points) | ERHMS |
| Rostering and Post-Disaster Surveillance |  | Mortality Surveillance |
| Rapid Needs Assessment/CASPER |  | Shelter Surveillance |
| Chemical Release Assessments/ACE |  |  |
| Descriptive Epidemiology |  |  |
| Syndromic Surveillance |  |  |