Project Management Set-Up Process

https://lightstep.com/blog/incident-response-playbook

https://lightstep.com/blog/incident-response-best-practices

- Project Initiation after project requested

  - Determine scope, requirements, and business case

  - Create project or workgroup Charter

  - Identify Milestones

  - Identify Deliverables

  - Identify thresholds, escalation, and end state

- Identify Stakeholders

What units or people do we need to contact to create a workgroup?

  - Provide contact information for all stakeholders

- Customers (Internal/External)

- Team Members (Consultants, Project Manager, Sponsor, Leadership)

- Center for Public Affairs and Equity (C4PA)

- Office of Information Technology (HTS)

- REDCap, WDRS, etc.

- Disease Subject Matter Experts or Units

- Public Health Lab (PHL)

- Vendors (travel, data, software, etc.)

- Agencies (Federal, State, Local Health Jurisdictions, Tribal Health Jurisdictions)

- Roles and Responsibilities (RACI or RAM)

- Org charts

- IMT Positions

- Equity Staff Memeber

- Project Planning

  - Identify Strategy and Objectives, Tactics and Planning

    - Metrics for success

    - Measures for cancelling or closing project (infection/death rate)

    - Measure IMT activation

  - Resource Planning to determine needs:

    - Logistic support

    - Communication Support

    - REDCap, WDRS, etc.

    - Build out workflows and communications with resources

    - Org charts and reporting structures

  - Risks and Assumptions

    - Project success factors

    - Project failure factors

    - Contingency plans

  - Procurement Considerations

  - Formal IMT set up and structure

- Project Schedule

  - Determine operational period

  - Determine timeline

    - Create Schedule/WBS

    - Task List (Excel, SmartSheet, Project)

    - Dashboard (BaseCamp)

    - Milestone plan

- Communication

  - Create Teams Channel or SharePoint Site

  - Response specific email inbox

  - Documentation

    - Storage location for Cat4 data

    - Consistent location and access

  - Create Project OneNote Notebook

  - Define Roles and Responsibilities

  - Coordinate and facilitate meetings – Project Management, Project Strategy and Objectives, Tactics and Planning

  - External

    - LHJ meetings

    - Training

    - Flyers Etc.

- Budget

  - Who does DOH team members charge their time too?

  - Determine potential funding sources

  - Create or add to Outbreak hourly tracker – track hours worked

  - Direct costs (software, hardware, travel, etc.)

- Meeting Facilitation

  - Kickoff

  - Project Management team

  - Project Strategy and Objectives team

    - Are we meeting obj or missing them

    - Hot Wash

  - Tactics team

  - Planning team

  - External Meetings – CDC, DOC, LHJs, Tribal Health etc.

    - Coordinate with E&C Outreach Coordinators

  - Meeting Notes and Action Items

    - Maintain

    - Documentation of decisions

- Reports

  - Sit Rep

  - Hot Wash report or meeting

  - IMP or WIMP - Workgroup Incident Management Plan

- Specialty reports

  - Fiscal considerations

  - Time Reporting

  - Leadership updates

- Project Closure and Lessons Learned

  - Hot Wash

  - AAR (After Action Review)

  - Lessons learned

  - Support and coordination debrief

    - Project Management team

    - Response team

    - Leadership/Sponsor

  - Return equipment or resources