CSTE LD Case Definition/Position Statement Timeline
	Date
	Case Definition Subgroup Timeline
	CSTE Timeline

	Monday, December 3, 2018
	Small group leads (lab, HAI, incubation period, clinical) will present their concrete work to the smaller LD Case Definition Subgroup (SG)
	

	Friday, December 7, 2018
	
	2019 position statement template released

	Thursday, December 20, 2018
	Case Definition small groups present their concrete work to the full Legionnaires’ Disease Surveillance Workgroup (WG)
	

	January 2019
	
	CSTE position statement author training webinars released

	Monday, January 7, 2019
	Review draft position statement with CSTE LD Case Definition SG
	

	Thursday, January 17, 2019
	Present draft position statement with larger CSTE LD Surveillance WG
	

	Monday, February 4, 2019
	Discuss and make changes to the position statement within CSTE LD Case Definition SG
	

	Thursday, February 21, 2019
	Finalize draft position statement with larger CSTE LD Surveillance WG
	

	Monday, March 4, 2019
	Built-in buffer to discuss last minute things before the submission deadline (includes appendices)
	

	Thursday, March 7, 2019
	
	CSTE position statement submission deadline (includes appendices)

	Thursday, March 21, 2019
	
	Position statement assigned to specific committee

	Thursday, April 4, 2019
	
	Position statement reviewed and suggestions for revision are sent to primary author

	Thursday, April 18, 2019
	
	Revised revisions must be submitted

	Thursday, April 25, 2019
	
	Position statement posted on CSTE website

	April-May 2019
	
	Webinars for position statement discussion

	June 2-6, 2019
	
	CSTE Annual Conference in Raleigh, NC
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