# Mini-project Charter

## PROJECT NAME

Model Interjurisdictional Dashboard

## PROJECT MEMBERS

Amanda, Kelli, Rob, Kevin, Carson, Dametreea

PURPOSE

To develop a template dashboard to be implemented with various types of interjurisdictional outcomes

DELIVERABLES

- Template dashboard(s) by facility and/or patient location

  - Example queries included

  - Example alerts included

  - Multiple widget types (bar charts, time series, maps, etc)

  - Stratifications by site

  - Demographics (age/sex/race/ethnicity)

## TASKS

- Develop a modifiable dashboard template

  - Schedule a conference call within the next two weeks (by Jul 7th)

  - Talk through the template format and key components to include

  - Assign someone to create the dashboard and share

  - Team review/update of the dashboard

  - Dashboard “owner” make final updates and re-share

  - Share template dashboard with regional group

## NOTES

- Template should be modifiable to suit various data/outcome needs