
Project Name: Determining a process for syndromic surveillance data sharing within the  Western Region. 

Project Members: Greg, Eunice, Melinda, Mitch, Teresa, Kirk

Purpose: 

Assuming a DUA is in place, determine a procedure for shared data handling including the request and closing processes, stakeholder engagements, and communication pathways.

Deliverables:
1. Create a basic workflow and further define each process for each sharing request
2. Create a standardized form for data sharing requests including:
a. How the data will be used
b. Data description and other details related to data governance
c. Format for sharing (dashboard and aggregation details, other data visualization options, etc.)
d. Timelines
e. Data suppression including interstate considerations
3. Communication pathways and contact lists for stakeholder engagement

Tasks in the next two weeks:
-Review data sharing resources available on the knowledge repository
-Review and assess DUA with facilities as a model for inter/intrajurisdictional data sharing
-Check in with CDC about how data access rules are set up in the BioSense platform and to what granularity (can we specify a timeline and is it per user or per jurisdiction?)
-Determine platforms and interest from participating jurisdictions
-Finalize basic process diagram
-Explore possibility of oversight committee to ensure data is used appropriately - workgroup?
