CSTE Zika Preparedness Resource Toolkit Workgroup Call

October 16, 2017 at 1 pm (ET)

Roll Call

In attendance was Jen Brown, Kim Cervantes and Hanna Oltean from the Work Group; Paul Etkind, Consultant; and, Meri Phillips from CSTE.

Progress on Toolkit

- Some current events from MedlinePlus have been added.

- We continue to receive tools from CSTE members – 6 so far

- I am continuing to look at disaster and preparedness sites for materials.

- For tools, I will continue to focus on submissions from CSTE members

- The focus will be less on tools going forward, and more on webinars and beginning writing the explanatory text to accompany the different categories of tools

Webinars

- Emails and phone calls have been sent and made to confirm commitments from speakers

  - See Webinar Plan dated 171013 in Base Camp for details

- A Doodle Poll was re-sent to those who have not responded

- All but four speakers have responded to the Doodle Poll

- (This bullet’s information developed after the October 16 call) There are two webinars for which all speakers have responded - #3 (Diagnostics) and #5 (Control and Prevention)

  - The numbers are arbitrary and will not reflect the order of the occurrence of the webinars

  - Diagnostics is tentatively being scheduled for January 11, 2018 at 2:30 PM

  - Prevention and Control is tentatively being scheduled for November 15, 2017 at 2 PM

- (Some of this bullet’s information was developed after the October 16 call) A separate phone call was held with colleagues from NYC on October 13, who felt that the topics in #1 (Surveillance) were not mutually exclusive as proposed. Speakers would be repeating materials if we kept the structure intact. It was suggested that we change the topics to a discussion of ArboNet, a presentation on the collaborations necessary for conducting surveillance, and a discussion of the collaborations necessary to investigate congenital abnormalities. A call was held on October 18 with the presenters slated for that webinar, and they agreed with the new arrangement.

- In addition to scheduling the rest of the webinars, the following information will have to be obtained from each speaker to schedule and promote each one:

  - Title of each talk

  - A brief description of the material to be presented in each talk

  - Speakers’ titles, credentials and affiliations

  - Permission from each speaker to be recorded and for the content and recording to allowed to be posted on CSTE’s webinar library

  - Assess the interest of each speaker to have a demo of the WebEx software to assure their familiarity with the technology

Open Forum

- Will begin focusing on writing the explanatory and descriptive information that will accompany each section of the tool kit

Next Call

- There will no longer be bi-weekly phone calls for the Work Group. We will continue to issue bi-weekly update documents like this one, and specific issues will be dealt with, to the extent possible, by email.