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CSTE Zika Preparedness Resource Toolkit Workgroup Call
October 16, 2017 at 1 pm (ET) 
Roll Call
In attendance was Jen Brown, Kim Cervantes and Hanna Oltean from the Work Group; Paul Etkind, Consultant; and, Meri Phillips from CSTE. 
Progress on Toolkit
· Some current events from MedlinePlus have been added. 
· We continue to receive tools from CSTE members – 6 so far 
· I am continuing to look at disaster and preparedness sites for materials. 
· For tools, I will continue to focus on submissions from CSTE members
· The focus will be less on tools going forward, and more on webinars and beginning writing the explanatory text to accompany the different categories of tools 
Webinars
· Emails and phone calls have been sent and made to confirm commitments from speakers 
· See Webinar Plan dated 171013 in Base Camp for details
· A Doodle Poll was re-sent to those who have not responded 
· All but four speakers have responded to the Doodle Poll 
· (This bullet’s information developed after the October 16 call) There are two webinars for which all speakers have responded - #3 (Diagnostics) and #5 (Control and Prevention) 
· The numbers are arbitrary and will not reflect the order of the occurrence of the webinars 
· Diagnostics is tentatively being scheduled for January 11, 2018 at 2:30 PM
· Prevention and Control is tentatively being scheduled for November 15, 2017 at 2 PM
· (Some of this bullet’s information was developed after the October 16 call) A separate phone call was held with colleagues from NYC on October 13, who felt that the topics in #1 (Surveillance) were not mutually exclusive as proposed. Speakers would be repeating materials if we kept the structure intact. It was suggested that we change the topics to a discussion of ArboNet, a presentation on the collaborations necessary for conducting surveillance, and a discussion of the collaborations necessary to investigate congenital abnormalities. A call was held on October 18 with the presenters slated for that webinar, and they agreed with the new arrangement. 
· In addition to scheduling the rest of the webinars, the following information will have to be obtained from each speaker to schedule and promote each one:
· [bookmark: _GoBack]Title of each talk
· A brief description of the material to be presented in each talk
· Speakers’ titles, credentials and affiliations
· Permission from each speaker to be recorded and for the content and recording to allowed to be posted on CSTE’s webinar library
· Assess the interest of each speaker to have a demo of the WebEx software to assure their familiarity with the technology
Open Forum
· Will begin focusing on writing the explanatory and descriptive information that will accompany each section of the tool kit
Next Call
· There will no longer be bi-weekly phone calls for the Work Group. We will continue to issue bi-weekly update documents like this one, and specific issues will be dealt with, to the extent possible, by email.  
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