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CSTE Zika Preparedness Resource Toolkit Bi-Weekly Update
October 29, 2017 
Progress on Toolkit
· Some current events from MedlinePlus have been added. 
· Nine sets of tools received from CSTE members. These are still welcomed, so please continue to urge your colleagues to submit materials to Paul or Meri. 
· I did not look at disaster and preparedness sites for materials these past two weeks. 
· The focus will continue to be less on tools going forward, and more on webinars and beginning writing the explanatory text to accompany the different categories of tools. 
Webinars
· [bookmark: _GoBack]Update: the Zika Project will support up to five webinars. All speakers have been confirmed for these five, and dates for all but one has been confirmed as well. We will continue developing the following sessions:
· Case Surveillance – date tbd
· Mosquito and Pesticide Resistance Surveillance – 2/20/18 at 1-2 PM Eastern
· Diagnostics – 1/11/18 at 1-2 PM Eastern
· Expanding Surveillance 2/7/18 1-2 PM Eastern
· Control and Prevention 11/15/17 2-3 PM Eastern
· Planning for the webinar focusing on Notes from the Field will not continue. Those speakers will be informed that the webinar is cancelled, and will be thanked for their willingness to participate.
· Meri will conduct an orientation to the use of WebEx for Paul the week of October 30.
· Announcement information about each webinar is under development. See below. 
· Title of each talk
· A brief description of the material to be presented in each talk
· Speakers’ titles, credentials and affiliations
· Permission from each speaker to be recorded and for the content and recording to allowed to be posted on CSTE’s webinar library
· Assess the interest of each speaker to have a demo of the WebEx software to assure their familiarity with the technology
Open Forum
· No writing of the explanatory and descriptive information that will accompany each section of the tool kit was initiated in the past two weeks.
Next Update
· Barring some dramatic change or situation with this Project, the next bi-weekly update will be issued shortly after November 13. Any questions or suggestions can be sent to us via email or Base Camp. 
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