## Time and Cost
Prioritization | Type | Current Yearly Frequency | Future Yearly Frequency | User 1 Time | User 2 Time | User 3 Time | Frequency of Refactoring (Monthly) | Yearly Total User Time (Current) | Yearly Total User Time (Future) | Average User Salary (Yearly) | Yearly Total Cost (Current) | Yearly Total User Cost (Future)
Output 1 | Dashboard
Output 2 | Report
Output 3 | Data Pull
Output 4 | Data Entry

## Scope
Prioritization | Type | Impact | Complexity | Dependencies | Constraints | Timeline | Priority | Political Blockers | Technical Blockers
Output 1 | Dashboard
Output 2 | Report
Output 3 | Data Pull
Output 4 | Data Entry

## Roles
RACI Matrix
RESPONSIBLE performs work | ACCOUNTABLE checks in can veto / approve | CONSULTED asked for input | INFORMED decision or output shared

## Schedule
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Days Remaining (for Gantt) | Percent Complete | Start Date in Number Form | 43066 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Draft Proposal | 2017-11-27 | 2017-12-01 | 5 | 0 | 5 | 5 | 0%
Hiring Process | 2017-12-04 | 2018-02-26 | 61 | 0 | 61 | 69 | 0%
Proposal Approved | 2017-12-04 | 2018-01-19 | 35 | 0 | 35 | 35 | 0%
Contract Signed | 2018-01-19 | 2018-02-26 | 27 | 0 | 27 | 27 | 0%
Inception Meeting | 2018-01-24 | 2018-01-26 | 3 | 0 | 3 | 3 | 0%
Addition of Lung Cancer and Diabetes Survey | 2018-01-29 | 2018-03-16 | 35 | 0 | 35 | 39 | 0%
Offline Data Collection Testing and Refactoring | 2018-02-16 | 2018-03-23 | 26 | 0 | 26 | 32 | 0%
Field GeneXpert Data Integration Between Sites | 2018-03-12 | 2018-03-23 | 10 | 0 | 10 | 14 | 0%
Field Progress Indicator Dashboards | 2018-03-19 | 2018-03-30 | 10 | 0 | 10 | 14 | 0%
Sputum Sample Shipment and Tracking | 2018-03-19 | 2018-03-30 | 10 | 0 | 10 | 12 | 0%
DISA and OpenLDR Integration of Lab Data | 2018-03-19 | 2018-04-13 | 20 | 0 | 20 | 26 | 0%
Central Progress Indicator Dashboards | 2018-04-13 | 2018-04-30 | 12 | 0 | 12 | 16 | 0%
Training of Trainers | 2018-04-02 | 2018-04-05 | 4 | 0 | 4 | 6 | 0%
Pilot + Refactoring | 2018-04-09 | 2018-04-23 | 11 | 0 | 11 | 13 | 0%
IT Support | 2018-04-30 | 2018-11-22 | 175 | 0 | 175 | 177 | 0%
[8 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[9 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.