Norm Anderson – Schedule of activities
Period of Performance: December 1, 2017 – June 30, 2018
	November – December 2017
	Begin developing assessment and research for white paper

	Early January 2018
	First draft of assessment due to workgroup for review

	Late January 2018
	Launch pilot assessment

	February 2018
	Incorporate pilot feedback and launch full assessment

	February – June 2018
	Complete data analysis, develop draft summary report, conduct research for white paper, develop draft white paper

	April 2018
	Final assessment report and the draft white paper due to CSTE

	April – June 2018
	Prepare and conduct webinars on the assessment and white paper findings for environmental health partners.

	By June 30, 2018
	Final white paper due to CSTE


*Please note the timeline is subject to change.
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