# Norm Anderson – Schedule of activities

Period of Performance: December 1, 2017 – June 30, 2018

| November – December 2017 | Begin developing assessment and research for white paper |
| --- | --- |
| Early January 2018 | First draft of assessment due to workgroup for review |
| Late January 2018 | Launch pilot assessment |
| February 2018 | Incorporate pilot feedback and launch full assessment |
| February – June 2018 | Complete data analysis, develop draft summary report, conduct research for white paper, develop draft white paper |
| April 2018 | Final assessment report and the draft white paper due to CSTE |
| April – June 2018 | Prepare and conduct webinars on the assessment and white paper findings for environmental health partners. |
| By June 30, 2018 | Final white paper due to CSTE |

*Please note the timeline is subject to change.