2017-2018 Influenza Education Among Youth in Agriculture Pilot Project

September 26, 2017, 3:00-4:00PM EST

--

Next Call: November 28, 2017, 3:00-4:00PM EST

CSTE - Monica Schroeder

CDC - Emily Lobelo, Eli Painter, Joe Gregg, Melanie Gross

Iowa – Molly Lee, Abbey Cannon, Kristen Obbink (CFSPH), Andy Weigel (IDPH)

Ohio – Andy Bowman, Jacqueline Nolting (OSU), Laurie Billing (ODPH)

Michigan – Mary Grace Stobierski, Kim Signs (MDHHS)

Maine – Johanna Mackenzie, Sara Robinson (MECDC)

North Dakota – Laura Cronquist (NDDPH)

Kentucky – Paul Royce, Kelly Giesbrecht (KDPH State Vet)

Project Logistic Updates (Monica):

- First progress reports due October 31, 2017

  - Templates posted on Basecamp

  - 2-part: Word document and Excel spreadsheet

  - Any issues accessing, please contact Monica

- Please continue to work with your grants and finance teams to invoice per the schedules included in the contract agreements

Workshop Updates (Monica):

- Meeting in person October 23 & 24, 2017 in Atlanta, GA

  - Should have received via e-mail with RSVP link

  - Please RSVP by September 29th

  - If RSVPing past that deadline, please let Monica know by e-mail

- Hotel block closes on October 1st; if need extension, please let Monica know so that you can receive government rate

- Developing pre-reading material so that everyone has baseline knowledge of what projects everyone has been doing over the past couple of years

  - CSTE/CDC would like to share project proposals from this year, with sensitive information removed (budget, etc.)

  - Will confirm with everyone by e-mail

- Comments:

  - MI – Fine with sharing

  - ME – Same

  - KY – Same

  - IA – Should be fine, will check

Workshop Updates Part II (Eli):

- Finalizing agenda for workshop

  - Would like to have 2 sessions with site overviews by each state

  - Speak for ~10 minutes, 5 min Q&A

  - Will create template with topics we would like you to cover

  - Will get template to you by end of the week

  - Ask you to turn in presentation a few days before workshop

Brief Overview of Projects from Grantees -

- Kentucky (Kelly): Have hired student, plan on doing outreach education with youth who show their livestock. Will put questions into youth skill-a-thon to measure if education has been effective.

  - Questions:

    - Emily – When will the actual education occur? Eli has been working on evaluation framework, in case you want to use some of our questions/would like a resource. Can offer technical assistance with evaluation.

      - Kelly – State skill-a-thon is February 17th; try and go to some expos in November and December to do some education. Multiple choice questions. Will be doing a lot more education during the 2018 fairs and education at CLL training (Certified Livestock Leaders).

- Maine (Johanna): Hired an intern last week. Had first fair event where kids were surveyed for pre-intervention knowledge.

- North Dakota (Laura): No updates. Many ideas but still working on contract with accounting office.

- Michigan (Mary Grace): Scheduled and soon beginning 7 regional meetings throughout the state from October 14 – November 9th. Connect fair boards, veterinarians, fair livestock council, 4-h club leaders, MSU extension, state agriculture staff, state and local health department staff in meet-and-greet setting. Discuss rolls of each agency; inform about current outbreaks; share resources and answer questions. 3 completed by workshop.

  - Comments:

    - Emily – May follow up about someone from CDC or CSTE attending one of the meetings

      - Mary Grace – Will e-mail registration sheet with locations and dates.

- Joe – Will try to make it to one of the meetings.

- Ohio (Andy): Offer help to KY and MI; just got results back from swine skill-a-thon at OH State Fair. 30-point station, average score was 13.9. MI – can share swine surveillance data for flu from MI fairs for their meetings. Will put information about skill-a-thon up on Basecamp.

  - Comments:

    - Emily – Will devote a good portion of second day of workshop to evaluation. Hoping to integrate things that have been done with new projects.

- Iowa (Abbey): No new updates from last call. Will start traveling to different events over next 2 months to distribute the course. International Association of Fairs and Expos presentation and booth. Encourage use of course and distribute! Free and open-access for all. Looking for feedback on how course is being used in their state; if it is being used; success/challenges; partners in the area who are using it and any feedback from them. Have some stickers to hand out at conferences. If anyone wants some, can send them to you to share at different events.

  - Comments:

    - Joe – Gone through most of curriculum and seems very timely and effective in the way it is presented.

    - Monica – Anyone including course in their outreach? Course is linked on Basecamp site.

Additional questions or comments can be directed to mschroeder@cste.org, 770-458-3811.