2017-2018 Influenza Education Among Youth in Agriculture Pilot Project

January 23, 2018 3:00-4:00 PM EST

--

Next Call: February 27th, 2018 3:00-4:00 PM EST

CSTE - Monica Schroeder

CDC – Lauren Roper, Eli Painter, Emily Eisenberg Lobelo, Kim Callaway, Megin Nichols

Iowa – Molly Lee, Abbey Cannon, Kristen Obbink (CFSPH)

Ohio – Andy Bowman, Jacqueline Nolting (OSU), Laurie Billing (ODH)

Minnesota – Carrie Klumb (MDH)

Michigan – Mary Grace Stobierski, Kim Signs (MDHHS)

Maine – Johanna Mackenzie (ME CDC)

North Dakota – Laura Cronquist, Michelle ? (NDDoH)

Kentucky – Kelly Giesbrecht (KDPH)

CDC Updates (Monica):

- Zoonoses & One Health Updates (ZOHU) webinars

  - Open invitation for state teams to present your work on the monthly call

  - Held on first Wednesday, 2 pm EST every month

    - Huge, varied audience

  - If interested, please e-mail zohucall@cdc.gov

    - Would like to have some groups present!

CSTE Updates (Monica):

- Updated progress report templates

  - Quarterly

  - Updates to better capture qualitative and quantitative data about project impact at state and national level

  - E-mailed out January 18th

    - Posted on Basecamp as well

  - 2-part template

    - Word and Excel document; please complete both using new template

    - Due February 28th

      - Also next invoicing deadline

- Basecamp

  - Please continue to utilize as you continue to finalize projects!

  - Post abstracts, publications as developed, etc.

- CSTE Conference

  - June 10-14 in West Palm Beach, FL

  - Have submitted a round table abstract on behalf of project team

    - Thank you to those who provided feedback

- If accepted, will coordinate with authors who will be in attendance

- Several other abstracts related to state projects were submitted!

  - Please keep us updated

- Supplemental Award Opportunity – Due Feb 16th

  - Sent via e-mail on Friday January 19th

  - Seeking proposals for enhanced evaluation efforts to better inform effectiveness of interventions

    - Proposals should incorporate methods to work collaboratively with other states to evaluate multiple methods

    - Examples included in attachment

    - Due by February 16th; processed as amendment to original contract agreement

    - Any questions, contact Monica

- Questions/Comments:

  - Mary Grace: Glad to hear that a number have submitted abstracts; is anyone looking at them collectively and scheduling a session so that they are presented around the same time?

  - Emily: Seems like a good idea.

    - Monica: CSTE sends abstracts out for review; when they come back, will have agenda planning discussion. Will be participating in zoonotic/vector-borne group. Hope to group into sessions that make sense.

Online Resource Library/Website Update (Lauren Roper):

- Library coming along

  - Trying to meet deadline of February 15th to have all state resources reported

  - Website beta landing page

  - Anyone needs additional information, please let Lauren know

Evaluation Update (Eli Painter):

- Using reports states made for October workshop, progress reports, and notes from the calls to create impact statements for each state

  - Have bare-bones bullet impact statement for each state that will be sent out for accuracy and to have states finish filling in

  - Way to use all the info to create reports that can be used at the state and federal level

  - Will try to send by January 24th

- Part of the new FOA is qualitative research project

  - Creating evaluation parameters, one-pager for scope of study

  - Will post on Basecamp in case you are interested in performing a qualitative research study

- Survey bank discussed during workshop will be ready January 24th and be on Basecamp

Round robin updates from sites:

Iowa

  - DVM/MPH student will be doing practicum

    - Develop new course for younger audience

  - Before the holidays, met with 4-H staff and had a great meeting

    - Ideas for things to do at 4-H conference

  - Have application complete to submit course to be certified curriculum for Iowa and national 4-H

    - Submitting in next few days

  - Article published in Fairs & Expos magazine

    - Can’t access online with membership

    - Will scan in and put on Basecamp

  - Did interview last week for National Swine Registry

    - Haven’t seen article yet

    - Questions about flu preventions, measures people can take

    - Wanted to know more about the course

  - Submitted an abstract to CSTE conference

Questions/Comments:

- Emily: NIFA reviews curriculum?

  - National 4-H curriculum isn’t directly related to each state, so there were 2 applications

    - National – goes through peer-review group; do not know who is involved

    - Similar components to address; different learning techniques, core elements, standards of education

    - Unsure how long the process will take!

Kentucky

  - In February, will be doing skill-a-thon

    - Creating questions for three age groups

    - Will have an hour to work with group leaders, who will bring information back to their groups

    - Three glow-germ trials; hands, objects, post-washing hands

    - Aerosol trial

  - For bigger training, going to have 30-35 people

    - Will buy glow-germ for each participant

    - Modified mucus swap

      - Use food coloring

  - Going to add more about food safety at the fair

    - Eating/living next to animals without spreading zoonotic diseases

  - Submitted poster to CSTE conference

    - KY public health meeting in April; looking for abstracts

    - Able to present the same topic?

Questions/Comments:

- Monica: Do not see an issue with presenting at both venues.

- Monica: For the train-the-trainer method, do you have a way you can track how many youths are educated/reached?

  - Kelly: Are doing pre/post-tests, but not sure how to measure how many youths are reached! Will work with UK on it

  - Hoping skill-a-thon in Feb and state fair will show kids have been trained.

Maine

- In last preparation for zoonotic train-the-trainer event Sunday January 28th

  - 6-hour event

  - Piggy backed off ME Association of Agriculture Affairs, which runs Fri-Sat

  - Using some of their space and are compensating for hotel rooms for participants

  - Over 50 people attending; aimed for 40!

  - Speaker (Valerie Koenig), veterinary medical officer from MA; big picture talk on agritourism and fairs, public health education

  - Intern will be giving presentation on foundation of zoonotic disease transmission

  - Planned 5 activities

    - Breaking into small groups

    - Mucus swap, Blue Not Flu video, glow-germ, board game (Germ-O); created new matching game for this year

  - Post-quiz and event evaluation

  - Trying to figure out the best way to track how many people the information is passed on to

    - Deadline of July 1st to send form back about where they presented, how many people attended

    - Offered assistance of intern

Michigan

- Survived all 6 regional meetings!

- Recently presented at MI Association of Fairs & Exhibitions annual meeting

  - Distilled down presentation into an hour

  - Had audience of about 30 people

- Have begun some analysis of pre/post tests given at regional meetings

  - Seeing some change!

  - Regarding restriction of food in barns; whether attendees thought they were vulnerable to zoonotic disease

- Asked to speak at AVMA in July in Denver

  - Will talk about MI as well as highlights of other states

- Still waiting to hear if there is a replacement MSU extension coordinator

  - Did have MSU extension at all regional meetings

  - Hoping to have someone to help complete final 2 lessons

- May do another regional meeting in upper peninsula in later spring

Questions/Comments:

- Carey (MN): Are the pre/post-test on Basecamp?

  - Not currently on Basecamp, but will add it.

- Monica: Offer coordination help prior to AVMA conference

  - One Health office working on one-pager

    - Mary Grace: Would greatly appreciate help, especially the bulleted list for each state

Minnesota

- Trying to do sub-award for 4-H

  - A lot of what we are doing is directly with 4-H kids

  - Proving to be very difficult

  - 4-H has been paying for things, then state has to get money to them

  - Any suggestions are welcome!

- First year since 2014 that MN Fed of County fairs have not put group on agenda

  - Didn’t respond to any contact

- Have 4-H career day in February

- Agritourism events in March and April

  - Hosting out of 4-H office, which is centrally located in St. Cloud

  - 4-H is going to help advertise event

  - Hoping for big turnout!

- Initial meeting about educational videos on biosecurity and food safety

  - Follow-up meeting Thursday with videographer

- Joe is planning on adapting educational zoonotic disease toolkit and piloting at meeting next month

- Voluntary online certification is finally live!

  - Anyone else interested, can send the information

- Working with central state ag center in NE

  - Do commercial contest every year

  - Want to adapt that

Questions/Comments:

    - Monica: Anyone have experience with 4-H sub-awards?

    - Emily: Helpful to reach out to IAFE?

North Dakota

- Still working with fair boards to set up meetings

  - Trying to develop relationships with local public health and fair boards

  - Have been ignored by many

- Have had some luck – will be at state dairy convention January 24th giving examples of project

- Presented to board of animal health last month

  - Got a lot of contact information for programs in ND

  - Working on contacting

- Trying to set up order form for materials on website

- Working with 4-H contact to set up times to record educational videos featuring 4-H kids

Ohio

- Did interview with National Swine Registry/Seed Stock Ed magazine

  - Suggested course from MI

  - Have been working with NSR; think it will be a good collaboration

- Group working on revising measures to minimize swine influenza had a conference call

  - Haven’t revised guidelines much

  - Disseminating information was a big point to fair organizers and exhibitors

  - Volunteered to translate into more lay document (in progress)

- Presented to Ohio state veterinarian before he talked to Ohio Fair Association

  - Pushing guidelines

- Went to Indiana to talk to IN fair association

  - Representatives from all counties

  - Performed mucus swap

  - Big cry for shared resources

- Educational videos finished in next couple of weeks

- Meeting with ag economist and anthropologist for other ways to evaluate outputs of this project

- Submitted abstract to neglected influenza conference in UK

- Manuscript on attitude and behaviors from survey from last year

  - Close to finished!

- Educational events at OH junior swine day, OH swine circuit doing no pig swine show, OH 4-H youth conference, OH swine health symposiums

- Working on what to do for World Pork Expo

- Working on curriculum for the year

  - Developed biosecurity Jenga game

Open Discussion:

- Emily: Thank you for working on this project as well as current flu!

- Megin: Excited to hear about MI and great you are presenting at AVMA. Thank you!

Next call: Tuesday February 27th @ 3:00pm ET