2017-2018 Influenza Education Among Youth in Agriculture Pilot Project

August 22, 2017, 3:00-4:00PM EST
--
Next Call: Tuesday September 26, 2017 3:00-4:00PM EST

CSTE - Monica Schroeder, Caitlin Loretan (intern), Stephen Uong (intern)
CDC - Emily Lobelo, Joe Gregg, Casey Barton Behravesh, Ellie Painter, Michael Young, Melanie Gross
Iowa – Molly Lee, Abbey Cannon, Kristen Obbink (CFSPH), Andy Weigel (IDPH)
Ohio – Andy Bowman (OSU), Laurie Billing (ODH)
Minnesota – Carrie Klumb (MDH)
Michigan – Mary Grace Stobierski, Kim Signs (MDHHS), Jake DeDecker (MSU Extension)
Maine – Johanna Mackenzie, Sara Robinson (MECDC)
North Dakota – Tracy Miller (NDDoH)
Kentucky – Johnathan Ballard (KY DPH)

CDC Updates (Emily):
· Using this project as example for what CDC is doing with rural health
· Ex: Senate health committee wanted update on variant flu last week
· Prompted by Ohio H3N2v
· Pigs sent to slaughter was mark of concern by public health
· Corrected misconception about event
· Used as opportunity to talk about this project; federal/state interagency and university 
collaboration

Project Logistics (Monica):
· Thank you for helping move contracts through
· Reminder to continue working with your grants and accounting staff
· Be aware of invoicing schedule so that awards can get paid out on time

· Quarterly progress reports required
· Finalizing template, will send out soon
·  First progress report due by October 31st
· 2-part template
1. Word document with questions about top achievements, collaborators involved, concerns/challenges with deliverables, updates to project timelines, additional suggestions for CDC/CSTE to best facilitate progress
2. Excel that lists project deliverables, summary of what has been done related to deliverables, and (new this year) a brief impact statement about how these activities address project objectives; include how many people/youth have been reached; any other information that can be used in communication about this project
· Please provide feedback on any information or questions that would be helpful to include or rephrase; used as mechanism of communication between federal partners and grantees.



· Questions/Comments About Reports:
· Carrie (Minnesota): Not a time burden; reasonable structure for report. Cleared up timing of getting money out.
· Joe: Main reason for update is to be able to promote your work at/outside of CDC, keep momentum for project, and share products of your work with other places
·  If you think any changes need to be made to the template, please let us know
· Emily: Useful so that you can learn from one another; if there is a challenge, please share (as well as how you overcome the challenge)
· Have reports been shared in the past?
· Monica – Have not shared progress reports in the past; keep confidential unless see same challenges identified; if so, can aggregate and share during monthly call 
· Emily – When you are doing reports, if you think it would be useful to see what everyone is doing, let us know so we can figure out a method to share information

· Updates for Grantee Workshop
· Save-the-date: Grantee Workshop, October 23-24, 2017 in Atlanta, GA
· Still finalizing logistics; no formal invitations yet
· Will send formal invitation with draft agenda and accommodation information within 1 – 1 ½ weeks
· Questions/Comments About Workshop:
· Elizabeth (Ohio): Will the letter state travel is grant requirement? 
· Monica: Case-by-case basis; if needed for travel approval, can draft and send out
· Any feedback for specific topics/content for workshop?
· Portion of the agenda will be allcoated to define national evaluations framework
· Flexible in terms of content and discussions
· Please send any requests to Monica in the next few weeks

· Reminder: Have done site visits in the past – if interested, let us know

Overview of Projects from Grantees - 
· Maine (Johanna):
· Internship posted last week for student help (5-6 applicants so far)
· Will work mid-September – June 2018, 10 hours/week
· Estimated hire date of September 18th

· North Dakota (Tracy):
· 2 students went to 2-3 fairs in state to make observations 
· # people in barns, strollers, not washing hands, etc.
· Completed job description, will be looking for student to help with coordinating efforts, 10-12 hours/week
· Meeting with Department of Agriculture, 4-H, and NDSU Extension next week
· Will start organizing how they are going to move forward


· Kentucky (Johnathan):
· Started meeting with 4-H and University partners
· Have student who will be helping with swine influenza education project
· Identified conferences for the fall with access to certified leaders who lead 4-H groups across the sate

· Michigan (Mary Grace):
· Working on financial arrangements with outside agencies who will be assisting (MSU Extension, MI Department of Agriculture and Rural Development, MI Association of Fairs and Exhibitions)
· Developed rough agenda for fall meetings with MI Association of Fairs and Exhibitions after conclusion of fair season

· Questions/Comments:
· Emily: Other states working with their association of fair/exhibitions in their states? 
· Carrie (Minnesota): Working with MN Federation of County Fairs; good working relationship
· Kristin (Iowa): Attending the International Association of Fairs and Exhibitions convention and trade show in November – will have booth in “ed. shed” and will be giving 15-minute presentation to promote their course

· Iowa (Kristin & Molly):
· Article in listserv to area professionals (Epi Update) about course
· Submitted abstract for the Applied Animal and Public Health Research and Extension Symposium
· Will be giving 20-minute presentation in San Diego in October 
· Will share information about upcoming presentations and abstract in Basecamp

· Minnesota (Carey):
· Ordering second half of educational board game for each county and regional office in next week or two
· Forthcoming: Anyone will be able to order the board game from manufacturer Game Crafter LLC (Madison, WI)
· Board game not specific to MN; if another state wants to use or adapt they can; will be bringing game to meeting
· Partnering with Upper Midwest Agricultural Safety and Health Center (UMASH) with focus on agritourism
· UMASH will be helping promote work with 4-H and board game

· Ohio (Andy):
· At Ohio State Fair:
· Had a booth, skill-a-thon station 
· Chapter sent to county educators, available for download
· Found out many youth still do not know what zoonotic disease is
· Final banquet for jackpot pig shows, awarded prizes to age category winners for Swinetist competition
· Education to audience of ~300 about influenza, passed out biosecurity buckets, glow germ activity
· Finished up 2 videos for social media, others in progress

· Questions/Comments:
· Emily: Provide description and feedback on public comments received on social media around perceptions about swine surveillance?
· Andy (OSU): Learned that public has hard time differentiating between Ohio state veterinarians and veterinarians at OSU
· Regulatory decisions made by Department of Agriculture had blowback on OSU; false headlines that barn at country fair was burned to the ground after pigs euthanized (false); barn was quarantined and pigs sent to harvest
· Push made to not get involved with any activities with OSU
· Set record straight; Ohio Department of Agriculture is now looking at changing some rules around swine exhibitions and including information about zoonotic disease for kids
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Additional questions or comments can be directed to mschroeder@cste.org, 770-458-3811.

