2017-2018 Influenza Education Among Youth in Agriculture Pilot Project

July 25, 2017, 3:00-4:00PM Eastern

CSTE - Monica Schroeder

CDC - Emily Lobelo, Joe Gregg, Grace Goryoka

NIFA - Lisa Lauxman, Amy McCune

APHIS – Tom Gomez

Iowa – Molly Lee (CFSPH), Andy Weigel (IDPH)

Ohio – Andy Bowman (OSU), Elizabeth Cross (ODH)

Minnesota – Carrie Klumb (MDH)

Michigan – Mary Grace Stobierski, Kim Signs (MDHHS), Jake DeDecker (MSU Extension)

Maine – Johanna Mackenzie (MECDC)

North Dakota – Tracy Miller (NDDoH)

Kentucky – Johnathan Ballard, Kelly Giesbrecht, Paul Royce (KY DPH), Ashley Osborne, Bob O’Brien (UK Extension)

- Project Overview (Emily):

  - CDC & CSTE facilitation of work at state level

    - Communication & outreach to individuals with high risk for zoonotic disease

    - Focus on youth agriculture

    - Partnership building element – state, federal, agriculture, health, youth agriculture; helpful when outbreak occurs

- Project Logistics (Monica):

  - Will be sending communications about calls and workshop; coordinating with contracts and progress reporting

  - Utilizing Basecamp portal – same one as last year (https://3.basecamp.com/3164497/projects/2026830)

    - Already invited point of contact for each group (look for email from notifications@3.basecamp.com)

    - Will send more detailed information on how to access

    - Sharing platform for resources between project partners

      - Will contain call summaries and reporting templates

    - Working on public-facing platform

    - Please post material; use private chat; add other collaborators from your team

  - Next progress report due October 31st

    - Will be sharing template; please document accomplishments, challenges, timeline changes, and impact of projects

  - Monthly conference calls – 4th Tuesday of each month at 3pm Eastern

    - Any ideas for topics or discussion, reach out to Monica to set up on upcoming call agenda

- Save-the-date: Grantee Workshop, October 23-24, 2017

  - In Atlanta, GA

  - Will get agenda and documentation for travel out ASAP

  - Jonathan: Do you anticipate the meeting start Monday morning or afternoon?

    - Plan to start Monday morning, but open to feedback

- Overview of Projects from Grantees –

  - Iowa (Molly): 3 major goals

    - Enhance existing online course made from last year’s grant

      - Course very well received, few issues with browsers and certificates – addressed. Will hopefully be updated with OIE logo - help with reach and credibility.

      - Next step - Pursue national 4-H development standards and hope to put into national 4-H curriculum.

    - Outreach and promotion and distribution of existing course in Iowa and nationally

      - Hosted exhibit tables: Iowa FFA state convention; Iowa Association of Ag Educators; worked with Dr. Bowman in Ohio to promote course at World Pork Expo; students were able to take course on site using tablets

        - Booth at Iowa Immunization Conference

        - Have banner, flyer, stickers; handing out with letter; materials that reach both kids and adults

        - Feedback: People are adding to their curriculum

      - Been monitoring google analytics: Over 2900 unique page views, 47 states, DC, 32 countries

      - Planning on attending National FFA Conference in Indianapolis

      - International Association of Fairs & Expositions annual convention; presentation and booth

      - Before end of 2017 – National Association of Ag Educators; Association of Iowa Fairs; more events planned for 2018

    - Create course for younger students ages 7-12

      - Lower reading level, shorter courses; creating outline

Questions/Comments:

      - Emily: Please bring list of places you plan on attending to the workshop; Website: www.bluenotflu.org

  - Michigan (Mary Grace & Kim)

    - June: Michigan 4-H Animal & Veterinary science camps

      - High school 4-H students

    - Printing more signs to give out at more fairs

      - Have been asked for more!

    - Create two more lessons in the Animal Science Anywhere series

      - 6 already – as they are completed, they are put onto Michigan State University Extension Program’s website

    - Want to make three short 2 minute videos that will in general promote healthy habits with animals

      - Can be used in a variety of settings

        - 4-H meetings, on continuous loop

    - Biggest plan for fall – host meetings

      - Want to host a series of 6-7 regional meetings around the state that will bring together local fair boards, local vets that support local fairs, county DoH staff, state agricultural and DoH staff

        - Depending on locale, varying levels of relationships between health departments and agricultural fair boards

        - After fairs done this summer, we want to have debrief regionally and make sure that these people know each other on a face-to-face basis

        - Plan to host in October & November

    - On agenda for state’s annual fairs & expo conference in January

      - Presentation

    - Host a training for fairs that will tell them how to set up the fair to prevent disease, educate about zoonotic diseases

      - Contemplating the use of IAFE consumer protection program – Wondering if anyone in call is familiar with it or used it?

Questions/Comments

      - Kerry (Minnesota): Have program started in 2013 called Healthy Fairs Workshop – use One Health perspective; co-hosted by board of animal health, health department, and environmental health

      - Jake (Michigan State University): New contact for Michigan 4-H

      - Emily: MI last year put work into action around flu – MMWR and one in works looking at knowledge, attitude and behaviors; MI project helped justify budget for public health for these projects; as much as possible, publication for public health or education; present at conference/poster

      - Mary Grace: Relationship between MSU 4-H; key to helping work with fairs and human surveillance

  - Minnesota (Carrie):

    - Working on continuing the Healthy Fairs Workshop

      - Planning on doing two more

    - Switching focus a bit; have good relationships with the county fairs based off workshops

      - Now go to their annual conference - MN Federation of County Fairs

      - Mini workshop focused on agritourism; help from 4-H

    - Make educational videos

      - Made three last year with grant

        - New videos will focus on biosecurity for kids (PPE) and food safety for 4-H participants

    - Last year created educational board game

      - Did not have enough to buy for every county

      - Will be able to supply each county and regional office this year

    - Developing curriculum on USB for clubs with poor internet access to go out with game

    - Continuing from last year - emerging issues breakfast

      - Feedback – participants want twice a year if possible

        - People will take turns hosting

        - All One Health partners invited – MN Milk, beef council, university, 4-H, FFA, governmental agencies (animal health, department of agriculture), humane society

          - Talk about things people are working on and see where they can collaborate and leverage funds

          - Buy-in from groups to help host so it’s not just them providing the breakfast

    - Borrowing from MI – Zoonotic Toolkit

      - Planning on using a few of the already developed lessons and going to create new lesson plans (will end up with 4 lessons in toolkit)

    - 4-H Science of Ag Challenge

      - Clubs participate

      - Students tackle question in any area of agriculture

        - Work with adult mentor

        - Present at end of year and compete for scholarships

        - Would like to have directed zoonotic public health challenge

          - Provide some funds from grant to help complete project?

          - Ex: Tested turkey bedding; how to attract zombie bees away from hives

        - Provide structure for mentoring program; public health/other governmental agency that wants to be mentors to sign up; would provide material for expectations and ideas; check-ins throughout working relationship

Questions/Comments:

- Emily: Work on cross-coordination to help states who are just starting so that they do not have to start from scratch.

  - Ohio (Andy): 3 objectives

    - Last year:

      - Developed zoonotic chapter for swine 4-H resource handbook

        - Rolled out and developed skill-a-thon station

        - Being used at Ohio State Fair this year

      - Zoonotic influenza transmission

        - Beyond county fairs – jackpot shows

        - Need to get education out to professional showmen

        - Affect change there, see trickle down to local level (emulate peers)

    - Pilot program - Becoming a “Swine-tist”

      - Partnered with Ohio Pork Council

      - Host annual jackpot show circuit in spring

        - Hosted training session at one of the shows, provided material from previous years/other states

        - Launched web platform on healthy habits

        - Post selfies doing healthy habits with their animals (ended July 15th)

          - Received ~70 selfies

          - Will send out prizes

    - Move educational component to more national presence

      - Attended World Pork Expo

        - Booths with different hands on activities to engage with the youth

        - Passing out popsicles, need to wash their hands. Made simple hand wash station

        - Had clean and dirty line and boot covers; teach basic biosecurity

        - Biosecurity buckets/kits (MI) and passed them out. Made over 1000 that day

        - Snot swap game - teaching how virus can spread through population of pigs and trace back. Trying to interest careers in public health and animal health

          - Stuffed pigs test for flu – sample pig and test them at the makeshift lab. Lots of positive feedback from folks there, educators, take things back to their local classrooms and clubs

        - Noticing lots of people with stickers on their show boxes – making change!

  - North Dakota (Tracy):

    - First year of funding

    - Some things done so far:

      - Did some basic preliminary observation work at a couple of fairs

        - General ideas on the number of people in the fairs

        - Did fairs have required signage

        - Did fairs have hand washing stations

        - Number of people going into barns/number of people with strollers in the barn

      - Over fall and winter, will be trying to meet with ag department and ND Association of Fairs and 4-H groups

        - Use materials found here to bring more awareness to what you should and should not be doing at fairs

  - Maine (Johanna):

    - Submitted updated timeline and awaiting contract

    - Ideas:

      - Have had success with train-the-trainer program for Lyme disease

      - Looking to model that with this program; train youth leaders beginning in fall-winter and have them report back to their clubs

  - Kentucky (Johnathan):

    - First year of funding

    - Collaborating with University of Kentucky and Kentucky 4-H Youth Foundation

      - 4-H already has certified livestock leadership program

        - Leaders throughout the state become certified in barn handling

      - Opportunity to get involved with train-the-trainer program

      - Start of One Health Initiative

        - Holding meetings quarterly

        - Last meeting presented information on poultry salmonella outbreak and Zika pregnancy registry

Questions/Comments

- Emily: Would like continued feedback if call is good format. We have set up recurring monthly calls based on feedback received last year.  Want to facilitate information sharing opportunities.

--

Additional questions or comments can be directed to mschroeder@cste.org, 770-458-3811.