1) List project deliverables and describe progress made towards completion of these deliverables:  

· Deliverable 1: Maintain and promote existing courses and supplemental material

Accomplishments: Modified the existing online courses to remove references specifically to Iowa so that the course is more "generic" for use by multiple states. Modified the last page of the courses to redirect to a page external to the course where users can select which state or group they are from, which will allow us to have multiple/different surveys for different states, but still allow us to track this data. Created a Nebraska-specific webpage similar to www.bluenotflu.org (this allows us to still track usage data of the course, but target the page specifically towards NE users which was important to NE). Obtained IRB approval (IRB ID 19-220) to publish youth engagement activities and results from evaluation components.

Did this deliverable include an educational intervention: Yes 
(If Yes, please complete the Impact Chart appended to this report.) 

· Deliverable 2: Conduct outreach to youth by using the courses and hands-on activities developed by CFSPH, other states, and CDC during previous funding cycles 

Accomplishments: Outreach was performed at the following events: State FFA Convention, World Food Prize Iowa Youth Institute, Iowa 4-H Youth Conference and Animal Science Roundup, ISU Undergraduate Underrepresented Veterinary Internship Program (UVIP), and Story County Fair. For all events, participants were either provided information about the course in the form of a flyer and in-person reference (State FFA and Story Co. Fair) or were required to take the course, as well as a pre- and post-course survey, before attending the event (World Food Prize immersion, Iowa 4-H Youth Conference and Animal Science Roundup, and UVIP). During the events, in-person activities were performed with the students (e.g., mucous swap, PPE activity, glo germ activity) and associated learning objectives were discussed. Students had the opportunity to engage with the presenter(s) and ask and answer questions.

Did this deliverable include an educational intervention: Yes
(If Yes, please complete the Impact Chart appended to this report.) 

· Deliverable 3: Conduct outreach, support, and training to adults by using the materials developed during previous funding cycles and expanding training materials to build capacity and ability for others to train youth

Accomplishments: Outreach was performed at the ISU Extension and Outreach Annual Conference Learning Fair, and a train-the trainer session was held at the Midwest Vet Conference in Ohio. A presentation was delivered during the March monthly call to project partners on Iowa's experiences with reaching older youth and identifying and leveraging funding sources. CFSPH engaged with adult mentors/teachers at the World Food Prize Iowa Youth Institute to offer materials and support for use in their classrooms. 

Did this deliverable include an educational intervention: Yes
(If Yes, please complete the Impact Chart appended to this report.) 

2) List the collaborators involved and briefly describe their role in the project (i.e. 4H, State PH, State Animal Health).
a. Iowa FFA – partnered to host workshop including hands-on activities at State Convention about the Excellence in Exhibition Course
b. ISU Extension and Outreach – partnered to host an exhibit at the Annual Conference during the Learning Fair about the Excellence in Exhibition course
c. World Food Prize Iowa Youth Institute – partnered to host two immersions with hands-on activities for youth about the Excellence in Exhibition course
d. Nebraska – using Excellence in Exhibition course in their outreach
e. Iowa 4-H Youth Conference and Animal Science Roundup – partnered to host four sessions of hands-on activities for youth about the Excellence in Exhibition course
f. ISU Undergraduate Underrepresented Veterinary Internship Program – partnered to host hands-on activities and activity for underrepresented undergraduate students about the Excellence in Exhibition course 
g. Story County Fair – partnered to host an immersion activity for youth about the Excellence in Exhibition course

3) Describe areas of concern or challenges in meeting the objectives or providing deliverables.
a. We pursued external funding to be able to hold 1-2 Biosecurity Camps for youth. However, because we were not able to identify a mechanism to fund personnel time to develop agendas and activities, facilitate the events, and collect and report any evaluation data collected, we were unable to complete this outreach activity (was included as an additional objective contingent upon receiving external funding). 

4) Include an updated project timeline, if relevant.

	February 1- April 30, 2019
	· Maintained and promoted existing courses and supplemental material
· CFSPH made course edits as appropriate to maintain content accuracy and timeliness.
· CFSPH continued to host and maintain the courses on the current website, ensuring that software and programming are kept updated to allow continued access for a variety of users (including common mobile devices and laptops/computers) to courses and website content, and work with users to address any problems with content access and usability. 
· CFSPH distributed and collected evaluation data from course use, as well as selected in-person events, and  analyzed and reported to other states, CSTE, and CDC any pertinent information gained from the evaluations via monthly update calls. CFSPH will revise the evaluation component as necessary to collect the most useful data to improve the course.
· CFSPH continued to track and report to other states, CSTE, and CDC visits to the course webpage and the courses themselves via monthly update calls, to monitor the need for and impact of these materials
· Conducted outreach to youth by using the courses and hands-on activities developed by CFSPH, other states, and CDC during previous funding cycles
· CFSPH held interactive workshops to directly reach our target audience of Iowa youth as we did in the previous year at Iowa 4-H State Conference and Animal Science Roundup. During the workshops, we shared some of the hands-on activities developed by CFSPH, other states, and CDC in previous years. Workshops were held during the following events:
· Iowa FFA Association Leadership Conference and State Convention (2019)
· World Food Prize Iowa Youth Institute (WFP IAYI)
· Iowa 4-H Youth Conference and Animal Science Roundup (IYC ASR)
· ISU Undergraduate Underrepresented Veterinary Internship Program (UVIP)
· Story County Fair
· In order to participate in the workshop at the WFP IAYI, IYC ASR, and UVIP participants were required to complete the online course ahead of time, including the evaluation component that was developed in 2018. 
· CFSPH pursued additional funding sources to develop, implement, and facilitate 1–2 biosecurity camps for middle–high school aged youth, to be held at Iowa State University, in partnership with previously engaged Iowa 4-H and Iowa FFA partners. No additional funding was secured. 
· Conducted outreach, support, and training to adults by using the materials developed during previous funding cycles and expanding training materials to build capacity and ability for others to train youth
· [bookmark: _GoBack]CFSPH held a train-the-trainer session at the Midwest Vet Conference in Ohio. 
· CFSPH continued to initiate contact with and offer support to Iowa 4-H leaders, County Youth Coordinators, Agricultural educators, and other adults to facilitate use of the courses in their youth outreach and education.  
· CFSPH continued to support health and agriculture departments, educational institutions, and other organizations in other states and regions in adopting and adapting the courses for youth education in those areas.

	May 1- August 30, 2019
	· Maintained and promoted existing courses and supplemental material
· CFSPH continued to make course edits as appropriate to maintain content accuracy and timeliness.
· CFSPH continued to host and maintain the courses on the current website, ensuring that software and programming was kept updated to allow continued access for a variety of users (including common mobile devices and laptops/computers) to courses and website content, and work with users to address any problems with content access and usability. 
· CFSPH worked with CDC and CSTE to continue to participate in any evaluation framework to assess implementation of the project on a national level.
· CFSPH continued to collect, analyze, and report to other states, CSTE, and CDC any pertinent information gained from the evaluations. CFSPH revised the evaluation component as necessary to collect the most useful data to improve the course.
· CFSPH continued to track and report to other states, CSTE, and CDC visits to the course webpage and the courses themselves to monitor the need for and impact of these materials.
· CFSPH requested Institutional Review Board (IRB) review and was granted IRB Exempt status (Iowa State University IRB ID 19-220). IRB provided feedback on best practices for collection and use of data collected in the pre- and post-surveys administered to course and workshop participants, and surveys administered as a part of this grant were in compliance with these practices.
· Conducted outreach to youth by using the courses and hands-on activities developed by CFSPH, other states, and CDC during previous funding cycles.
· CFSPH held interactive workshops to directly reach our target audience of Iowa youth as we did in the previous year at Iowa 4-H State Conference and Animal Science Roundup, ISU Undergraduate Underrepresented Veterinary Internship Program (UVIP), and the Story County Fair. During the workshops, we shared some of the hands-on activities developed by CFSPH, other states, and CDC in previous years. In order to participate in the workshops, participants in the Iowa 4-H State Conference and Animal Science Roundup and UVIP were required to complete the online course ahead of time, including the evaluation component that was developed in 2018. Participants at the Story County Fair received a flyer and/or in-person reference to the course. Hands-on, interactive workshops were held during the following events:
· 4-H State Conference and Animal Science Roundup
· UVIP
· Story County Fair
· Conducted outreach, support, and training to adults by using the materials developed during previous funding cycles and expanding training materials to build capacity and ability for others to train youth.
· CFSPH submitted an application for presenting an interactive workshop including recommendations for using the courses within the 4-H curriculum during Youthfest, the annual conference for 4-H County Youth Coordinators and staff in Iowa. 
· CFSPH continued to initiate contact with and offer support to Iowa 4-H leaders, County Youth Coordinators, Agricultural educators, and other adults to facilitate use of the courses in their youth outreach and education.  
· CFSPH continued to support health and agriculture departments, educational institutions, and other organizations in other states and regions in adopting and adapting the courses for youth education in those areas.
· CFSPH developed a series of demonstration videos to supplement the hands-on activities associated with the Excellence in Exhibition course, and posted these on the course website at www.bluenotflu.org



5) If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mhuynh@cste.org. 
a. All materials are posted to the Basecamp site.

6) List suggestions for CSTE and CDC for how we can best facilitate your progress.
a. Continued assistance in promoting the course at the national level would be valuable.

7) List any topics or questions you would like to add for discussion on an upcoming all-site conference call.  
a. None

8) Would you like to request an extension on your contract? If so, please provide an estimated project end date in which all activities and deliverables will be completed.  Please note, this does not guarantee approval of extension.  Additional information may be requested, as relevant, including revised workplan, timeline, and budget.  CSTE will be in touch following review of your report to discuss next steps for contract amendment. 
a. An additional extension is not requested. 

OPTIONAL (but please complete if relevant)
If you have a story or anecdotal example of how an individual, group, or community was positively impacted OR an outbreak response that was better facilitated as a result of your YIA project’s interventions, either describe it here or just write ‘YES’ and we will follow up with you at a later date.  These ‘success’ stories combined with quantitative impact numbers will be used to share project successes with leadership. 


YES
Example from Story County Fair—email received from colleague involved with the fair:

Influenza and Zoonoses Education among Youth in Agriculture
Final Report
Jurisdiction: Iowa (Submitted by ISU CFSPH) 
Date: August 30, 2019

“I have received lots of positive feedback from your biosecurity workshop that you conducted for the poultry kids at the fair. There have been many kudos and much appreciation expressed. Some of the adults that attended the workshop are 4-H supervisors and/or on the Fair Board and were checking it out. Your workshop was discussed in the Board meeting and now the Board is inquiring about your willingness to put on a bigger workshop for the 4-H kids in the pavilion next year. They want ALL the kids to attend and learn...they really were taken with your excellent work!”
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Impact Chart 
If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report
	Impact 
	Evaluation

	Intervention Activity
	Baseline #  prior to 2018-19 grant period
	How did you measure the baseline? Did you include direct participants, families, etc?
	2018-19 Audience (youth, community leaders, etc?)
	# of attendees/participants
	# of materials distributed
	



Did you collaborate with another state? If so, which one(s)?
	Pre-test administered? (How many? To whom?)
	Post-test administered? (How many? To whom?)

	EXAMPLE: Four Scenario based training exercises
	X# of training sessions held in 2016 to X total youth aged 11-15
	Only counted the number of actual youth who attended  the session
	Youth aged between 12 and 16
	X # attendees per training; total of X attendees
	
	
	
	

	NA

	Website was viewed 4,617 times by 3,698 unique users, and the online course was accessed 1,755 times by users in 44 states during the previous funding period (May 1, 2017–Dec 28, 2018).
	Counted unique users/views (did not count multiple views on same computer)

	Target audience is youth aged 13–18 years for the middle/high school course and aged 7-12 years for the elementary course but is open to anyone freely on the website
	As of August 2019, the middle/high school course was accessed 2,296* times by unique users in all 50 states. The elementary course was accessed 367 times by unique users in 37 states.

	NA

	Course available nationally 

Worked directly with NE to create a landing page specifically for their target audience and to create a Google survey specific to their audience.
	NA

	NA


	Eight activity-based workshops

	In previous funding cycles, 5 activity-based workshops were held in conjunction with the Iowa 4-H Conference and Animal Science Roundup, and one workshop with the East Iowa Extension FSQA. 

Number of workshop participants totaled over 300 people in the previous funding periods.
	Only counted the number of individuals who attended the workshops

	
High school aged FFA members 

High school aged WFP participants

	
State FFA workshop with interactive activities – 130 participants

Immersion interactive activity for youth at the World Food Prize Iowa Youth Institute (WFP IAYI) –  60 participants
Iowa 4-H Youth Conference and Animal Science Roundup (IYC ASR) – 78 participants
UVIP – 8 participants
Story County Fair – 20 participants

Number of participants attending workshops this project period totaled approximately 300.


	45 Biosecurity Buckets

Promotional flyers and educational handouts on disease prevention
  
Promotional stickers

	NA

	A pre-course survey was distributed to all participants in the WFP IAYI (41 students), IYC ASR (78 students), and UVIP (8 students)

	A pre- and post- course survey and a post-activity evaluation was distributed to all participants in the WFP IAYI (41 students), IYC ASR (78 students), and UVIP (8 students)


	One interactive booth 

One webinar 

One train-the-trainer seminar

One activity-based workshop

	In previous funding cycles, booths have been hosted at 7 events, one webinar was delivered, one train-the-trainer seminar was delivered, and 5 activity-based workshops were held.

	Only counted the number of individuals who attended the workshops

	Extension personnel

	Learning Fair at the ISU Extension and Outreach Annual Conference – 450 attendees

50 participants at the train-the-trainer seminar

Webinar with project partners from 8 states, CDC, and CSTE

16 adult mentors/teachers at  WFP IAYI activity-based workshop

	Electronic resources distributed

	National audience for webinar and train-the-trainer

	NA

	NA




