## Project Timeline
Youth in Ag Grant- MN Project Timeline
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE
2016-07-14 | Board game pilot with MDH staff | 25 | 1
2016-07-29 | Educational videos completed | 15 | 1
2016-08-01 | Board game pilot with middle schoolers | -10 | 1
2016-09-15 | PowerPoints for 4H curriculum completed | -10 | 1
2016-09-30 | 4H instructor manual complete | -15 | 1
2016-09-28 | Agritourism workshop | 15 | 1
2016-10-12 | Board game produced | 25 | 1
2016-10-21 | Ag Youth in Health Day | -15 | 1
2016-11-15 | One Health Annual Meeting | 15 | 1
2016-12-30 | Completion of e-learning Voluntary Certification Program | -10 | 1