Influenza Education among Youth in Agriculture Progress Report 


Please return completed Progress Report to CSTE at mschroeder@cste.org.  


1. Identify your top three achievements over the last quarter. 
a. Hosting a successful Healthy Fairs Workshop at the end of April. Six different county fairs as well as 4H were represented at the workshop. There was great discussion amongst the different fairs and each fair was able to self-identify things they needed to change in order to be following the Compendium guidelines.
b. The content for the Voluntary Certification Program was completed. There are ~115 slides, which include graphics, a video, and quizzes. All of this content is now being put into Captivate, an e-learning platform. 
c. Creating a prototype of an educational board game, that is part of the 4H curriculum and getting two educational videos scripted and filmed. 

2. Please list collaborators on this quarter’s achievements, and briefly describe roles of different organizations involved (i.e. 4H, State PH, State Animal Health)
a. [bookmark: _GoBack]Minnesota Board of Animal Health (MBAH) co-hosted the Fergus Falls Healthy Fairs Event on April 28, 2016. 
b. MDH- completed content and now working on producing voluntary registration program on-line using Captivate (e-learning platform).
c. MDH- prototype of educational board game has been produced. Pilot testing will follow
d. MDH- two educational videos have been shot and are now in the editing phase.


3. Please describe any areas of concern or challenges to meeting the objectives or providing deliverables.
a. Time to work out these outreach activities due to competing interests (animal contact outbreaks, routine surveillance, rabies surveillance, etc.).
b. Difficulty finding a time that works well for our 4H partners to meet with us to discuss the details of the curriculum. 

4. Please include an updated project timeline.
See attachment	

5. If you have materials you are already distributing, please include a sample PDF or link of those materials.
a. Have Fun and Stay Safe on the Farm – handout to be used to educate visitors at public animal contact venues.
b. Petting Zoo Checklist- This is a distillation of the Measures to Prevent Disease
Associated with Animals in Public Settings, 2013 Compendium.


6. Please list any suggestions for CSTE and CDC for how we can help best facilitate your progress.
It would be great if we had longer to spend the money. Right now as it stands, we only have 6 months left to get all of these relationships built and outreach activities planned. It’s a very short timeline to do all of this. If the money could be extended into next year that would be really helpful. 


7. Please complete the attached spreadsheet, to indicate progress made towards project deliverables.  


