Influenza Education among Youth in Agriculture
Progress Report 


Please return completed Progress Report to CSTE at mschroeder@cste.org.  

1. Identify your top three achievements over the last quarter. 
a. Hired project coordinator for project, whose main responsibility will be coordination and planning of the One Health Exploration Day 
b. Developed draft agenda (see attached) for One Health Exploration Day—to be held on Tuesday August 16th—and outlined detailed timeline for material creation and communication with key partners. Planning calls have been hosted with project team. Email has been sent out email to invite human, animal, and environmental health partners to participate in the One Health Exploration Day. Partners have been asked to develop and lead an interactive and educational activity (module) for youth in attendance. 
c. Developed One Health fact sheet and One Health logo contest guidelines. Disseminated to youth organizations and statewide partners. Due by July 8th. 

2. Please list collaborators on this quarter’s achievements, and briefly describe roles of different organizations involved (i.e. 4H, State PH, State Animal Health)
- Arizona Department of Health Services: main leader for project activities, 	coordinating and developing structure and objectives for One Health Exploration 	Day and One Health outreach in Arizona. Identification and bringing together 	of key partners for One Health and zoonoses prevention and response are 	conducted by ADHS. Social media messaging created by ADHS and sent through 	ADHS housed platforms (Facebook, website, director’s blog).
-Maricopa County Department of Public Health: secondary lead for project 	activities and plays large role in developing and implementing outreach 	objectives for One Health message. 
-Arizona Department of Agriculture: participatory role in project activity 	development and outreach.
-Arizona Game and Fish Department: participatory role in project activity 	development and outreach.
-USDA Wildlife Services: participatory role in project activity development 	and outreach.
-Midwestern University College of Veterinary Medicine: veterinary student was 	hired as project coordinator and lead planner for the One Health Exploration 	Day. 





3. Please describe any areas of concern or challenges to meeting the objectives or providing deliverables.
· At this time, the project team has not identified any concerns of challenges with meeting objectives or deliverables. Much of our work currently is in preparation for the One Health Exploration Day. As the weeks pass, we will need to rely on our partner agencies to meet deadlines given for development of activities and will need to rely on their ability to submit all required plans, outlines, and materials.

4. Please include an updated project timeline (see below, only included relevant components). 
[bookmark: _GoBack]
Ongoing throughout Grant Period
· Key partners from Arizona Department of Health Services, Arizona Department of Agriculture, Arizona Game and Fish Department, Maricopa County Department of Public Health, Midwestern University College of Veterinary Medicine meet on a monthly basis via teleconference to plan deliverables throughout grant period. 
· Social media (every other week) and blog posts (once a month) for One Health and zoonotic disease awareness and prevention

May-June 10 2016 –completed 
· Collected contact information for schools and youth programs
· 4-H
· FFA
· Girl Scouts, Boy Scouts, Cub Scouts
· Big Brothers, Big Sisters
· Science clubs
· Camps (science, health, wildlife)
· Created guidelines for One Health Logo Contest due July 8th 
· Disseminated to youth organizations and through local partners
· Development One Health Fact Sheet
· Drafted agenda for One Health Exploration Day including brainstorming specific activities to be hosted during event (August 16th)
· Key partners in One Health (Arizona Department of Health Services, Arizona Department of Agriculture, Arizona Game and Fish Department, Maricopa County Department of Public Health, Midwestern University College of Veterinary Medicine) were invited to participate in the One Health Exploration day as panelists and leaders of activities (draft due June 20)

June- July 2016
· Continue organization of activities and material development for One Health Exploration Day including booklets, jeopardy questions, disease detective glow germ activities, scenario development for break-out exercises, and pre/post evaluation questions to assess knowledge of participants/evaluate learning experiences
· Create and disseminate application for One Health Exploration Day
· Order supplies for One Health Exploration Day

August 2016
· Finalize and host One Health Exploration Day (August 16)
· Analyze and compile pre/post evaluation data, highlighting original gaps in knowledge and areas of improvement. Share report with key partners 
· Host a hot wash with planners and facilitators for One Health Exploration Day

September-December 2016
· Develop building blocks for One Health training module to be shared online with activities and curriculum for youth
· Create guidelines for One Health essay OR poster contest how to be “SAFE” around animals, announce and host
· Coordinate meeting with leadership from youth agriculture and science/health/animal groups to plan for sustainability

5. If you have materials you are already distributing, please include a sample PDF or link of those materials.  

One Health Fact Sheet is being finalized for distribution. We also create bookmarks for zoonotic disease prevention, which are being finalized. Arizona will be able to share those within the coming weeks.

6. Please list any suggestions for CSTE and CDC for how we can help best facilitate your progress.

Arizona does not require additional assistance at this time. We are very excited about the work being conducted in the other states and are looking forward for the site visits from CSTE/CDC partners in August.

7. Please complete the attached spreadsheet, to indicate progress made towards project deliverables. 

See attached.

