Influenza Education among Youth in Agriculture
Progress Report - Michigan

Please return completed Progress Report to CSTE at mschroeder@cste.org.  

1. Identify your top three achievements over the last quarter. 
· Created three new Animal Science Anywhere lesson plans and submitted them to ANR Communications for editing and revisions.
· Created the Zoonotic Disease Prevention Presentations and have already presented in 4 different counties thus far and are continually scheduling additional presentations.
· Reprinted 300 “Be Healthy Around Animals” signs and have distributed many of the signs to county extension offices (2 per county), MDHHS offices and university farms and teaching centers.

2. Please list collaborators on this quarter’s achievements, and briefly describe roles of different organizations involved (i.e. 4H, State PH, State Animal Health)
· Michigan State University (MSU) Extension and Michigan 4-H: 
· Hired two recent MSU alumni to assist with the grant project. 
· Created three lesson plans focusing on careers in human and animal health, how influenza virus mutates, and the One Health initiative.
· Designed Youth Zoonotic Disease Prevention Presentation and refined it as needed. Have conducted four presentations thus far and have scheduled over 30 presentations in 13 out of the 14 MSU Extension districts.
· Created promotional materials to advertise the Youth Zoonotic Disease Prevention Presentations. 
· Conducted four presentations in different locations reaching 44 youth thus far.
· Applied for and received an additional $20,000 grant from the Michigan 4-H Participation Fee Grant to allow for increased outreach beyond the fourteen district presentations.
· Designed the card for the Pathogen Prevention Packages that each youth will take away along with supplies from the Youth Zoonotic Disease Prevention Presentations.
· Designed the 11x17 sign that will go through editing to remind youth how to practice biosecurity when returning from a fair or animal exhibition event.
· Worked with companies to arrange for estimates to fulfill printing needs and lesson plan supplies.
·  Worked with MDHHS to create the layout and verbiage of the pull-up banners.
· Continued to organize the third annual Michigan 4-H Animal and Veterinary Science Camp.
· Michigan Department of Health and Human Services (MDHHS): 
· Reviewed and helped finalized presentation, pull-up banner and lesson plan materials. 
· Presented at the CYI Spring Conference to help educate county 4-H program coordinators (program staff) on resources and concerns relating to zoonotic diseases.
· Began organizing session for 4-H Exploration Days.
· MSU Agriculture and Natural Resources (ANR) Communications: 
· Reviewed lesson plan content for one lesson thus far.
· Graphic designer created the pull-up banner.
· Neogen Corporation: 
· Donation of 800 gloves for the Pathogen Prevention Packets that are handed out to the youth at each presentation.

3. Please describe any areas of concern or challenges to meeting the objectives or providing deliverables.
· Scheduling: it has been difficult coordinating schedules for the presentations. Most counties already have events planned for the summer. If the grant would have been awarded earlier, this would have better fit the educational timeframe most counties are holding events.
· Existing knowledge: Both youth and adults have a very limited knowledge base relating to zoonotic diseases.  Therefore, many counties find it difficult to motivate youth to attend these events because they do not understand why it is important for their own health or animals.

4. Please include an updated project timeline.
· Attached in the email is a current timeline of our presentations and their locations through the month of August. 
· Timeline listed below indicates items that have changes in red.
	April-May 2016:  
	Develop curriculum for 4-H Exploration Days with partners
Develop curriculum for Veterinary Science Camp with partners
Design and print pull-up display 
Reprint and distribute “Be Healthy Around Animals” signage to Michigan Local Health Department, Fairs and MSU animal facilities

	March 2016:
	Begin process of hiring additional staff person for part-time

	April 26, 2016:
	Two presentations at 4-H CYI Spring Conference                      

	April-June 2016:  
	Develop 3 Animal Science Anywhere curriculum units

	April-June 2016:
	Design and print table top displays

	June 2016:
	Distribute pull-up displays

	June 22-23, 2016:  
	Present “Be a Disease Detective” session at 4-H Exploration Days

	June 27-July 1, 2016:  
	Michigan 4-H Animal and Veterinary Science Camp
· One Health focus to the camp with a special presentation from the CDC on June 27th 

	May-October 2016:
	Regional presentations throughout the state taught by part-time staff

	October 2016:
	Compile 2,000 zoonotic packages with supplies for lessons

	October 25-26, 2016:
	Distribute Zoonotic Disease Prevention Packages to leaders 

	January 12-14, 2017:
	Distribute table top displays to Michigan Association of Fairs members *No charge to grant



5. If you have materials you are already distributing, please include a sample PDF or link of those materials. 
· In the Pathogen Prevention Packets include 4 purple nitrile gloves, 4 polyboots, 2 hand sanitizer wipes, and 1 card that explain how to use the items in the packets.
· The “Be Healthy Around Animals” signs are in the final stages of being distributed. 
· The pull-up banners are printed and in the process of being distributed to each MSU Extension district in Michigan.
· [bookmark: _GoBack]Promotional flyer for Youth Zoonotic Disease Prevention Presentations (editable design). 

6. Please list any suggestions for CSTE and CDC for how we can help best facilitate your progress.
· Have a staff member at the CDC or CSTE that would be willing to review content of created curriculum. This would ensure a unified national message while taking some stress off of grantees.
· Offer the grant in the fall to better meet 4-H staff and leader schedules.
· Consider allowing the grant to go to two sites – example MDHHS and MSU Extension to avoid additional paperwork for staff.
· Increase the notification timeline so that progress can begin more rapidly on grant objectives based on a December deadline.

7. Please complete the attached spreadsheet, to indicate progress made towards project deliverables.
· Please see attached file.
