Influenza Education among Youth in Agriculture
Progress Report 


Please return completed Progress Report to CSTE at mschroeder@cste.org.  
1. Identify your top three achievements over the last quarter. 
A. IDPH and CSTE executed contract 
B. IDPH and Center for Food Security and Public Health (CFSPH) executed contract
C. Center for Food Security and Public Health conducted and summarized agriculture educator and youth in agriculture focus group surveys and began developing content for six online modules. 
2. [bookmark: _GoBack]Please list collaborators on this quarter’s achievements, and briefly describe roles of different organizations involved (i.e. 4H, State PH, State Animal Health)
The focus of the work this quarter was on product development. Once the Center for Food Security and Public Health has fully developed draft products, the Iowa Department of Public Health, Iowa Department of Agriculture and Land Stewardship, 4-H and FFA partners will review the materials and provide input.  
3. Please describe any areas of concern or challenges to meeting the objectives or providing deliverables.
No challenges or concerns have been identified at this time. 
4. Please include an updated project timeline.
	Present–June 30, 2016
	· Conduct  ag educator and youth focus group surveys; summarize findings
· Explore and determine different web-based course delivery options
· Hold technology development meetings to determine best method of course delivery and evaluation component
· Develop module content outlines and learning objectives for modules 1–6
· Research and draft content for modules 1–3
· Circulate outline, learning objectives, and draft content for review by IDPH, CFSPH, 4-H and FFA staff for modules 1–3

	July 1–August 31, 2016
	· Determine interactive elements needed for modules 1–3
· Research and draft content for modules 4–6
· Determine interactive elements needed for 4–6
· Circulate outline and learning objectives for review by IDPH, CFSPH, 4-H and FFA staff for modules 4–6
· Begin web module design and programming

	September 1–October 31, 2016
	· Finalize content for all modules
· Continue with technology development and course design
· Populate web pages with content, graphics, and interactive elements
· Circulate all module content for review by IDPH, CFSPH, 4-H and FFA staff
· Incorporate evaluation component into modules
· Begin drafting supplemental module content (handouts, instructor guide, signage, etc.)

	November 1–December 31, 2016
	· Finalize six web-based modules
· Complete supplemental materials based on module content (handouts, instructor guide, signage, etc.)



5. If you have materials you are already distributing, please include a sample PDF or link of those materials. 
No completed materials are available at this time. 

6. Please list any suggestions for CSTE and CDC for how we can help best facilitate your progress.
None. 
7. Please complete the attached spreadsheet, to indicate progress made towards project deliverables.  


