## Sheet1
Please describe the progress made towards completion of the following project deliverables. | Outputs (What activities have happened over the past 3 months? What materials have been developed or produced as a result?) | Outcomes (What is the impact and reach of these activities? How have these activities addressed one or more of the project objectives? 1. Improve participant awareness and knowledge of zoonotic diseases, including zoonotic disease transmission and prevention, 2. Increase participant awareness and knowledge of careers in public and animal health, 3. Facilitate a better understanding among participants of the role public and animal health play in disease prevention, 4. Motivate participants to adopt behavior that can help prevent zoonotic disease transmission, 5. Develop relationships among stakeholders that could be used to facilitate more effective and efficient responses to important public and animal health issues (e.g., the response to infectious disease outbreaks or epidemics))
1. Web-based, interactive educational modules addressing zoonotic disease prevention and biosecurity measures | Web-based course delivery options were explored, and CFSPH content creators met with technology designers to determine the best mode of course delivery. Outlines, learning objectives, and content were drafted for: Module 1: Zoonotic Diseases and Risks Module 2: Zoonotic Disease Transmission Module 3: Biosecurity Outlines and learning objectives were drafted, and content development began for: Module 4: 2015 HPAI Case Study, Module 5: Influenza A Virus of Swine Origin (H3N2v) Associated with Animal Exhibitions Case Study Module 6: Animal and Public Health Agencies and Careers | Content development continues for all six modules. Module 1 will describe zoonotic diseases, their importance, and risk factors for infection. Module 2 will describe the five routes of disease transmission, provide examples of zoonotic diseases transmitted by each route, and offer suggestions for prevention of disease transmission. Module 3 will teach users the importance of biosecurity and describe measures that can be taken to prevent disease transmission to people and animals on farm and at exhibitions. Module 4 will describe the 2015 highly pathogenic avian influenza outbreak and its impact on animal agriculture and potential impact on public health. Module 5 will describe the H3N2v influenza outbreak associated with swine exhibitions and prevention measures exhibitors should take. Module 6 will introduce users to agencies involved in animal and public health and career opportunities for those interested in animal and public health.
2. Development of supplemental materials on zoonotic disease prevention and biosecurity measures | Ag educators and youth involved in animal agriculture in Iowa were surveyed to determine the most useful supplemental teaching tools and materials. The results of these surveys were summarized. | Supplemental materials for all modules will be developed to support classroom education or zoonotic disease preventive practices. Supplemental materials will be developed for Module 1 relating to common zoonoses and the disease they cause in both animals and humans. Supplemental materials will be developed for Module 2 relating to the routes of disease transmission. Supplemental materials will be developed for Module 3 relating to biosecurity practices that should be implemented to prevent zoonotic disease transmission. Supplemental materials will be developed for Modules 4 and 5 to aid in classroom based or group instruction. Supplemental materials will be developed for Module 6 relating to animal and public health agencies and careers.