Influenza Education among Youth in Agriculture

Progress Report

Please return completed Progress Report to CSTE at mschroeder@cste.org.

- Identify your top three achievements over the last quarter.

- Shared materials piloted in 2015 with >300 youth attending the Ohio 4-H Conference and/or OSU Junior Swine Day.

- Developed messages to be distributed via social media the week prior to each county’s fair.

- Met with collaborators to develop a plan for writing project book chapter and creating and piloting skill-a-thon

- Please list collaborators on this quarter’s achievements, and briefly describe roles of different organizations involved (i.e. 4H, State PH, State Animal Health)

Ohio Department of Health:  Provided support and expertise for all other partners.

Ohio 4-H Youth Development: Enabled access to state 4-H Animal Science social media venues; disseminated a notice to all extension educators to make them aware of social media campaign; collaborated with AIEERP to develop a plan of action for writing project book chapter and skill-a-thon station.

Department of Agricultural Communication, Education, and Leadership: Assembled list of individual county’s social media pages and calendars of fair events; coordinated with AIEERP to develop social media messaging; and coordinated with 4-H to set up TweetDeck for disseminating messaging.

Animal Influenza Ecology and Epidemiology Research Program: Used educational materials piloted in 2015 to share with youth attending the Ohio 4-H Conference and/or OSU Junior Swine Day; coordinated with 4-H to develop a plan of action for creating skill-a-thon and writing book chapter; drafted letter to be sent to extension educators; and provided content to ACEL to create social media messages.

- Please describe any areas of concern or challenges to meeting the objectives or providing deliverables.

Presently, no concerns or challenges to meeting objectives are anticipated. We have progressed according to the proposed timeline and all collaborators and stakeholders have been supportive.

- Please include an updated project timeline.

Feb-16	        Apr-16        Jun-16         Aug-16       Oct-16            Dec-16

Present education at state wide youth meetings

Develop social media campaign

Implement social media campaign

Analyze Sysomos MAP data

Develop content for zoonotic disease chapter

Format, revise, edit zoonotic disease chapter

Develop skillathon station

Present education materials to Extension Educators

- If you have materials you are already distributing, please include a sample PDF or link of those materials.

Develop skillathon station

Social media messages are included on page 3-4

- Please list any suggestions for CSTE and CDC for how we can help best facilitate your progress.

N/A

- Please complete the attached spreadsheet, to indicate progress made towards project deliverables.

Hashtag: #4Hcares

Facebook Posts

Day 1

Is your animal sick? Did you know bringing a sick animal to the fair could spread diseases to other animals or people? Zoonotic diseases, like influenza, can spread between animals and people, so it is important to keep sick animals at home. Not only do sick animals need to stay at home but sick people need to stay home too, so they do not risk infecting other animals or people.

Day 2

Did you know that kids younger than 5 years, people 65 years and older, pregnant women, and people with certain long-term health conditions (like asthma and other lung disease, diabetes, heart disease, weakened immune systems, and neurological or neurodevelopmental conditions) are advised to avoid certain animals at the fair?

Day 3

How can you keep yourself and your animals healthy during the fair?

- Don’t eat, drink, or sleep in the animal barns

- Wash your hands frequently, especially after you’ve had animal contact

- Keep your animals and your area clean and dry

- If you are sharing equipment, like hurdles, clippers, halters, and brushes, clean and disinfect them between uses.

- Use precautions when caring for sick animals to minimize the opportunity for disease transmission to other animals or people.

Day 4

What if your animal gets sick during the fair? Evaluate your animal’s health daily.

  - Is your animal eating normally?

  - Is your animal coughing or having trouble breathing?

  - Does your animal have a fever?

  - Does it appear tired?

  - Does your animal have loose stool?

Report any illness to the fair veterinarian or the appropriate fairboard member so the animal can be evaluated.

If you feel ill, you should see your health care provider and tell them you’ve had animal exposure. Ill people with should stay away from animals until they are fever-free for at least 24 hours without the use of medication.

Day 5

What should I do after the fair?

- Isolate and observe animals returning to the farm daily for illness no fewer than 7 days after returning home and before allowing contact with other animals

- Clean and disinfect equipment, clothing, shoes, and vehicles/trailers that were at the fair.

- Consult a veterinarian if your animals become ill.

- Similarly, consult a health care provider as soon as possible if exhibitors or family members become ill.

Twitter Posts (140-character maximum) – include Bitlys if more info

Day 1

Bringing a sick animal to the fair could spread disease to other animals or people. Zoonotic diseases spread bt animals and people so keep sick animals at home. #4Hcares

Day 2

Kids under 5, people 65+, pregnant women and people w/chronic health conditions are advised to avoid certain animals at the fair #4Hcares

Day 3

Find tips to keep you and your animals healthy during the fair on the @Ohio4H Facebook page. Bitly…. #4Hcares #4H

Day 4

Learn more abt caring for sick animals @ the fair on the @Ohio4H Facebook page. Bitly…. #4Hcares #4H

Day 5

Home from the fair? Learn how to care for animals when you return. Bitly… @Ohio4H #4Hcares #4H