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Please return completed Progress Report to CSTE at mhuynh@cste.org.  


1. Identify your top achievements for the project. 
Through the Youth in Agriculture Grant, the Indiana State Department of Health (ISHDH) was able to establish new partnerships as well as strengthen existing partnerships with key stakeholders. This project has met a significant public health need by providing biosecurity education and resources. Top achievements include the “Teens as Teachers – Biosecurity” workshop as well as the distribution of improved biosecurity signage and handwashing stations to Indiana’s county fairs. 

2. Please list the collaborators on this project’s achievements and briefly describe their role in the project (i.e. 4-H, State PH, State Animal Health).

a. Indiana Association of Fairs and Festivals (INAF)
i. The INAF was instrumental in providing a platform to connect with fair organizers at the local level. Steve Patterson, the INAF contact, invited ISDH staff members to conduct a training on zoonotic disease transmission prevention at the annual INAF Convention attended by county fair organizers. During this convention, ISDH staff members also had the opportunity to manage a booth and provide information on safe animal exhibition practices. A contact list of fair organizers was provided by the INAF and used to disseminate the self-assessment. INAF also provided a training workshop to help fairs understand enteric pathogens, such as E. coli, and zoonotic influenza, such as swine influenza. Finally, the INAF purchased and distributed a total 12 handwashing stations among five Indiana counties. 
b. Indiana 4-H Youth Extension (4-H)
i. Indiana 4-H conducted the Teens as Teachers training to 4-H youth. This program was piloted when the CDC/USDA/CSTE Project Development Grant was first awarded to Indiana in 2014. The biosecurity and zoonotic disease workshop focused on variant influenza prevention and was presented to regional teams of 4-H participants. With the funds from this grant, 4-H expanded and enhanced the curriculum for this workshop. The workshop focused on incorporating engineering design and maker activities into the 4‐H Animal Science Program. Indiana 4-H also collaborated with the ISDH to design and distribute improved biosecurity signage for county fairs. 
c. Ohio State University College of Veterinary Sciences
i. Dr. Andrew Bowman shared programming materials and resources he and his colleagues developed at the Ohio State University. They have received the CDC/USDA/CSTE Project Development Grant award every year since 2014 and have implemented biosecurity workshops to teenagers in Ohio. Dr. Bowman shared some of his insight and provided suggestions for applying the content to Indiana. He also agreed to serve as a speaker at the Teens as Teachers training in 2019. 
d. Indiana Board of Animal Health (BOAH) 
i. The Indiana State Board of Animal Health provided several training tools and resources, including an interactive card game that was disseminated to 4-H youth. The team also collaborated with BOAH to develop biosecurity signage that was distributed across the state. BOAH provided input on messaging as well as layout/design and the final product displayed the organization’s logo alongside the ISDH and 4-H logos. 
e. Indiana State Fair Board
i. The Indiana State Fair Board provided valuable insight on biosecurity signage. We had productive conversations with them on both the content and design. The Indiana State Fair Board also displayed some of their own plans for revamped signage around the fairgrounds and solicited feedback from ISDH on the plans.

3. Please describe areas of concern or challenges in meeting the objectives or providing deliverables.
The biggest challenge faced in meeting the objectives/deliverables of this grant was staff turnover. At the ISDH, grant activities were led by one of the Enteric Epidemiologists and the Zoonotic/Vectorborne Epidemiologist. Both staff members departed the ISDH in August 2019 while grant deliverables were still in progress. Though team members were briefed on the status of grant activities as part of the transition, some details were omitted or not fully explained. As a result, the team members who took the lead were not aware of some proposed activities. For example, it was not communicated that money had been allocated for travel to attend 4-H biosecurity workshops. The money was ultimately allocated towards other activities, but there was a missed opportunity to observe those workshops.	

4. Please include an updated project timeline.
	Deliverable
	Date

	1. Expanded curriculum for annual 4-H “Teens as Teachers – Biosecurity” workshop via a partnership with Dr. Bowman and OSU.
	06/15/2019

	2. Pre-test/post-test for workshop participants to evaluate expanded 4-H curriculum.
	06/15/2019

	3. Materials for INAF workshop.
	01/04/2019

	4. State and county fair self-assessment and scoring rubric based on the Compendium of Measures to Prevent Disease Associated with Animals in Public Settings.
	02/01/2019

	5. Distribution of 12 handwashing stations and educational signage at local agricultural events in greatest need of assistance.
	02/29/2020

	6. Attendance of INAF staff at the IAFE training on zoonotic disease prevention.
	01/04/2019



5. If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424). For Basecamp access, please email mhuynh@cste.org. 

6. Please list suggestions and recommendations for CSTE and CDC for how we can improve support to future sites participating in the project.
Based on the ISDH experience with this grant, there are a few recommendations for future grant cycles. ISDH progress on the grant was initially delayed due to the contract approval process. We would suggest that future grant cycles attempt to shorten the window for this process or establish a longer grant period to execute activities. Moreover, conference calls with all states involved with the grant were useful and informative, but we would recommend adjusting the frequency. Since ISDH’s progress with the grant was gradual, there were often few updates to present on the monthly calls. In lieu of a conference call to provide updates every month, we would recommend all-state calls every other month and one-on-one calls between states and CSTE in the intervening months. 
 
Impact Chart 
If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report. Please note: the chart below should be reflective of the cumulative project period and can include deliverables met in the interim report. 
	Impact 
	Evaluation

	Intervention Activity
	Baseline #  prior to 2018-19 grant period
	How did you measure the baseline? Did you include direct participants, families, etc?
	2018-19 Audience (youth, community leaders, etc?)
	# of attendees/participants
	# of materials distributed
	



Did you collaborate with another state? If so, which one(s)?
	Pre-test administered? (How many? To whom?)
	Post-test administered? (How many? To whom?)

	EXAMPLE: Four Scenario based training exercises
	X# of training sessions held in 2016 to X total youth aged 11-15
	Only counted the number of actual youth who attended  the session
	Youth aged between 12 and 16
	X # attendees per training; total of X attendees
	
	
	
	

	Expanded curriculum for annual 4-H “Teens as Teachers – Biosecurity” workshop via a partnership with Dr. Bowman and OSU.
	450 youth
	This number was based of existing program numbers in those areas.  This would be direct participants and those youth that were taught by the Teens as Teachers – Animal Biosecurity youth.
	Youth
	168 people
	110 Biosecurity Buckets

10 Teens as Teachers Teaching kits

380 Biosecurity signs
	Ohio – collaborated with Dr. Andrew Bowman at Ohio State University
	No
	Surveys were given, and a follow up survey will be given after 6 months.

	Attendance of INAF staff at the IAFE training on zoonotic disease prevention.
	N/A
	Counted the number of attendees at the INAF Convention
	County Fair/Festival Organizers
	125
	N/A
	N/A
	N/A
	N/A



