Influenza and Zoonoses Education among Youth in Agriculture
Progress Report 


Please return completed Progress Report to CSTE at mschroeder@cste.org.  


1. Identify your top three achievements over the last quarter. 
· Signed document with CSTE (September) and attended Grantee Meeting.
· Hired an intern to help with grant project (October).
· Observed signage and actions taking place in and around animal barns at state and two county fairs to gather baseline information.

2. Please list the collaborators on this quarter’s achievements and briefly describe their role in the project (i.e. 4H, State PH, State Animal Health).
· 4-H (Dr. Leigh Ann Skurupey): She is working with us to develop hands on educational trainings for 4-H Animal Science Project participants to identify ways to reach/educate Extension agents/coaches/club leaders and 4-H members to order to implement tangible learning activities that directly apply to real-world agricultural situations. This includes zoonotic disease-related lesson plans for Extension agents/coaches/club leaders to utilize during club meetings and Volunteer Training tools to educate 4-H’ers. As a result, these exciting activities will engage 4-H’ers to provide a positive environment in which youth can grow and develop confidence, a sense of accomplishment, and a greater level of competence of the animal science industry after each activity.
· Working with all collaborators on this grant towards a November 15th meeting with the North Dakota State Fair Board to initiate discussion and plan of action regarding this grant’s progress. 
· ND Department of Agriculture, Animal Health Division: The State Veterinarian, Deputy State Veterinarian, and ND State Board of Animal Health members are acting as our liaisons with industry.
· ND Environmental Health Association: Environmental health practitioners from the state health department and LPHUs will help us distribute materials in their jurisdictions and notify us of possible educational opportunities. 

3. Please describe areas of concern or challenges in meeting the objectives or providing deliverables.
· Unforeseen length of time for grant application to be signed. As a result, we are slightly behind schedule since projects could not be initiated until late September or early October.
· North Dakota is a very large state and thus outreach may be challenging, but certainly attainable after some deliberation to execute a proper method and action plan.

4. Please include an updated project timeline.
[bookmark: _GoBack]
	[bookmark: RANGE!A1]Objective One – Collaborative Development

	
	Activity
	
	Completion Date
	
	Updated Timeline

	
	Hire Student Intern
	
	31-Jul-17
	
	1-Oct-17

	
	Meet with 4-H Youth Livestock Specialist
	
	31-Jul-17
	
	1-Aug-17

	
	Meet with FFA Leaders
	
	31-Jul-17
	
	30-Nov-17

	
	Develop stakeholder meeting
	
	16-Aug-17
	
	15-Dec-17

	
	
	
	
	
	

	[bookmark: RANGE!A13]Objective Two – Training Activities

	
	Activity
	
	Completion Date
	
	

	
	Iowa State University online training
	
	1-May-18
	
	1-May-18

	
	MN Fair posters/placards/postcards
	
	1-Jun-18
	
	1-Jun-18

	
	Georgia 4-H Friends Magazine
	
	1-Jun-18
	
	1-Jun-18

	
	
	
	
	
	

	[bookmark: RANGE!A24]Objective Three – Summit
	
	
	
	

	
	Activity
	
	Completion Date
	
	

	
	Invite MT/SD/WY to Summit
	
	21-Jul-17
	
	15-Dec-17

	  
	Hold Summit
	
	29-Sep-17
	
	30-Apr-18

	
	Finalize minutes and initial summit report
	
	31-Oct-17
	
	31-May-18

	
	
	
	
	
	

	[bookmark: RANGE!A35]Objective Four – Evaluation
	
	
	
	

	
	Activity
	
	Completion Date
	
	

	
	In-person training evaluation survey
	
	31-Aug-17
	
	15-Feb-18

	
	Evaluation of online trainings and format
	
	20-Oct-17
	
	20-Jan-18

	
	Development of fair survey evaluation
	
	29-Dec-17
	
	29-Dec-17

	
	Evaluation of stakeholder’s strategic plan
	
	12-Jan-18
	
	15-Jun-18

	
	Finalize initial stakeholder report and send out
	
	9-Feb-18
	
	15-Jun-18




5. If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mschroeder@cste.org. 
· We have not distributed any products at this time.
· The ND 4-H State Specialist did present at the September ND Fall Conference for Extension agents the hands-on activity that Ohio State University put into action at the grantee meeting utilizing sodium bicarbonate and phenolphthalein to replicate a swine barn infected with influenza. She felt this was very well-received and enriched non-agricultural Extension agents with great perspective and awareness.

6. Please list suggestions for CSTE and CDC for how we can best facilitate your progress.
· During the calls, we would like to see one or two presentations from states to see what they did, what they are doing, things they have in the works, etc. Perhaps highlighting a couple different states on each call will encourage more in-depth sharing and discussion.

7. Please complete the attached spreadsheet to indicate progress made towards project deliverables.  


