## Sheet1
Please describe the progress made towards completion of the following project deliverables. | Summary of what was done (200 words or less). (What activities have taken place over the past 3 months? What materials were developed or produced as a result?) | Impact Statement (300 words or less) (How have these activities addressed one or more of the project objectives? Be sure to quantify impact as much as possible (i.e. How many educators and youth have been reached?)
Deliverable 1: Collaborative Development | We have had conference calls and/or meetings with the State Vet's Office, 4-H Leadership, LPHUs, and the Board of Animal Health. Our discussions were focused on ideas and education opportunities. We have started weekly conference calls with NDDoH, the student intern, and 4-H leadership to help keep on top of activities. | # of extension agents at ND Fall Conference meeting with Leigh Ann: 40 # of people at NDEHA Conference: 30; # of people at Board of Animal Health Meeting: 20
Deliverable 2: Training Activities | No activities
Deliverable 3: Summit | No activities
Deliverable 4: Evaluation | baseline observations done at the state fair, two county fairs. | In one hour: 97 people observed drinking in the horse barn 19 people eating 3 handwashing stations located outside horse barn 7 handwashing signs in the barn 3 handwashing signs located outside the barn 106 strollers observed in the horse barn Additional data gathered in other barns, just not put together at this time; now that intern is hired, all information will be entered and put into a report.