2020 Youth in Agriculture Individual Site Calls
April – May 2020

Iowa (April 30, 2020)
IA: Andy, Molly, Amy
CDC: Eli, Grace
 
Team Deliverables Update
· Continue to improve website (under active developments
· Should be done by mid-May
· Facilitator guides, templates and pilot test and web-based train the trainer
· Guides and templates are based on standard youth outreach event
· Planned to pilot test with University of TN Extension in the spring but has been canceled (unsure if this will be rescheduled)
· Will still be able to do this when TN is ready
· Web-based train the trainer will move forward to be held in IA 
· Can complete pilot on schedule but slightly different group
· Date TBD - anticipate second half of May
· Comprehensive evaluation plan
· Survey to be administered at the end of online courses (similar questions as in-person events)
· Plan to revamp the current evaluations due to less than desired response rate in previous project period
· Currently being revised with team member
· Next step: share with evaluation experts at IA State Vet School
· Hoping to share back with Eli for feedback/input
· Incorporate content from other partners to existing content
· Target end date: June/July after train-the-trainer
· No issues here
· Tracking is constant
· Youth outreach
· World Food Prize IA Youth Institute meeting moved to virtual platform
· Emergence part was canceled
· Trying to do more robust follow-up to hopefully get info out re: online course 
· 4H Conference is canceled
· However, the Animal Science Round-Up will be held virtually in July 
· State FFA meeting is canceled
· Need to get in touch with organizer to discuss outreach
· Adult outreach
· Held presentation at Association of IA Fair Conference (Dec 2019)
· A lot of contact with people that organize county fairs
· IA Association of Agriculture Educators Conference – status is unsure
· Typically held mid-summer
· On hold for now pending more information on pandemic
· IA School Nurse Organization Conference is canceled
· Additional activities in the works
· 4H extension developed and posted list of at home learning resources
· Shared information on social media and was able to reach a broad audience
· Received contact from extension specialist at University of NV-Reno
 
Maine (April 27, 2020)
ME: Catie, Donna
CDC: Eli, Grace
 
Team Deliverables Update
· Printing and shipping
· Dept of Agriculture handles shipping of materials to fairs
· Meeting packets were prepared in January
· Donna shared website for downloadable materials 
· Travel to 2 agricultural fairs have not been completed at this time
· 4H lessons have not been moved online it seems, mostly club-based/in-person
· 4H events have been canceled through June
· Awaiting additional guidance on next steps to see if activities can occur in July
 
Maryland (April 28, 2020)
MD: Chris Anderson 
CDC: Eli, Grace
 
Team Deliverables Update
· All interagency agreements and accounts are in place and established
· Project coordination team (MDH, Dept of Ag, 4H) meet regularly
· 4H team meets independently from larger group since deliverables done by this team, but all partners have met twice since January
· Continuing to meet and plan and move work forward
· West Virginia counterparts have been included in these meetings as well
· Seminar proposal accepted for 2020 National 4H Conference 
· Zoonoses kits
· 80 kits sent last year, and 84 facilitators were trained
· The in-person training has not been done but there have been a number of lessons (PPE, handwashing, etc.) that were popular from last cycle that will be incorporated this year
· Virtual sessions (e.g., livestock club) have been held
· Educator talked through handwashing and resources
· Facebook videos posted by members of team
· Some lesson plans applied to current pandemic/COVID-19
· Looking to enhance kits (adding 35) to add to county health offices
· Want to add additional supplies that are already distributed and replenish consumable supplies
· New lesson plan to be added to lesson book which will be professionally printed
· Planned to have another face-to-face facilitator training in summer but have moved this to virtual platform
· Purchasing items are on hold for now as people are not in the office
· Continue to work on videos and animal health checks using at home equipment as opposed to professional videographers for the time
· April 15 - AH&QA training program launched (25% content is zoonoses focused)
 
Michigan (May 5, 2020)
MI: Katie, Kim, Mary Grace
CDC: Eli 
 
Team Deliverables Update
· Deliverables completed
· Two sessions in January at Michigan Fairs and Exhibitions (MAFE)
· Creating a healthier barn environment for animals, exhibitors, etc.
· Focus on biosecurity practices
· Overview of research study on air quality and effect on spread of disease
· Training with communication specialist as it relates to media training and building relationships with local health departments
· Focusing on this aspect as an existing gap in current infrastructure and how to communicate effectively with the public
· April 16 – Katie (4H) hosted swine flu webinar with fairs
· Highlighted resources available
· 19 people on live Zoom, 25 who viewed recording = 44 participants
· Promoted through MAFE (~76 member fairs)
· Another webinar tomorrow and will then again plug swine flu tips webinar
· Not in grant plan, but as result of situation, pivoted to ensure biosecurity is included in larger scope of work 
· Many educators for 4H have been doing youth webinar series 
· Katie did 3 webinars on biosecurity tailored to specific species
· Horse (35 youth on call) - recorded and uploaded to YouTube
· Dog (companion animal and bring awareness, 20 youth) - recorded but unsure if posted
· Livestock (swine flu, crypto, other zoonotic diseases, 55 youth) - recorded
· MSUE Website
· Re-done to accommodate virtual lessons and plans
· Previous animal science lessons developed since 2014
· 7 to 9 lessons on there
· Animal health pages are updated as well to highlight this existing material
· Plan to highlight Be a Disease Detective given the relevancy

· In progress
· Career fair tomorrow, 5/6
· Mary Grace and Kim to present to remind people about handwashing stations and working with local health departments
· Develop materials to augment Germ-O game
· Creating an insert and thinking of ways to let youth learn symptoms, terms, etc.
· Club game night distribution site 
· Supposed to be done during this fall conference but has been moved to online platform
· Next step: how to distribute this and swap travel budget for postage to get these kits (lesson plans and materials) sent out to counties 
· Waiting for announcements on Annual Exploration Days for the pre-college program
· Canceled due to COVID-19
· MSUE staff cannot do any in-person programming through September 1, 2020
· TBD on what platform this will be held

· Future ideas to augment face-to-face activities
· Nick Babcock - last year's deliverable on the lesson plan Be a Disease Detective
· Will be held as webinar or virtual meeting
· Plug on MSUE COVID-19 site with various lesson plans 
· Teachers all over the state are utilizing this
· Date: June or July 2020
· Plan to have an epidemiologist on board to do question and answer
· Staying open to any other opportunities to still have impact even though at disadvantage with inability to travel

· Challenge
· Need printing for game night
· Waiting for people to be back in offices and see where we go from there
 
 
Minnesota (May 1, 2020)
MN: Carrie, Beth, Joe 
CDC: Eli, Grace
 
Team Deliverables Update
· 4H Extension in-person meetings have been canceled through June
· Everyone in MN Dept of Health/epidemiology division has been dedicated to COVID 100%
· Workshops canceled
· State home order still in state
· Started working with Minnesota Agriculture in the classroom
· Zoonotic disease detective toolkit sent to educators
· Work has started but unable to move beyond at this time
· North Star Farm Tour - moved forward with trying to figure out more opportunities for additional translations/languages and companies to use
· Blueprints developed for their own handwashing station
· Agritourism Education packets
· Maybe able to do this over the summer
· Hope to move workshops to fall
· County fairs and state fair are still TBD 
· Partnerships with ND and WI to be continually evaluated to figure out if/when conferences will be rescheduled conferences
· University of MN is under a hiring freeze through end of June
· Currently unable to hire intern and staff the escape room trailer
· Can attempt to do workshop and Emerging Issues Breakfast in the fall
· Asking to carryover these through next summer/fall 2021
· Agritourism activities on complete hold
 
Nebraska (April 27, 2020)
NE: Robin, Ali, Bryan
CDC: Eli, Grace, Joe
  
Team Deliverables Update
· Subaward sent to UNMC
· Working with UNL One Health team to create position for this project (master student, grad assistant)
· UNLE is currently maintaining website, continuing to look at measures, waiting to see assessment results but delayed as in-person club meetings are now on hold and school is not in session
· Can encourage FFA teachers to push out online programs/training 
· Outreach to FFA science teachers
· Career exploration component can be included in the evaluation component with job interest
· Only had one meeting with team in January
· Other meetings and deliverables have been put on pause and have not been met 
 
 
Ohio(4/29)
OH: Jacqueline, Laurie, Andy
CDC: Eli, Grace, Joe
 
Team Deliverables Update
· Poultry chapter is under review at 4H
· Unsure about next steps Skill-a-Thon
· Still working on curriculum with FFA
· No June meeting as originally planned
· Hoping to pilot this information but will not happen until fall
· Becoming a Swientist - still up in the air
· OH Circuit will still plan to move forward and show pigs in May
· World Expo (previously World Pork Expo) will occur in June
· Selfies and other activities are still up in air
· National Pork Board Curriculum has not started yet due to other issues evolving
· [bookmark: _GoBack]Still plan to make this happen
· Considerations for COVID-19 educational material and needs will be discussed and incorporated as able
