2020 Youth in Agriculture Individual Site Calls

April – May 2020

Iowa (April 30, 2020)

IA: Andy, Molly, Amy

CDC: Eli, Grace

Team Deliverables Update

- Continue to improve website (under active developments

  - Should be done by mid-May

- Facilitator guides, templates and pilot test and web-based train the trainer

  - Guides and templates are based on standard youth outreach event

  - Planned to pilot test with University of TN Extension in the spring but has been canceled (unsure if this will be rescheduled)

    - Will still be able to do this when TN is ready

  - Web-based train the trainer will move forward to be held in IA

  - Can complete pilot on schedule but slightly different group

    - Date TBD - anticipate second half of May

- Comprehensive evaluation plan

  - Survey to be administered at the end of online courses (similar questions as in-person events)

  - Plan to revamp the current evaluations due to less than desired response rate in previous project period

    - Currently being revised with team member

  - Next step: share with evaluation experts at IA State Vet School

    - Hoping to share back with Eli for feedback/input

- Incorporate content from other partners to existing content

  - Target end date: June/July after train-the-trainer

  - No issues here

  - Tracking is constant

- Youth outreach

  - World Food Prize IA Youth Institute meeting moved to virtual platform

    - Emergence part was canceled

    - Trying to do more robust follow-up to hopefully get info out re: online course

  - 4H Conference is canceled

    - However, the Animal Science Round-Up will be held virtually in July

  - State FFA meeting is canceled

    - Need to get in touch with organizer to discuss outreach

- Adult outreach

  - Held presentation at Association of IA Fair Conference (Dec 2019)

    - A lot of contact with people that organize county fairs

  - IA Association of Agriculture Educators Conference – status is unsure

    - Typically held mid-summer

    - On hold for now pending more information on pandemic

  - IA School Nurse Organization Conference is canceled

- Additional activities in the works

  - 4H extension developed and posted list of at home learning resources

  - Shared information on social media and was able to reach a broad audience

    - Received contact from extension specialist at University of NV-Reno

Maine (April 27, 2020)

ME: Catie, Donna

CDC: Eli, Grace

Team Deliverables Update

- Printing and shipping

  - Dept of Agriculture handles shipping of materials to fairs

  - Meeting packets were prepared in January

  - Donna shared website for downloadable materials

- Travel to 2 agricultural fairs have not been completed at this time

- 4H lessons have not been moved online it seems, mostly club-based/in-person

- 4H events have been canceled through June

- Awaiting additional guidance on next steps to see if activities can occur in July

Maryland (April 28, 2020)

MD: Chris Anderson

CDC: Eli, Grace

Team Deliverables Update

- All interagency agreements and accounts are in place and established

- Project coordination team (MDH, Dept of Ag, 4H) meet regularly

  - 4H team meets independently from larger group since deliverables done by this team, but all partners have met twice since January

  - Continuing to meet and plan and move work forward

  - West Virginia counterparts have been included in these meetings as well

  - Seminar proposal accepted for 2020 National 4H Conference

- Zoonoses kits

  - 80 kits sent last year, and 84 facilitators were trained

  - The in-person training has not been done but there have been a number of lessons (PPE, handwashing, etc.) that were popular from last cycle that will be incorporated this year

  - Virtual sessions (e.g., livestock club) have been held

    - Educator talked through handwashing and resources

    - Facebook videos posted by members of team

    - Some lesson plans applied to current pandemic/COVID-19

  - Looking to enhance kits (adding 35) to add to county health offices

  - Want to add additional supplies that are already distributed and replenish consumable supplies

- New lesson plan to be added to lesson book which will be professionally printed

- Planned to have another face-to-face facilitator training in summer but have moved this to virtual platform

- Purchasing items are on hold for now as people are not in the office

- Continue to work on videos and animal health checks using at home equipment as opposed to professional videographers for the time

- April 15 - AH&QA training program launched (25% content is zoonoses focused)

Michigan (May 5, 2020)

MI: Katie, Kim, Mary Grace

CDC: Eli

Team Deliverables Update

- Deliverables completed

  - Two sessions in January at Michigan Fairs and Exhibitions (MAFE)

    - Creating a healthier barn environment for animals, exhibitors, etc.

      - Focus on biosecurity practices

      - Overview of research study on air quality and effect on spread of disease

    - Training with communication specialist as it relates to media training and building relationships with local health departments

      - Focusing on this aspect as an existing gap in current infrastructure and how to communicate effectively with the public

  - April 16 – Katie (4H) hosted swine flu webinar with fairs

    - Highlighted resources available

    - 19 people on live Zoom, 25 who viewed recording = 44 participants

    - Promoted through MAFE (~76 member fairs)

    - Another webinar tomorrow and will then again plug swine flu tips webinar

  - Not in grant plan, but as result of situation, pivoted to ensure biosecurity is included in larger scope of work

    - Many educators for 4H have been doing youth webinar series

    - Katie did 3 webinars on biosecurity tailored to specific species

      - Horse (35 youth on call) - recorded and uploaded to YouTube

      - Dog (companion animal and bring awareness, 20 youth) - recorded but unsure if posted

      - Livestock (swine flu, crypto, other zoonotic diseases, 55 youth) - recorded

  - MSUE Website

    - Re-done to accommodate virtual lessons and plans

    - Previous animal science lessons developed since 2014

      - 7 to 9 lessons on there

    - Animal health pages are updated as well to highlight this existing material

  - Plan to highlight Be a Disease Detective given the relevancy

- In progress

  - Career fair tomorrow, 5/6

    - Mary Grace and Kim to present to remind people about handwashing stations and working with local health departments

  - Develop materials to augment Germ-O game

    - Creating an insert and thinking of ways to let youth learn symptoms, terms, etc.

  - Club game night distribution site

    - Supposed to be done during this fall conference but has been moved to online platform

    - Next step: how to distribute this and swap travel budget for postage to get these kits (lesson plans and materials) sent out to counties

  - Waiting for announcements on Annual Exploration Days for the pre-college program

    - Canceled due to COVID-19

    - MSUE staff cannot do any in-person programming through September 1, 2020

    - TBD on what platform this will be held

- Future ideas to augment face-to-face activities

  - Nick Babcock - last year's deliverable on the lesson plan Be a Disease Detective

    - Will be held as webinar or virtual meeting

    - Plug on MSUE COVID-19 site with various lesson plans

    - Teachers all over the state are utilizing this

    - Date: June or July 2020

    - Plan to have an epidemiologist on board to do question and answer

  - Staying open to any other opportunities to still have impact even though at disadvantage with inability to travel

- Challenge

  - Need printing for game night

  - Waiting for people to be back in offices and see where we go from there

Minnesota (May 1, 2020)

MN: Carrie, Beth, Joe

CDC: Eli, Grace

Team Deliverables Update

- 4H Extension in-person meetings have been canceled through June

- Everyone in MN Dept of Health/epidemiology division has been dedicated to COVID 100%

  - Workshops canceled

  - State home order still in state

- Started working with Minnesota Agriculture in the classroom

  - Zoonotic disease detective toolkit sent to educators

  - Work has started but unable to move beyond at this time

- North Star Farm Tour - moved forward with trying to figure out more opportunities for additional translations/languages and companies to use

  - Blueprints developed for their own handwashing station

- Agritourism Education packets

  - Maybe able to do this over the summer

- Hope to move workshops to fall

- County fairs and state fair are still TBD

- Partnerships with ND and WI to be continually evaluated to figure out if/when conferences will be rescheduled conferences

- University of MN is under a hiring freeze through end of June

  - Currently unable to hire intern and staff the escape room trailer

- Can attempt to do workshop and Emerging Issues Breakfast in the fall

- Asking to carryover these through next summer/fall 2021

- Agritourism activities on complete hold

Nebraska (April 27, 2020)

NE: Robin, Ali, Bryan

CDC: Eli, Grace, Joe

Team Deliverables Update

- Subaward sent to UNMC

- Working with UNL One Health team to create position for this project (master student, grad assistant)

- UNLE is currently maintaining website, continuing to look at measures, waiting to see assessment results but delayed as in-person club meetings are now on hold and school is not in session

  - Can encourage FFA teachers to push out online programs/training

  - Outreach to FFA science teachers

- Career exploration component can be included in the evaluation component with job interest

- Only had one meeting with team in January

  - Other meetings and deliverables have been put on pause and have not been met

Ohio(4/29)

OH: Jacqueline, Laurie, Andy

CDC: Eli, Grace, Joe

Team Deliverables Update

- Poultry chapter is under review at 4H

  - Unsure about next steps Skill-a-Thon

- Still working on curriculum with FFA

  - No June meeting as originally planned

  - Hoping to pilot this information but will not happen until fall

- Becoming a Swientist - still up in the air

  - OH Circuit will still plan to move forward and show pigs in May

  - World Expo (previously World Pork Expo) will occur in June

  - Selfies and other activities are still up in air

- National Pork Board Curriculum has not started yet due to other issues evolving

  - Still plan to make this happen

- Considerations for COVID-19 educational material and needs will be discussed and incorporated as able