## Sheet1
Please describe the progress made towards completion of the following project deliverables. | Summary of what was done (200 words or less). (What activities have taken place over the past 3 months? What materials were developed or produced as a result?) | Impact Statement (300 words or less) (How have these activities addressed one or more of the project objectives? Be sure to quantify impact as much as possible (i.e. How many educators and youth have been reached?)
1. Enhance existing Youth in Agriculture course | CFSPH continued to research how to incorporate the existing course into the state and national 4-H curriculum through state and national 4-H development standards and peer review. CFSPH made edits to the existing course, as needed, to maintain content accuracy and timeliness. CFSPH began researching how to improve the evaluation component of the course. CFSPH modified the Google Analytics tracking of the course to better capture course use. | Enhancing the existing course ensures all users are able to access the course. Aligning the course with state and national 4-H standards will allow the course to be available as official 4-H curriculum. Although there has been a lower response rate than expected, the optional evaluation component has indicated an increase in knowledge and plans to adopt disease prevention habits upon post-course completion.
2. Promote and increase existing course distribution and implementation | CFSPH presented a seminar at the 2017 American Association of Extension Veterinarians' (AAEV) annual meeting (held during the United States Animal Health annual meeting) on October 14, 2017. Printed materials for attendees were provided. CFSPH hosted an exhibit table at the National FFA Convention and Expo (October 25–29, 2017; Indianapolis, IN). Printed materials for youth, educators, and others at the convention were provided. A plush pig, brush, and Glo Germ was used to demonstrate disease transmission. The hashtag #bluenotflu was promoted to encourage sharing of photos on social media. CFSPH worked with the International Association of Fairs and Expositions to explore best options to reach membership. CFSPH, IDPH, and IAFE participated in a conference call. CFSPH will host and exhibit table in the "Ed Shed" and present a seminar at the annual convention (November 26-29, 2017; Las Vegas, NV). CFSPH worked with the National Association of Agriculture Educators to explore best options to reach membership. CFSPH began making travel arrangements to host an exhibit table at the NAAE annual convention (December 7–9, 2017; Nashville, TN). | During March 1–October 29, 2017, the web page hosting the Excellence in Exhibition course was viewed 3,575 times (2,913 unique views). Google analytics tracked 42 logins to the password protected instructor page; there were 261 accesses to the actual course from users in 27 states. A total of 67,006 registered youth, educators, and guests attended the National FFA convention; CFSPH distributed approximately 3,250 stickers promoting the course. Feedback from attendees was very positive. Many educators indicated their intent to use the course in their curriculum in the upcoming weeks and months; one educator indicated this was probably the most useful tool he will take home from the entire convention. AAEV attendees totaled 55 extension veterinarians, state animal health officials, and other USAHA attendees.
3. Develop new course for younger audiences (specifically, children aged 7–12 years) based on existing course | CFSPH attended training in online course development conducted by the Center for Excellence in Learning and Teaching at Iowa State University. Lessons in accessibility will be applied to the current and new online courses. | The new course curriculum will build upon the existing course structure and will continue to be interactive and engaging. The expanded course curriculum will also focus on influenza and other zoonotic disease prevention, but it will be age appropriate for younger children, including more gamification, less text, a lower reading level, and shorter lessons. Creating a course for this target audience will enable us to broaden the reach of these important educational materials to all ages.