Influenza and Zoonoses Education among Youth in Agriculture
Progress Report 


Please return completed Progress Report to CSTE at mschroeder@cste.org.  


1. Identify your top three achievements over the last quarter. 
a. The Center for Food Security and Public Health (CFSPH) promoted the existing Excellence in Exhibition course at several different venues and made arrangements for continued promotion of the course at upcoming events (see attached spreadsheet for details).
b. The Iowa Department of Public Health (IDPH) and CFSPH attended the grantee meeting in Atlanta, GA, October 22–24. 
c. CFSPH attended training in online course development conducted by the Center for Excellence in Learning and Teaching at Iowa State University. Lessons in accessibility will be applied to the current and new online courses. 

2. Please list the collaborators on this quarter’s achievements and briefly describe their role in the project (i.e. 4H, State PH, State Animal Health).

CFSPH worked with the National FFA Association to encourage youth participation in the existing course at the National FFA Convention and Expo (October 25–29, 2017, in Indianapolis, IN). CFSPH and IDPH also worked with the International Association of Fairs and Expositions (Marla Calico) and the National Association of Agriculture Educators to identify the best way to promote the course to membership. CFSPH and IDPH met and collaborated with all grantees, CSTE, and CDC at the grantee meeting and workshop in Atlanta, GA, October 23–24, 2017. 
3. Please describe areas of concern or challenges in meeting the objectives or providing deliverables.

CFSPH is exploring options to increase participation in the voluntary course evaluation. 
4. Please include an updated project timeline.
	Present–Oct 31, 2017
	· Enhance existing course
· CFSPH will continue researching how to incorporate the course into state and national 4-H curriculum through state and national 4-H development standards and peer review.
· CFSPH will make course edits as appropriate to maintain content accuracy and timeliness. 
· As a collaborating center with the OIE, CFSPH will place the OIE logo on the course.
· CFSPH will modify the Google Analytics tracking of the course to better capture course use.
· Promote and increase existing course distribution and implementation
· CFSPH will continue distributing materials at upcoming events listed in the project proposal.
· CFSPH will present a seminar during the 2017 American Association of Extension Veterinarians’ annual meeting (held during the United States Animal Health Association meeting) and distribute promotional materials.
· CFSPH will host an exhibit table at the National FFA Convention. CFSPH will also provide printed material for youth, educators, and others at the National FFA Convention.
· CFSPH will register, research, and begin making travel arrangements to host an exhibit table and interactive teacher/student workshop at the International Association of Fairs and Expositions Annual Convention.
· CFSPH will register, research, and begin making travel arrangements to host an exhibit table at the National Association of Agriculture Educators conference.  
· Develop new course for younger audiences (specifically, children aged 7–12 years) based on existing course
· CFSPH will continue to develop the outline, research content, and research best practices in online course development for the new course.

	Nov 1, 2017–June 30, 2018
	· Enhance existing course
· CFSPH will review and modify the existing course website to ensure compliance with Section 508 of the Rehabilitation Act, ensuring accessibility for all learners and allowing distribution through federal partners.
· CFSPH will consult with Iowa State University’s Center for Excellence in Learning and Teaching (CELT), http://www.celt.iastate.edu/about, to identify and implement enhancements to the current course. Specifically, CFSPH will consult CELT’s Online Learning Innovation Hub aimed at enhancing quality of instruction, increased reach, and accessibility.
· CFSPH will consult with CELT and CDC to revise the evaluation component as necessary to collect the most useful data to improve the course.
· CFSPH will work with CDC and CSTE to participate in any evaluation framework to assess implementation of the project on a national level.
· Promote and increase existing course distribution and implementation
· CFSPH will contact the Youth for the Quality Care of Animals administrators to explore options for including the Excellence in Exhibition course as part of the YQCA curriculum. 
· CFSPH and collaborating agencies will pursue opportunities to engage participation among Iowa youth through exhibits, formal presentations, and/or demonstrations/workshops at the following venues:
· Association of Iowa Fairs Annual Conference (2017 & 2018)—During 2017 and 2018, we will present our recommendations to the Iowa fair boards encouraging them to consider requiring all exhibitors to take the course prior to exhibiting animals.
· Iowa FFA Association Leadership Conference and State Convention (2018)
· Iowa Association of Agricultural Educators Summer Conference (2018)
· 4-H State Conference and Animal Science Roundup (2018)—CFSPH will pursue hosting an interactive workshop to directly reach our target audience of Iowa youth involved in 4-H. By holding an interactive workshop during the three-day event, we will share some of the hands-on interactive elements of the course and encourage all Iowa 4-H members in attendance (more than 1,000 each year) to take the course in preparation for the upcoming exhibition season.
· [bookmark: _GoBack]CFSPH, IDPH, and the Iowa Department of Agriculture and Land Stewardship will write an article for the IAFEIFAE newsletter.  
· CFSPH and collaborating agencies will also seek opportunities to engage youth participation from across the nation through exhibits, formal presentation, and/or demonstrations/workshops at the following venues: 
· Council of State and Territorial Epidemiologists Annual Conference (2018)—CFSPH and/or IDPH representatives will submit an abstract to promote the course and present results of the evaluation component.
· At all venues, we will display interactive elements of the course on laptops and tablets, distribute informational flyers, handouts, stickers, and other material developed by CFSPH advertising the free course, and distribute zoonotic disease resources developed by CFSPH, other states, and CDC.
· Develop new course for younger audiences based on existing course
· Expand course curriculum to build upon the current course structure and be age appropriate for younger children, including more gamification, less text, a lower reading level, and shorter lessons.
· Develop an evaluation component comparable to the existing course and consistent with any guidelines outlines by CDC and CSTE will be included in the new curriculum. In addition to the online course, supplemental materials will be developed, such as signs that 4-H clubs and FFA exhibitors can post at fairs/exhibitions promoting public health prevention messages.




5. If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mschroeder@cste.org. 

All materials are posted to the Basecamp site. 

6. Please list suggestions for CSTE and CDC for how we can best facilitate your progress.

As discussed at the grantee meeting, assistance in promoting the course at the national level would be valuable. 

7. Please complete the attached spreadsheet to indicate progress made towards project deliverables.  


