Influenza Education among Youth in Agriculture 1st Quarter (July-Oct) Progress Report 


Please return completed Progress Report to CSTE at mschroeder@cste.org.  


1. Identify your top three achievements over the last quarter. 
a. Ordered an additional 54 educational board games titled, “Farmstead Enterprise: Adventures in Agritourism.” Now each county and regional 4-H office in Minnesota will have a game available for club meetings to check-out. The games are in the process of being distributed. 
b. Completed a handout entitled, “Staying Safe When the Farm Comes to You.” This is the 2nd iteration of handouts meant for the public engaging in agritourism. Our first handout from last year focused on what visitors to agritourism venues need to know. This handout focuses on what the public needs to know to stay safe and healthy when agritourism comes to them. Typical settings for such thing are daycares, preschools, and churches. The handout has been uploaded to the Basecamp site and is also being shared on the UMASH website. 
c. Influenza ads for poultry and pork producers were submitted to producer groups again. 4-H will also plan to post these ads on their social media platforms. 
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2. Please list collaborators on this quarter’s achievements, and briefly describe roles of different organizations involved (i.e. 4H, State PH, State Animal Health)
a. MN 4-H was heavily involved in the development of the game during Year 1 of the grant and is instrumental in getting the games out to the county and regional offices.
b. [bookmark: _GoBack]Our partners at UMASH helped us create and disseminate “Staying Safe When the Farm Comes to You” handout. 4-H is also very interested in disseminating this handout to their 4-H families. 


3. Please describe any areas of concern or challenges to meeting the objectives or providing deliverables.
a. There were some issues on MDH’s legal end regarding the wording of the contract so we didn’t actually get the money until the first week of August. That left us feeling behind and trying to catch up. I anticipate we will have a lot more of our grant objectives completed by the 2nd report in February. 
b. It is still challenging to find time to meet to discuss grant deliverables between MDH and 4-H staff. We all wear several hats so it’s about finding that balance. 
c. We are also recognizing that some of the original grant deliverables might not be realistic based on our timeline, resources, and buy-in. The grantee meeting helped us clarify what we might change about our deliverables.

4. Please include an updated project timeline.
See attachment	

5. If you have materials you are already distributing, please include a sample PDF or link of those materials.
See attachment
6. Please list any suggestions for CSTE and CDC for how we can help best facilitate your progress.
Having the in-person grantee meeting was wonderful and something that I hope continues if the funding for this program continues. Also, establishing a public-facing online resource library is great. Anything else CSTE and CDC can do to streamline collaborations between the states would be beneficial.  

7. Please complete the attached spreadsheet, to indicate progress made towards project deliverables.  
See attachment
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