Influenza and Zoonoses Education among Youth in Agriculture
Progress Report 


Please return completed Progress Report to CSTE at mschroeder@cste.org.  


1. Identify your top three achievements over the last quarter. 
a. Host MSUE Exploration Days session, “Be a Disease Detective”
b. Attend the CDC/CSTE Grantees Meeting (two staff from MDHHS)
c. Plan and host 6 of 7 Zone meetings with fair planners, 4-H youth leaders, local public health, MSU Extension staff and state agriculture and public health staff.

2. Please list the collaborators on this quarter’s achievements and briefly describe their role in the project (i.e. 4H, State PH, State Animal Health).
a. MSU Extension 4-H staff:  work with new person (Jake DeDekker) pending hiring of replacement for previous collaborator, Julie Thelen. Additional regional MSUE staff also participated and presented on their role in educating youth and their participation in the Educating Youth in Agriculture grant.
b. Fair administration:  as part of the current grant funding, MDHHS partnered with the Michigan Association of Fairs and Exhibitions President (Steve Thelen) to host a series of meetings around the state for fair organizers, 4-H volunteers, animal superintendents and others to provide education about zoonotic disease risks, with an emphasis on influenza, associated with fairs and how to reduce risk and plan/prepare in the case of an outbreak at their fair.
c. Public Health: MDHHS is encouraging Michigan local health departments to engage with their local fair organizers and 4-H volunteers to provide support and expert guidance regarding disease risk mitigation and also education for their exhibitors and the public.  We are emphasizing the value of establishing relationships before the event.  A response to ill animals or people at the fair can be better coordinated and carried out if plans are made in advance.
d. Animal Health:  the Michigan Department of Agriculture and Rural Development regional veterinarian attended each “Be Healthy at the Fair” meeting and provided information about their role in animal health and disease response in the fair setting.
e. 4-H adult volunteers/ Animal superintendents:  invited to attend “Be Healthy at the Fair” meetings.  These are the people that work most closely with youth before and during the fair and are important sources of information and guidance for their kids.  Animal superintendents are responsible for making sure animals are properly handled and cared for during the fair.  This was another target group for the “Be Healthy at the Fair” meetings.


3. Please describe areas of concern or challenges in meeting the objectives or providing deliverables.
a. Unfortunately, we lost our most valuable asset, Julie Thelen, the MSU Extension Educator and primary partner in this project, when she took another job out of state.  At this time, the MSU Extension position remains vacant so we have not been able to move forward with ideas for videos or additional curriculum units on Epidemiology and Outbreak Response. MSUE plans to fill her position and we look forward to working with her replacement.  
b. [bookmark: _GoBack]The attendance at our regional meetings for adults lacked robust local public health participation.  This may have because the meetings were scheduled in the evenings, outside of their normal work hours.  The meetings were scheduled in the evenings to accommodate the 4-H/fair personnel who were mostly volunteers and who work at their regular jobs during business hours.  Thus, we’ve decided to present this topic at our MDHHS Communicable Disease annual Conference in Spring 2018 – where LHD attendance is the primary audience.

4. Please include an updated project timeline.
	April 2017:
	Notification of Award

	May-August 2017:  
Zone Meeting: DONE
Reprint signs: ordered
Curriculum and videos:
December 2017-April 2018
	Plan and invite attendees to the seven Zone Fall meetings
Develop curriculum for Veterinary Science Camp with partners
Reprint and distribute “Be Healthy Around Animals” signage 
Creation of three short videos about healthy habits

	May 2017: NOT DONE
	Begin process of hiring additional student for part-time work

	August-November 2017:
DONE
	Conduct 7 zone meetings across the state in coordination with MAFE/MSUE/MDARD

	TBD 2017:  
DONE
	Three Michigan partners travel and participate in national CSTE Grantee Meeting

	June 21-23, 2017
DONE
	Present session “Be a Disease Detective” during 4-H Exploration Days

	June 26-30, 2017: 
DONE (student mentor) 
	Organize/present “One Health” sessions at 4-H Animal and Veterinary Science Camp; hire 1 veterinary student mentor for each 10 campers

	May-November 2017:  
January 1-April 2018
	Develop two Animal Science Anywhere curriculum units; 1) Epidemiology and 2) Outbreak Response
Develop “One Health” youth signage with ANR Communications

	October-December 2017:
January 1 – April 2018
	Compile questions and concerns from Zone meetings and prepare resources as needed
Reprint additional signage for next fair season
Find or create curriculum for Fair Organizer Zoonotic Disease Prevention Training

	January 11-13, 2018:
	Michigan Association of Fairs Convention including a MDHHS/MSUE session about the Youth Ag Education Grant accomplishments
Host Fair Organizer Zoonotic Disease Prevention Training
Distribute “One Health” youth signage

	March 2018:
	Follow-up with Zone Meeting attendees to help prepare for 2018 fairs, conduct follow-up KAP survey.

	April 2018:
	Combine evaluation data from presentations to determine impact
Present results from “Be Healthy at the Fair” meetings to Michigan Local Public Health staff at the annual Michigan Communicable Disease Conference April 25, 2018




5. If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mschroeder@cste.org. 


6. Please list suggestions for CSTE and CDC for how we can best facilitate your progress.
a. Maintaining a list of national meetings where this program has been presented either in oral or poster sessions.
b. Brainstorm on ways to publicize this program and materials developed thru it to other (non-funded) states.  Host a website? Webcast? Maybe devote a ZOHU call to the topic.

7. Please complete the attached spreadsheet to indicate progress made towards project deliverables.  


