
Please return completed Interim Progress Report to CSTE at mhuynh@cste.org by July 31, 2020.
Note: Please submit one response per site.

1) List project deliverables and describe progress made towards completion of these deliverables:  

Deliverable 1: Update, maintain, enhance, and promote existing courses and supplemental material
Accomplishments/Progress to-date: 
· The CFSPH instructional technology team, with guidance from the project team, made significant updates to the www.BlueNotFlu.org webpage to clearly market the online courses as well as the supplemental material to accompany the course objectives. With the website upgrade, usability has been improved, along with the incorporation of new resources related to the “Bring Home the Blue, Not the Flu!” course objectives (see Deliverable 3). The updated version of the website also includes a ‘Related Resources’ section which includes links to additional disease education resources, biosecurity tips for swine exhibitors, and other agriculture-related learning activities. Many of these resources were developed by other states as a part of the Youth in Agriculture project. The CSTE Youth in Ag Resource Repository is also linked on the new website.
· The CFSPH developed facilitator guides and workshop templates (listed individually below) to ease the workshop planning process for youth leaders and facilitate implementation of such events. To support and test this concept, the CFSPH worked directly with Iowa State University Extension to hold a train-the-trainer session held on May 29, 2020 (see Deliverable 3). To further work across state lines, University of Tennessee extension staff were also invited to participate in this train-the-trainer, and, following their engagement in such, the facilitator guides and workshop templates were provided to University of Tennessee Extension staff. 
· Additional resources developed include:
· ‘Trainer’s Guide’ to integrate the curriculum into a workshop with hands-on activities. This included guidance for holding workshops of various durations (e.g., 1-1.5 hours, half day or more) and held under various circumstances (e.g., students are able, or unable, to complete independent learning ahead of a workshop) as well as a step-by-step planning guide, general agenda, lesson-activity correlation guide, and suggested materials list.
· Generic ‘Workshop Flyer’
· ‘Project Background’ information sheet
· ‘Curriculum Standards’ document aligning the “Bring Home the Blue, Not the Flu!” course with state and national 4-H program priorities and education standards, and
· ‘Resource Guides’ summarizing the content and resources available within the curriculum.
· These resources are provided individually on the website, and were also included along with existing materials, including Learning Objectives (with Answer Keys), Worksheets, Activity Instructor Guides and Participant Guide, and Workshop Evaluations, within a “digital packet” provided to session attendees (see Deliverable 3).
· Prior to the above train-the-trainer session, the pre- and post- course evaluations (hard copy and web versions) were updated to simplify the survey and highlight questions that would improve response rates and increase the value of the responses provided. 
· The CFSPH continued to track visits to the course webpage and the courses themselves to monitor the need for and impact of these materials (see Impact Chart).
· The CFSPH continued to monitor content accuracy and timeliness to be able to make course edits as appropriate.
· The CFSPH continued to be available to participate in any evaluation framework to assess implementation of the project on a national level

Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.) 

Deliverable 2: Conduct outreach to youth by using the courses and hands-on activities developed by the CFSPH, other states, and CDC during previous three fiscal years
Accomplishments/Progress to-date: 
· Originally, four interactive workshops at three events were proposed. Due to the COVID-19 outbreak, all events’ in-person activities were cancelled. Of the four planned workshops at events scheduled by entities other than the project team, one (4-H Animal Science Roundup) was modified by the organizer to be held in a digital format instead; the other three events (Iowa FFA Association Leadership Conference and State Convention, 4-H State Conference, and World Food Prize Iowa Youth Institute) were cancelled for 2020. However, the project team proceeded with youth outreach via different mechanisms to reach the desired numbers of youth. Modified outreach is described below.
· Dr. Molly Lee led a 50-minute session covering the Blue Not Flu course material during the 2020 online Animal Cy-ience Academy. This event replaced the Iowa 4-H Animal Science Round-Up, which was cancelled due to COVID-19. 7 students and one adult were in attendance from five states, including Iowa, Tennessee, Georgia, Mississippi, and South Dakota. 
· Iowa 4-H created a template for “At Home ‘On the Go’” lessons which offers materials and directions for a hands-on youth activity related to a 4-H project area. The CFSPH developed two “At Home ‘On the Go’” lessons related to the “Bring Home the Blue, Not the Flu” curriculum, and included with the lesson information on accessing the online course.  These lessons have been promoted to all Iowa County Youth Coordinators (CYCs) (one CYC per each of Iowa’s 99 counties), and are provided to the CYCs free of charge. 
· Iowa 4-H also developed a list of at-home learning resources, and the CFSPH was able to ensure the “Bring Home the Blue, Not the Flu” curriculum was included, and featured, within this publicly available list directed at parents and other youth leaders. 
· To further socialize the course as an educational, online learning opportunity, our social media graphic promoting the course was shared across multiple Facebook pages, including: Iowa State University Dairy Extension, Iowa Beef Center, Iowa Pork Industry Center, and Iowa Small Farms. 

Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)

Deliverable 3: Conduct outreach, support, and training to adults by using the materials developed during FY16 and FY17 and expanding training materials to build capacity and ability for others to train youth         
Accomplishments/Progress to-date:
· Originally, three trainings at three different events were proposed. Due to the COVID-19 outbreak, two events’ in-person activities were cancelled. The project team proceeded with adult outreach via different mechanisms to reach the desired numbers of adults (who then impact youth). The one in-person activity that was held, in addition to the modified outreach, is described below.
· In December 2019, Dr. Danelle Bickett-Weddle of CFSPH attended the Association of Iowa Fairs (AIF) Annual Conference and delivered a presentation on the “Bring Home the Blue, Not the Flu!” course, disease transmission, and prevention strategies for influenza and other zoonotic diseases. Additional fair organizers were able to be reached via the opportunity to include a handout promoting the course in the organization’s annual newsletter and on the AIF website as a resource for member fairs. 
· In May 2020, Dr. Molly Lee led a virtual train-the-trainer workshop on the “Bring Home the Blue, Not the Flu” online courses and supplemental material, and revealed the updated website to 49 County Youth Coordinators (CYCs) and youth educators from Iowa and Tennessee. During the hour and a half interactive training, Dr. Lee trained attendees on the course objectives and material while also presenting the updated www.BlueNotFlu.org website. Course content was explained, and materials to ease workshop planning and implementation, including new course materials such as the facilitator guides and sample workshop templates, were presented to attendees. Dr. Lee also discussed alternative ways that youth educators could utilize the course material in the absence of “normal” programming (e.g., virtual workshops, “kits” to provide to youth for at-home use, etc.). At the end of the training, the attendees were asked questions via a Slido poll on how they could implement the “Bring Home the Blue, Not the Flu!” course materials with the youth they interact with. The number of attendees were measured along with the number of youth they interact with on a yearly basis. The 49 attendees cumulatively impact an estimated 36,500 youth.
· Subsequent to the virtual train-the-trainer workshop, the CFSPH initiated contact with and offered support to Iowa 4-H leaders and County Youth Coordinators (CYCs), and other adults to facilitate use of the courses in their youth outreach and education who participated in the webinar, and shared with them a “digital packet” which included the facilitator guides and workshop materials (see Deliverable 1). In addition, the webinar was recorded and published to the CFSPH’s YouTube channel. The additional 27 CYCs who registered for the train-the-trainer session, but were unable to attend, were sent a recorded copy of the non-interactive portion of the webinar and a link to the www.BlueNotFlu.org website. 
· The CFSPH has continued to offer support to health and agriculture departments, educational institutions, and other organizations in other states and regions in adopting and adapting the courses for youth education in those areas.
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)

2) List the collaborators involved to-date and briefly describe their role in the project (i.e. 4H/FFA, State PH, State Animal Health).

During completion of project deliverables, the CFSPH collaborated closely with the primary project coordinators: the Iowa Department of Public Health, Iowa 4-H, Iowa FFA Association, and the Iowa Department of Agriculture and Land Stewardship (IDALS). Specifically, IDALS, especially Dr. Andrew Hennenfent, facilitated the hosting of the train-the-trainer webinar, and participated in the webinar, emphasizing the importance of youth education programs in Iowa agriculture. Additionally, Iowa 4-H, especially Dr. Amy Powell, was instrumental in socializing the train-the-trainer session to the primary audience—Iowa CYCs—as well as distributing information about the course through various channels (see deliverable 2). 

3) Have you incorporated COVID-19 into activities or deliverables completed in Phase 1 of this project period? If so, please describe in detail (e.g., partners involved, role of each partner, etc.). (Please note: changes to activities, budget, and timeline initially proposed for Phase 2 should be documented in an updated workplan during the contract amendment process).

Two 4-H “At Home ‘On the Go’” lessons were created to correlate with the Blue Not Flu material. These were created and provided to the Iowa 4-H program for youth to use during the COVID-19 period (see Deliverable 2). During the train-the-trainer workshop (see Deliverable 3), Dr. Lee provided many options on how youth educators could utilize course material during the COVID-19 period, such as holding virtual workshops or alternative ways to engage students in course material and activities. 
One benefit of supplementing the online “Bring Home the Blue, Not the Flu” course with an in-person or virtual workshop is the ability to teach disease transmission and prevention concepts using current and relevant examples. For instance, in previous years, swine-interested youth at workshops expressed concern related to African swine fever, a high-consequence Foreign Animal Disease of high concern in agriculture, so this disease was used to teach concepts, to supplement the information on influenza and zoonotic disease information emphasized within the online course. This year, COVID-19 was the focus of most examples, and used as a model to teach concepts covered throughout the curriculum. This is true for both education directly with youth, as well as education targeted at youth leaders. 
Another important activity completed by the project team directly related to youth in agriculture was to assist ISU Extension, Iowa FFA, and the Story County Fair Board with plans to hold a modified County Fair during the COVID-19 pandemic. The primary entity responsible for developing the plan was ISU Extension, specifically Jess Soderstrum, and at various stages throughout the project team (Dr. Lee) was consulted with and provided input on plans to allow for continuation of exhibitions and education of our county’s youth while maintaining safe practices (e.g., social distancing, sanitation, appropriate flow of people, appropriate use of PPE) to prevent transmission of COVID-19, as well as protect human and animal participants from influenza and other zoonotic diseases. 
4) Describe areas of concern or challenges in meeting the objectives or providing deliverables especially as it relates to COVID-19.

Because of the COVID-19 pandemic, several of the anticipated opportunities to present the Blue Not Flu course material and information were cancelled. As a result of restrictions on public gatherings and public health guidelines, hosting our own replacement event was also not an option during this phase. However, the CFSPH feels that we have been able to modify our activities to effectively reach youth virtually, via youth events held remotely; reach adults (who will then impact youth) through virtual train-the-trainer sessions for youth leaders, and increase socialization of and interest in the online course to fulfill educators’ and parents’ desire for a reputable, accessible, engaging online educational resource. Thus, we feel that we were able to impact just as many, if not more, youth as if we were able to hold the original events intended. 

5) List suggestions for CSTE and CDC for how we can best facilitate your progress (e.g., frequency of individual site calls vs. all site calls, Basecamp utilization, etc.).

None

6) If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mhuynh@cste.org. 



OPTIONAL (but please complete if relevant)
If you have a story or anecdotal example of:

· how an individual, group, or community was positively impacted as a result of your YIA project’s interventions; 
· how an outbreak response that was better facilitated as a result of strengthened One Health collaboratives and relationships built through this project; OR
· how Youth in Agriculture network, relationships, or program activities helped in your state’s fight against COVID

either describe it here or just write ‘YES’ and we will follow up with you at a later date.  These ‘success’ stories combined with quantitative impact numbers will be used to share project successes with leadership. 


Feedback from youth leaders about “Bring Home the Blue, Not the Flu” online courses and   associated materials:
· “We are always trying to find interactive programs/lessons to do with a group that includes a range in age of participants. This would be a GREAT program to implement. We feel like this would be a good program to take material from with the current pandemic we are facing this would offer good insight on the high risk of spread.”

· I believe that this material will be very useful. I could see using this information as part of a clinic tied to county livestock shows, workshops/camps, and sharing the online information activities with students to work on at home.”

· I see this as a great summer workshop that combines hands-on learning as well as online learning.

2020 Influenza and Zoonoses Education among Youth in Agriculture Program
Interim Progress Report
Site:	Iowa
Completed by:	Molly Lee, Center for Food Security and Public Health (CFSPH), Iowa State University 
Date:	23 July 2020
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Impact Chart 
If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report
	Impact 
	Evaluation

	Intervention Activity
	Baseline # prior to current grant period
	How did you measure the baseline? Did you include direct participants, families, etc?
	2020 Audience (youth, community leaders, etc?)
	# of attendees/
participants
	# of materials distributed
	Did you collaborate with another state? If so, which one(s)?
	Pre-test administered? (How many? To whom?)
	Post-test administered? (How many? To whom?)

	EXAMPLE: Four Scenario based training exercises
	X# of training sessions held in 2016 to X total youth aged 11-15
	Only counted the number of actual youths who attended the session
	Youth aged between 12 and 16
	X # attendees per training; total of X attendees
	
	
	
	

	“Bring Home the Blue, Not the Flu!” online course
	In 2019, there were 1,001 users who visited the website, 303 users who took the course for youth aged 7-12 years, and 698 users who took the course for youth aged 13-18.
	Unique visitors

	Anyone with internet access
	Unique visitors to the website: 984

Took the middle/high school course: 200

Took the elementary course: 97
	[bookmark: _GoBack]N/A (full access to all materials on website, including both online courses)
	Users nationwide could complete; NE has unique online form from 2019 collaboration
	Yes; 122 (incl. 59 from NE); optional for individuals who completed online course 
	Yes; 122 (incl. 59 from NE); optional for individuals who completed online course


	Sharing “Bring Home the Blue, Not the Flu” course website via social media
	N/A
	People reached, engagements, and shares as reported by Facebook
	People reached, engagements, and shares as reported by Facebook
	346 people reached, 19 engagements, 3 shares
	Link to course website: www.BlueNotFlu.org 
	
	N/A
	N/A

	Train-the-Trainer Workshop for the Blue Not Flu material
	1 training session held on May 29, 2020
	We measured the number of attendees as well as the number of youth each attendee interacts with per year
	Partners in Iowa and Tennessee Extension and 
4-H
	49 attendees live; 27 additional registered but could not attend live and were sent link to recording
	Digital packet- included
	Tennessee
	
	Not a post-test, but a survey about the materials and the training session was completed by 20 live attendees

	Virtual Animal 
Cy-ience Academy
	1 training session held on July 1, 2020
	We measured only the number of youth and adults that attended the session. 
	4-H youth from five different states
	8 attendees
	Link to course website: www.BlueNotFlu.org 
	Georgia, Mississippi, North Dakota, Tennessee 
	
	






