
Please return completed Interim Progress Report to CSTE at mhuynh@cste.org by July 31, 2020.
Note: Please submit one response per site.

1) List project deliverables and describe progress made towards completion of these deliverables:  

· Deliverable 1: Distribute Educational Materials 

Accomplishments/Progress to-date: No progress made to date. Maine DACF typically distributes materials in a mailing during the month of April. However due to the COVID-19 situation in Maine and fairs cancelling, during this time the mailing did not make sense. As of July 10th, nearly all fairs cancelled their 2020 fair and three fairs are under evaluation for the 2020 season. If any of the three fairs does happen in 2020, materials will be provided by Maine DACF to that fair.

Did this deliverable include an educational intervention: Yes / No

· Deliverable 2: Hold Train-the-Trainer Webinar Event 

Accomplishments/Progress to-date: No progress made to date. Due to fairs cancelling for 2020 and the reprioritization of Maine CDC staff to the COVID response, this objective is postponed. The train-the-trainer is geared toward fairs

Did this deliverable include an educational intervention: Yes / No
Due to this deliverable not being completed to date, the Impact Chart is not filled out for this deliverable.
[bookmark: _GoBack]
· Deliverable 3: Work with Local 4H Groups to Educate Visitors at Their Local Fair on Biosecurity and Disease Transmission

Accomplishments/Progress to-date: No progress made to date. Due to COVID-19, local 4H groups are not meeting and fairs are cancelled or evaluating for the 2020 season, so this objective will not be able to be completed during 2020.
 
Did this deliverable include an educational intervention: Yes / No
Due to this deliverable not being completed to date, the Impact Chart is not filled out for this deliverable.


· Deliverable 4: Hold a One-Day Public Health Career Summit Days for 4H Youth 

Accomplishments/Progress to-date:  No progress made. Due to the COVID-19 situation in Maine, there was a Stay Healthy At Home Order that prevented this from being held when we initially planned. In addition, social distancing would be nearly impossible to do this in person since students would have come from across Maine and we would have moved them from place to place in vans. Finally, most organizations are only open to a limited number of employees and not allowing visitors into state facilities. A virtual summit day would not nearly compare to doing this in person and therefore is postponed.

Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)


2) List the collaborators involved to-date and briefly describe their role in the project (i.e. 4H/FFA, State PH, State Animal Health).

There are no collaborators to date, due to all objectives being postponed due to the COVID-19 situation in Maine. 

3) Have you incorporated COVID-19 into activities or deliverables completed in Phase 1 of this project period? If so, please describe in detail (e.g., partners involved, role of each partner, etc.). (Please note: changes to activities, budget, and timeline initially proposed for Phase 2 should be documented in an updated workplan during the contract amendment process).

Not applicable since Maine has not completed any objectives. 

4) Describe areas of concern or challenges in meeting the objectives or providing deliverables especially as it relates to COVID-19.

Maine CDC has three individuals that provide the primary work to the Influenza and Zoonoses Education among Youth in Agriculture Program; Anna Krueger, Catie Peranzi, and Sara Robinson. Due to the COVID-19 situation in Maine, all three individuals had to reprioritize Maine’s COVID-19 response as a first priority. Anna Krueger serves as the subject matter expert for COVID-19, Catie Peranzi oversees the COVID consult call team, and Sara Robinson oversees all aspects of the COVID-19 efforts for the Infectious Disease Epidemiology Program. This allows for a limited amount of non-COVID work from all three individuals. 
In addition to the reprioritization of Maine CDC workload, twenty-three of twenty-six fairs postponed their fairs until 2021. Currently, three fairs are evaluating to determine if it makes sense for the fairs to continue during 2020. Three of Maine’s four deliverables heavily rely on Maine holding their fairs and the objectives must be postponed until fairs are operational again. The fourth deliverable is not able to be completed at this time due to social distancing and other restrictions due to COVID-19.

5) List suggestions for CSTE and CDC for how we can best facilitate your progress (e.g., frequency of individual site calls vs. all site calls, Basecamp utilization, etc.).

At this time, Maine does not have any suggestions as to how CSTE and CDC can help facilitate our progress. It really comes down to the fact that our deliverables heavily rely on fairs being held. 

6) If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mhuynh@cste.org. 

All of Maine’s materials are posted to Basecamp.



OPTIONAL (but please complete if relevant)
If you have a story or anecdotal example of:

· how an individual, group, or community was positively impacted as a result of your YIA project’s interventions; 
· how an outbreak response that was better facilitated as a result of strengthened One Health collaboratives and relationships built through this project; OR
· how Youth in Agriculture network, relationships, or program activities helped in your state’s fight against COVID

either describe it here or just write ‘YES’ and we will follow up with you at a later date.  These ‘success’ stories combined with quantitative impact numbers will be used to share project successes with leadership. 
2020 Influenza and Zoonoses Education among Youth in Agriculture Program
Interim Progress Report
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Impact Chart 
If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report
	Impact 
	Evaluation

	Intervention Activity
	Baseline # prior to current grant period
	How did you measure the baseline? Did you include direct participants, families, etc?
	2020 Audience (youth, community leaders, etc?)
	# of attendees/
participants
	# of materials distributed
	Did you collaborate with another state? If so, which one(s)?
	Pre-test administered? (How many? To whom?)
	Post-test administered? (How many? To whom?)

	EXAMPLE: Four Scenario based training exercises
	X# of training sessions held in 2016 to X total youth aged 11-15
	Only counted the number of actual youths who attended the session
	Youth aged between 12 and 16
	X # attendees per training; total of X attendees
	
	
	
	

	
	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	






