
Please return completed Interim Progress Report to CSTE at mhuynh@cste.org by July 31, 2020.
Note: Please submit one response per site.

1) List project deliverables and describe progress made towards completion of these deliverables:  

· Deliverable 1: Online training for 4-H and FFA students on novel influenza and other zoonotic diseases using a One Health approach

Accomplishments/Progress to-date:
•	Reviewed and strengthened novel influenza and zoonotic disease content added during 2019 pilot year to the Maryland and West Virginia 4-H AH&QA online training program.
•	Enhancements made to AH&QA platform and user interface.
•	The system opened April 15 and will close on August 10, 2020. To date, 1,627 4-H/FFA youth in Maryland and West Virginia have completed the AH&QA program. 
· Created five videos about performing animal health checks that were added to the AH&QA program.
· Conducting Animal Health Certification Checks - Beef
· Conducting Animal Health Certification Checks - Goats
· Conducting Animal Health Certification Checks - Rabbits
· Conducting Animal Health Certification Checks - Sheep
· Conducting Animal Health Certification Checks - Swine
•	To be completed in the fall of 2020 - evaluation of novel influenza and zoonotic disease content in the AH&QA program with pre-test/post-test questions focused on these topics

Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.) 

· Deliverable 2: Healthy Animals | Healthy YOUth Kits - zoonotic disease activity lesson plans and other educational materials and Train-the-Trainer Training 

Accomplishments/Progress to-date:
•	Reviewed and made edits to lesson plans and resources included in the 2019 pilot program Healthy Animals | Healthy YOUth Activity Kits Resource Notebook.
•	Created a new hands-on, educational activity lesson plan to include in the kit.
· Lesson 6.1 What is Antimicrobial Resistance?
· Created videos to guide facilitators through five lessons to compliment the Resource Notebook for the index categories and lessons listed below.
· Lesson 2.1. What is a pathogen? - “Build a pathogen”
· Lesson 2.2. Health for One, One Health for All
· Lesson 3.3. Disease Transmission via Aerosol and Droplets
· Lesson 3.4. Direct Contact Glo Germ Activity
· Lesson 4.2. Painted Hands: Hand Sanitizer and PPE Glove Use
•	Conducted a virtual Train-the-Trainer session, added 9 new facilitators to the pool of 84 trained facilitators who were trained during the 2019 pilot program.
· In process - refill consumable supplies (i.e. Glo-Germ powder, disposable PPE) and add additional supplies for new lesson plans that will be added in 2020 for the 80 kits already distributed to county Extension offices across Maryland and West Virginia.
•	In process - create 35 additional kits to place in county Health Department offices in Maryland.
•	Professional print the Healthy Animals | Healthy YOUth Kits Resource Notebook.
•	In process - create a Healthy Animals | Healthy YOUth Facilitator Resource webpage for trainers, where essential and supplemental resource documents, slide sets, and videos may be accessed.

Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)

· Deliverable X: (please include project deliverable here)
Accomplishments/Progress to-date:
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)

2) List the collaborators involved to-date and briefly describe their role in the project (i.e. 4H/FFA, State PH, State Animal Health).

a. Maryland Department of Health: Project Coordination, Public health subject expertise
b. University of Maryland Extension 4-H: Youth education expertise, Educational resources/curriculum development, Dissemination to youth and volunteers for MD, Coordinate training for Zoonoses Activity Kit Facilitators.
c. Maryland Department of Agriculture: Animal health subject expertise.
d. West Virginia Extension: Dissemination to youth and volunteers for WV.

3) Have you incorporated COVID-19 into activities or deliverables completed in Phase 1 of this project period? If so, please describe in detail (e.g., partners involved, role of each partner, etc.). (Please note: changes to activities, budget, and timeline initially proposed for Phase 2 should be documented in an updated workplan during the contract amendment process).

· County Extension offices were encouraged to use the Zoonoses Activity Kit lessons to conduct virtual meetings with youth, emphasizing lessons that concentrated on proper handwashing and sanitizer use, proper use of PPE, and disease transmission routes.
· COVID-19 references were suggested during virtual Facilitator Training session. Again, calling attention to Healthy Animals | Healthy YOUth Activity Kits lessons that addressed measures similar to CDC recommended COVID-19 practices.



4) Describe areas of concern or challenges in meeting the objectives or providing deliverables especially as it relates to COVID-19.

University of Maryland Extension was in required telework status and most offices were closed between March 13 - July 20, 2020. Telework has been strongly encouraged since July 20, 2020. Additionally, Maryland 4-H in-person activities were suspended between March 13 and August 1, 2020. After August 1 Maryland 4-H in-person activities will be limited to groups of 10 and being held outdoors; a written plan for conducting in-person activities must be submitted and reviewed prior to the activity.
Some Maryland 4-H clubs have met virtually since March 13, 2020, and some activities from the Healthy Animals | Healthy YOUth Activity Kits have been delivered virtually. Many of the kit activities are more relevant than we would all like them to be as we live each day with the current pandemic situation.
The following comment was shared by a county 4-H staff member who had conducted sessions using the kit’s lesson plans in the months immediately preceding the pandemic, 
“I've been finding myself concerned about our members and fretting about what in the world is going on but I am also very thankful that you gave us those zoonosis trainings and we were able to share the information with several clubs. I am hoping that the handwashing activities really made an impression upon folks and that they can take comfort in knowing they have learned something that can literally save lives. So, thank you for the trainings and the new lessons and presentations.”
To date, 1,627 4-H/FFA youth in Maryland and West Virginia have completed the AH&QA program. This number is lower than anticipated at this point in time because completion of the training is associated with livestock exhibition at fairs and shows, and many fairs were cancelled due to COVID-19.

5) List suggestions for CSTE and CDC for how we can best facilitate your progress (e.g., frequency of individual site calls vs. all site calls, Basecamp utilization, etc.).
The flexibility that CSTE and CDC has offered to adjust timelines and budget lines, and to convert some action steps to virtual delivery and execution has been most appreciated. It took organizations and clientele several months to navigate the immediacy created by COVID-19. New routines are becoming formed and programming is resuming in daily and special project work with clientele.
The scheduled site call was beneficial as was the opportunity to schedule a special site call to have questions addressed regarding transition from Phase 1 to Phase 2 efforts.

6) If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mhuynh@cste.org. 
OPTIONAL (but please complete if relevant)
If you have a story or anecdotal example of:

· how an individual, group, or community was positively impacted as a result of your YIA project’s interventions; 
a. See the quote above in response to question 4).
· how an outbreak response that was better facilitated as a result of strengthened One Health collaboratives and relationships built through this project; OR
· how Youth in Agriculture network, relationships, or program activities helped in your state’s fight against COVID
a. The enhanced relationship between partners was beneficial as our individual and collective responses to animal health / human health questions, response strategies, and re-opening suggestions for COVID-19-related concerns were being formulated. 
b. [bookmark: _GoBack]Conversion of a planned face-to-face Healthy Animals | Healthy YOUth Activity Kits facilitator training to virtual format led to creation of videos to demonstrate how to facilitate five lessons from the kit. These videos served purpose during the virtual training, but are being made available on the Facilitator Webpage for others and for future reference.

either describe it here or just write ‘YES’ and we will follow up with you at a later date.  These ‘success’ stories combined with quantitative impact numbers will be used to share project successes with leadership. 
2020 Influenza and Zoonoses Education among Youth in Agriculture Program
Interim Progress Report
Site: __Maryland______________________________
Completed by: __Chris Anderson_____________________
Date: ____7/28/20___________________________
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Impact Chart 
If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report
	Impact 
	Evaluation

	Intervention Activity
	Baseline # prior to current grant period
	How did you measure the baseline? Did you include direct participants, families, etc?
	2020 Audience (youth, community leaders, etc?)
	# of attendees/
participants
	# of materials distributed
	Did you collaborate with another state? If so, which one(s)?
	Pre-test administered? (How many? To whom?)
	Post-test administered? (How many? To whom?)

	EXAMPLE: Four Scenario based training exercises
	X# of training sessions held in 2016 to X total youth aged 11-15
	Only counted the number of actual youths who attended the session
	Youth aged between 12 and 16
	X # attendees per training; total of X attendees
	
	
	
	

	MD and WV Online AH&QA Program
	Online training module –  Site opened Apr 15 and will close Aug 10, 2020
	As of 7/28/20,    1,627 junior and intermediate/senior aged youth registered and completed the online training
	The online training is open so that parents, club leaders, and others can complete the program
	Individual online completion
	N/A
	Maryland and West Virginia collaborated on the AH&QA program
	1724  youth completed the Online AH&QA Training Pre-test
	1627  youth completed the Online AH&QA Training Post-test

	Train the Trainer Session
	Initially planned as an in-person training. Purpose to add to the 84 facilitators trained in 2019
	
	9 new facilitators trained on July 14, 2020 via virtual training
	Participation of 9 faculty/staff/volunteers/fair officials and 10 Team members and guest speakers.
	80 Zoonosis Activity Kits distributed to Maryland and West Virginia counties in 2019. 30 new kits to be distributed in Phase 2 of 2020
	Maryland and West Virginia
	0
	0

	
	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	






