Please return completed Final Progress Report to CSTE at mhuynh@cste.org by December 31, 2020.
Note: Please submit one response per site.

1. Identify your top achievements for the project.

a. Creation of cross-institute work team for One Health: A cross-institute team consisting of Extension Educators, 4-H Program Coordinators, District Directors and MSU Extension Administration have formed a core team that meets at least bi-monthly to discuss upcoming events and potential challenges, review materials available on the website, recommend website updates, and identify additional content for the website. 

Due to the unusual circumstances that 2020 has challenged us with, the team has met virtually and has developed a contingency response plan for any animal health situations for fairs and exhibitions that are holding in person events, given that MSU Extension employees are currently not allowed to participate in any face to face programming. 
b. Create and distribute 85 “Game Night” activity kits for each county 4-H office, utilizing materials and activities created by Michigan and other states funded by this project and available on the Basecamp site and CSTE Influenza and Zoonoses Education among Youth in Agriculture Resource Repository (https://resources.cste.org/yia). 

Due to the constraints on gathering due to the COVID-19 pandemic, we knew that to meet educational goals, we needed to adjust our outreach to provide for online learning opportunities. MSU Extension has suspended all in person programming activities, which include traditional animal science club meetings where the Game Night Activities were intended to be utilized.  To accommodate for this unique situation, a set of online education resources including videos and online games are being developed and will be posted online.  A video will demonstrate how to play the Germo game.  The online Kahoot platform is being utilized to create interactive content that aligns with other activities contained in the kits.  These games can be utilized during online 4-H club meetings or by youth independently. These resources will be posted to the MSUE Animal Science website once they are completed.

c. Held virtual meeting/webinar for Extension partners in other states to highlight the resources developed from this CDC/CSTE funding effort.  Participants learned about the variety of tools and materials that are available for use in their programs to meet the needs of educating youth involved in agricultural programs about zoonotic diseases and their prevention.  The goal is to aid states in building their capacity in zoonotic disease education and response by utilizing pre-existing materials and resources (https://resources.cste.org/yia).  In this way, we hope to extend the reach of the investments made by CDC/CSTE in a handful of states to other states and youth agriculture organizations who were not direct beneficiaries of this funding.  The webinar was recorded, close captioned and posted online for future viewing at https://mediaspace.msu.edu/media/Michigan+State+University+Extension-+Disease+Prevention+and+Education+Webinar/1_wh80b3ca.  To date, the webinar has been viewed live and via the recording, by 33 individuals.   All respondents to the post-webinar survey “strongly agreed” or “agreed” that they gained an understanding of the CDC’s One Health initiative, increased their knowledge of animal health planning at fairs and exhibitions, learned about tools and resources to help build an animal health response plan, learned about disease education resources developed for youth in agriculture education programs that may be useful for their state, better understand the role of public health when there is an animal illness outbreak event, and gleaned some ideas for how to improve communication among animal health and human health experts.  All respondents “strongly agreed” that they felt they could utilize the resources shared in the webinar in their state.

d. Pre-fair preparation webinar: MDARD, MDHHS and MSUE staff presented important pre-fair information for fair boards, superintendents, and MSUE staff including animal exhibition requirements, animal health procedures, and practices to implement to protect the health of exhibitors, their families and the public. This webinar was recorded, closed captioned, posted online at https://mediaspace.msu.edu/media/2020+Animal+Health+at+FairsA+Keeping+Animals+and+People+Healthy/0_fphoa3py, shared among the Michigan Association of Fairs and Exhibitions membership and MSUE staff and uploaded to Base Camp, reaching at least 85 individuals.  Although most agricultural fairs were cancelled for the 2020 season, this format was a great way to provide information in a virtual format and make it available to a wider audience via posting of recorded content on the MSUE website. 

e. MSUE Animal Health website updates and improvements at https://www.canr.msu.edu/fair-and-exhibition-animal-health/index and https://www.canr.msu.edu/animal_science/zoonotic-disease 

2. If there have been changes to the collaborators on this project since completion of the interim report, please list the updated collaborators and briefly describe their role in the project (i.e. 4-H, State PH, State Animal Health).  

· Nick Babcock, MSU Extension, creation of online game content using previously designed curriculum and contingency response plan

3. Please describe areas of concern or challenges in meeting the objectives or providing deliverables. 

a. Long delays in CSTE contract process and fulfilling financial obligations to grantees was very frustrating.  Phase 2 was to begin August 1, 2020.  Michigan had no changes to the timeline or activities to report.  Contract amendments to the General Contract Agreement for this phase were not completed by CSTE and sent to MDHHS until Nov. 25, 2020.  During this delay, MSUE was not able to access funds to cover the work they were doing to complete the project objectives. 

b. Alternatively, although meeting the grant’s planned objectives was challenged due to COVID-19, CSTE has been very supportive of adjustments we made to our grant objectives to incorporate pandemic precautions.  Although many in-person events and plans had to be cancelled, we were able to pivot to virtual meetings and made minor adjustments to the grant objectives in order to meet the new needs for socially distanced learning and activities.

c. With in-person seminars and meetings cancelled due to the COVID-19 pandemic, we had to adjust planned activities to virtual platforms when possible.  In most instances we were still able to meet the planned objective, with the following exceptions: 
 
1. MDHHS was not able to provide the “Be a Disease Detective” session as part of the MSUE Exploration Days in 2020.  This is a 4-day event, hosted annually on the campus of Michigan State University for youth involved in 4-H.  The event was cancelled due to concerns about COVID-19. For the past 4 years, MDHHS has been providing a 2-day, 6 hours of instruction session to 4-H youth, focused on zoonotic diseases, disease outbreak investigation, laboratory methods, and disease prevention.  Plans are underway at MDHHS to adapt the curriculum to incorporate virtual content and utilize online platforms, in the event the Exploration Days is offered as a virtual experience in 2021.  We have submitted our program proposal to MSUE.

2. MDHHS had planned to provide information about zoonotic influenza to Michigan healthcare providers during the MDHHS Immunization Division’s annual series of meetings each fall around the state.  Unfortunately, due to COVID-19, this meeting was scaled down to a half-day event and was held virtually, with content focused on concerns about falling immunization rates as a result of the pandemic, and discussions about pending SARS CoV 2 vaccination candidates.  We will continue to look for opportunities to provide information about zoonotic influenza to Michigan healthcare providers.

4. Do you expect one or more deliverables to be unmet by the project end date of December 31, 2020? If so, please indicate whether you would like to request a contract extension and what the new end date would be. Additionally, please include an updated project timeline.

We expect to meet our deliverables by the end of the year, Dec. 31, 2020.

5. If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mhuynh@cste.org. 

6. Please list suggestions and recommendations for CSTE and CDC for how we can improve support to future sites participating in the project.  

a. Improve CSTE processes for contracts and fund distribution.  MDHHS appreciates having MSUE as a long-term partner in the endeavor, and it is important that we be able to meet our financial obligations for the work they are doing in a timely fashion.  Unfortunately, this has been an ongoing issue with previous year’s funding as well.
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Impact Chart 
If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report. Please note: the chart below should be reflective of the cumulative project period and can include deliverables met in the interim report.
	Impact 
	Evaluation

	Intervention Activity
	Baseline #  prior to 2020 grant period
	How did you measure the baseline? Did you include direct participants, families, etc?
	2020 Audience (youth, community leaders, etc?)
	# of attendees/participants
	# of materials distributed
	



Did you collaborate with another state? If so, which one(s)?
	Pre-test administered? (How many? To whom?)
	Post-test administered? (How many? To whom?)

	EXAMPLE: Four Scenario based training exercises
	X# of training sessions held in 2016 to X total youth aged 11-15
	Only counted the number of actual youth who attended  the session
	Youth aged between 12 and 16
	X # attendees per training; total of X attendees
	
	
	
	

	“Swine Influenza Tips and Toolkits” webinar  April 13, 2020
	0
	Direct participants and those who watched the recorded webinar
	Fair Organizers
	40 direct participants and 16 who have viewed the recorded webinar to date
	
	No
	No
	No

	Michigan Pre-Fair Webinar  May 6, 2020
	0
	Direct participants and people who viewed the recorded webinar
	Fair Organizers, MSUE Regional Staff
	60 direct participants and 12 who viewed the recorded webinar to date
	
	No
	No
	No

	Build and Distribute 85 “Game Night” Activity Kits to MSUE offices in each Michigan County.
	0
	Counted the number of activity kits created and distributed. The actual reach has the potential to be exponentially more, as kits are advertised to county staff and volunteers.
	Youth, Local MSU Extension Staff, Adult 4-H Volunteers, Teachers
	Kits were distributed to 83 Counties in Michigan, as well as to the MSUE Veterinary Science Program, for use by 4-H youth, project groups and families served by these Extension offices.
	85 Activity Kits
	No
	No
	No

	Planning, Response, and Education to Prevent Disease Outbreaks at Fairs and Exhibitions webinar for Regional State Extension Partners, Oct. 27, 2020
	0
	Direct participants and number documented who viewed the posted webinar
	State Extension 4-H Leaders/Animal Science staff/community leaders
	33
	MSUE Website resources, CSTE Youth in Agricultural Education Resource Repository
	The program invitation was sent to all 4-H State Leaders in the country.
	No
	A program evaluation was distributed to all who participated in the webinar and the recording. 
33

	
	
	
	
	
	
	
	
	



