Please return completed Final Progress Report to CSTE at mhuynh@cste.org by December 31, 2020.
Note: Please submit one response per site.

1. Identify your top achievements for the project. 
a. The BlueNotFlu.org website was updated to improve usability and incorporate content from project partners. The website saw significantly increased traffic (over previous years) to online materials (website with courses, activities, and additional resources; middle/high school and elementary courses) even with virtual-only promotion. 
b. Additional content to support training of adults in youth outreach was developed and shared widely, including facilitator guides, workshop templates, and more. 
c. A virtual train-the-trainer session for Iowa County Youth Coordinators was held with 49 attendees who participated live and 27 additional individuals registered who could not attend live but were sent a link to the recording. The registrants cumulatively impact an estimated 36,500 youth.
d. The reach of the “Bring Home the Blue, Not the Flu!” suite of materials was further increased by leveraging delivery models, templates, and repositories created by other entities in response to the increased need for virtual learning due to the pandemic. For example, development of Iowa 4-H ‘At Home On the Go’ lessons based on our materials and inclusion within database of at-home learning resources, social media promotion by collaborators.
e. [bookmark: _GoBack]Alignment of the “Bring Home the Blue, Not the Flu!” curriculum with various national curriculum standards was described, including with National Agricultural Literacy Outcomes, Common Core standards, Next Generation Science Standards, National Health Education Standards, and Iowa Core Standards. This enabled the curriculum to be eligible for consideration of incorporation into the National Agriculture in the Classroom matrix and the Iowa Agriculture Literacy Foundation lesson plans (both currently under review, approval expected), which have significant reach among agriculture educators. This also enabled development of a positive relationship with the national Youth for the Quality Care of Animals (YQCA) team, which will be beneficial for future harmonization of efforts to educate youth in agriculture.
f. Work of the Standardized Curriculum WG was advanced through a MPH Practicum project which reviewed, organized, and communicated the resources available through the wider CDC/CSTE Youth in Agriculture project, particularly in relation to that National Education Standards and 4-H Program Priorities satisfied. 
g. A positive relationship was developed with Tennessee 4-H to leverage future use of “Bring Home the Blue, Not the Flu!” curriculum in their youth outreach programming (a state previously not included in YIA collaborations). Additionally, Nebraska continued to successfully utilize a custom version of the ‘Bring Home the Blue, Not the Flu’ landing page to direct youth towards Iowa’s curriculum.

2. If there have been changes to the collaborators on this project since completion of the interim report, please list the updated collaborators and briefly describe their role in the project (i.e. 4-H, State PH, State Animal Health).
a. There has been no change in collaborators during this project period. 
b. Collaborator activities during this project period included the following:
i. Association of Iowa Fairs 2020 Conference and Annual meeting (delayed until Feb 5-7, 2021), Dr. Jeff Kaisand, State Veterinarian, Iowa Department of Agriculture and Land Stewardship (IDALS). Dr. Kaisand give a presentation on the ‘Bring Home the Blue, Not the Flu’ curriculum and associated resources and its importance to Iowa agriculture and to youth fair exhibitors. Preparation completed/funds spent this year.

3. Please describe areas of concern or challenges in meeting the objectives or providing deliverables.
a. Like all sites, we experienced challenges with cancellation of in-person events or migration of events into virtual formats and needed to adjust work plans and activities. These challenges were overcome and we were able to meet our project objectives and we feel that we were able to impact just as many, if not more, youth as if we were able to hold the original events intended.

4. Do you expect one or more deliverables to be unmet by the project end date of December 31, 2020? If so, please indicate whether you would like to request a contract extension and what the new end date would be. Additionally, please include an updated project timeline.
a. No. No contract extension is requested. One event scheduled for 2020 has been postponed until 2021, but preparation for this event was completed in this CY and no funds were allocated for travel for this event.

5. If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mhuynh@cste.org. 
a. All materials uploaded to Basecamp site.

6. Please list suggestions and recommendations for CSTE and CDC for how we can improve support to future sites participating in the project.
a. Increased frequency of engagement from CSTE and CDC, as well as with other participating states, would be an added benefit to the project, but is not necessarily needed and we were able to achieve our objectives successfully even with ‘light touch’ support from CDC/CSTE.
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Impact Chart 
If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report. Please note: the chart below should be reflective of the cumulative project period and can include deliverables met in the interim report. 
	Impact 
	Evaluation

	Intervention Activity
	Baseline #  prior to 2020 grant period
	How did you measure the baseline? Did you include direct participants, families, etc?
	2020 Audience (youth, community leaders, etc?)
	# of attendees/participants
	# of materials distributed
	



Did you collaborate with another state? If so, which one(s)?
	Pre-test administered? (How many? To whom?)
	Post-test administered? (How many? To whom?)

	EXAMPLE: Four Scenario based training exercises
	X# of training sessions held in 2016 to X total youth aged 11-15
	Only counted the number of actual youth who attended  the session
	Youth aged between 12 and 16
	X # attendees per training; total of X attendees
	
	
	
	

	“Bring Home the Blue, Not the Flu!” online course
	In 2019, there were 1,001 users who visited the website, 303 users who took the course for youth aged 7-12 years, and 698 users who took the course for youth aged 13-18.
	Unique visitors

	Anyone with internet access
	Total visitors to the website: 1,731

Unique visitors to the website: 1,451

Took the middle/high school course: 360

Took the elementary course: 155

Logins to the password-protected instructor version of the website: 70
	N/A (full access to all materials on website, including both online courses)
	Users nationwide could complete; NE has unique online form from 2019 collaboration
	Yes; 146 (incl. 79 from NE); optional for individuals who completed online course 
	Yes; 146 (incl. 79 from NE); optional for individuals who completed online course


	Sharing “Bring Home the Blue, Not the Flu” course website via social media
	N/A
	People reached, engagements, and shares as reported by Facebook
	People reached, engagements, and shares as reported by Facebook
	346 people reached, 19 engagements, 3 shares
	Link to course website: www.BlueNotFlu.org 
	
	N/A
	N/A

	Train-the-Trainer Workshop for the Blue Not Flu material
	N/A
	We measured the number of attendees as well as the number of youth each attendee interacts with per year
	Partners in Iowa and Tennessee Extension and 
4-H
	49 attendees live; 27 additional registered but could not attend live and were sent link to recording

Approximately 36,500 youth are impacted every year by the individuals who attended/registered for this training.
	Digital packet- included
	Tennessee
	N/A
	Not a post-test, but a survey about the materials and the training session was completed by 20 live attendees

	Virtual Animal 
Cy-ience Academy
	N/A
	We measured only the number of youth and adults that attended the session. 
	4-H youth from five different states
	8 attendees
	Link to course website: www.BlueNotFlu.org 
	Georgia, Mississippi, North Dakota, Tennessee 
	N/A
	N/A



