Please return completed Final Progress Report to CSTE at mhuynh@cste.org by December 31, 2020.

Note: Please submit one response per site.

- Identify your top achievements for the project.

- Successfully implemented contract with the UNL Dept of Natural Resources.

- Maintained the public facing website for Youth In Agriculture (YIA) at the UNMC College of Public Health. This includes managing the servers, database and maintaining and refreshing the exiting code on a regular basis.

- Drafted a new module of COVID 19 for kids and teenagers that will be added to the YIA website in Spring 2021.

- Created a mobile Zoodemic game on Apple and Android platforms which will be launching in spring of 2021. This was inspired by this grant although no funding was used.

- If there have been changes to the collaborators on this project since completion of the interim report, please list the updated collaborators and briefly describe their role in the project (i.e. 4-H, State PH, State Animal Health).

- Dr. Elizabeth VanWormer has joined the project in place of Kathy Potthoff. Dr. VanWormer is the NE One Health Coordinator and her expertise and excitement for this topic will benefit this project and NE significantly. She will be joined by a graduate student, Ian Hoppe, who will be helping lead education efforts.

- Please describe areas of concern or challenges in meeting the objectives or providing deliverables.

- COVID priorities have slowed work on this project but now that Dr. VanWormer and Mr. Hoppe are on board, we should start making a lot of progress.

- Do you expect one or more deliverables to be unmet by the project end date of December 31, 2020? If so, please indicate whether you would like to request a contract extension and what the new end date would be. Additionally, please include an updated project timeline.

- Yes, a contract extension is requested through July 31, 2021. We will begin these efforts with our UNL contractor during the new school semester.

- If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mhuynh@cste.org.

- We still are currently using IA’s education module but plan to develop additional materials moving forward and will update when finalized.

- YIA site:

  - https://www.unmc.edu/publichealth/yia/ - landing page

  - https://www.unmc.edu/publichealth/yia/resources/index.html - resources page

  - https://www.unmc.edu/publichealth/yia/education/index.html - education page

- Please list suggestions and recommendations for CSTE and CDC for how we can improve support to future sites participating in the project.

None at this time. Thank you for your flexibility during this difficult time.

Impact Chart

If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report. Please note: the chart below should be reflective of the cumulative project period and can include deliverables met in the interim report.

Due to COVID education activities have not been implemented. We plan to have a lot of data in this table in the next 6 months.

| Impact |  |  |  |  |  |  | Evaluation |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Intervention Activity | Baseline # prior to 2020 grant period | How did you measure the baseline? Did you include direct participants, families, etc? | 2020 Audience (youth, community leaders, etc?) | # of attendees/participants | # of materials distributed | Did you collaborate with another state? If so, which one(s)? | Pre-test administered? (How many? To whom?) | Post-test administered? (How many? To whom?) |
| EXAMPLE: Four Scenario based training exercises | X# of training sessions held in 2016 to X total youth aged 11-15 | Only counted the number of actual youth who attended the session | Youth aged between 12 and 16 | X # attendees per training; total of X attendees |  |  |  |  |