Influenza Education among Youth in Agriculture

Progress Report

Please return completed Progress Report to CSTE at mschroeder@cste.org.

- Identify your top three achievements over the last quarter.

  - The Center for Food Security and Public Health (CFSPH) promoted the existing Excellence in Exhibition course at several different venues and made arrangements for continued promotion of the course at upcoming events (see attached spreadsheet for details).

  - The CFSPH submitted the current online course for state and national 4-H peer review.

  - CFSPH published an article in Fairs and Expos discussing zoonotic influenza prevention and promoting the online course.

- Please list the collaborators on this quarter’s achievements and briefly describe their role in the project (i.e. 4H, State PH, State Animal Health).

CFSPH and the Iowa Department of Public Health (IDPH) worked with the International Association of Fairs and Expositions (Marla Calico) and the National Association of Agriculture Educators to encourage participation in the existing course by hosting exhibit tables and giving an oral presentation (IAFE). CFSPH submitted an application to host exhibits at the Iowa State FFA Convention and Iowa Association of Agriculture Educators Conference.

The Iowa Department of Agriculture and Land Stewardship (Dr. Dave Schmitt, State Veterinarian) presented recommendations to the Iowa fair boards at the Association of Iowa Fairs Annual Conference, encouraging them to consider requiring all exhibitors to take the course prior to exhibiting animals.

CFSPH met with Iowa State 4-H Youth Program Specialists to explore options for partnerships and increase use of the available course. CFSPH worked with program specialists to submit a proposal for the Iowa 4-H Conference and Animal Science Roundup.

CFSPH is working with the National Pork Board to place a link to the course on the Pork Checkoff website.

- Please describe areas of concern or challenges in meeting the objectives or providing deliverables.

None

- Please include an updated project timeline.

| May 1–Oct 31, 2017 | - Enhance existing course - CFSPH continued to research how to incorporate the course into state and national 4-H curriculum through state and national 4-H development standards and peer review. - CFSPH continued to make course edits as appropriate to maintain content accuracy and timeliness. - As a collaborating center with the OIE, CFSPH explored placing the OIE logo on the course. - CFSPH modified the Google Analytics tracking of the course to better capture course use. - Promote and increase existing course distribution and implementation - CFSPH continued to distribute materials at events listed in the project proposal. - CFSPH presented a seminar during the 2017 American Association of Extension Veterinarians’ annual meeting (held during the United States Animal Health Association meeting) and distributed promotional materials. - CFSPH hosted an exhibit table at the National FFA Convention. CFSPH also provided printed material for youth, educators, and others at the National FFA Convention. - CFSPH registered, researched, and began making travel arrangements to host an exhibit table and interactive teacher/student workshop at the International Association of Fairs and Expositions Annual Convention. - CFSPH registered, researched, and began making travel arrangements to host an exhibit table at the National Association of Agriculture Educators conference. - Develop new course for younger audiences (specifically, children aged 7–12 years) based on existing course - CFSPH continued to develop the outline, researched content, and researched best practices in online course development for the new course. |
| --- | --- |
| Nov 1, 2017–Feb 28, 2018 | - Enhance existing course - CFSPH consulted with CDC to revise the evaluation component as necessary to collect the most useful data to improve the course. - CFSPH worked with CDC and CSTE to participate in any evaluation framework to assess implementation of the project on a national level. - CFSPH submitted the current course for state and national 4-H review. The course was approved as official Iowa 4-H curriculum in January 2018. - Promote and increase existing course distribution and implementation - CFSPH and collaborating agencies pursued additional opportunities to engage participation among Iowa youth through exhibits, formal presentations, and/or demonstrations/workshops. - CFSPH and IDPH submitted an abstract to the Council of State and Territorial Epidemiologists Annual Conference (2018). - At all venues, CFSPH displayed interactive elements of the course on laptops and tablets, distributed informational flyers, handouts, stickers, and other material developed by CFSPH advertising the free course, and distributed zoonotic disease resources developed by CFSPH, other states, and CDC. - Develop new course for younger audiences based on existing course - CFSPH identified a DVM/MPH student intern to help with course development. - CFSPH expanded course curriculum to build upon the current course structure and be age appropriate for younger children, including more gamification, less text, a lower reading level, and shorter lessons. - CFSPH finalized an outline for the new course. |
| March 1–June 30, 2018 | - Enhance existing course - CFSPH will review and modify the existing course website to ensure compliance with Section 508 of the Rehabilitation Act, ensuring accessibility for all learners and allowing distribution through federal partners. - CFSPH will consult with Iowa State University’s Center for Excellence in Learning and Teaching (CELT), http://www.celt.iastate.edu/about, to identify and implement enhancements to the current course. Specifically, CFSPH will consult CELT’s Online Learning Innovation Hub aimed at enhancing quality of instruction, increased reach, and accessibility. - CFSPH will revise the evaluation component as necessary to collect the most useful data to improve the course. - CFSPH will work with CDC and CSTE to participate in any evaluation framework to assess implementation of the project on a national level. - Promote and increase existing course distribution and implementation - CFSPH will continue to work with the National Pork Board to add a link to the course on the Pork Checkoff website. - CFSPH will contact the Youth for the Quality Care of Animals administrators to explore options for including the Excellence in Exhibition course as part of the YQCA curriculum. - CFSPH and collaborating agencies will continue to pursue opportunities to engage participation among Iowa youth through exhibits, formal presentations, and/or demonstrations/workshops at the following venues: - 4-H State Conference and Animal Science Roundup (2018)—CFSPH will continue to work with state 4-H to host an interactive workshop to directly reach our target audience of Iowa youth involved in 4-H. By holding an interactive workshop during the three-day event, we will share some of the hands-on interactive elements of the course and encourage all Iowa 4-H members in attendance (more than 1,000 each year) to take the course in preparation for the upcoming exhibition season. - CFSPH will host an FFA event at the Iowa State University College of Veterinary Medicine (112 students). - Develop new course for younger audiences based on existing course - CFSPH will continue course development and send to collaborating agencies and partners for review. - Expand course curriculum to build upon the current course structure and be age appropriate for younger children, including more gamification, less text, a lower reading level, and shorter lessons. - Develop an evaluation component comparable to the existing course and consistent with any guidelines outlined by CDC and CSTE to be included in the new curriculum. In addition to the online course, supplemental materials will be developed, such as signs that 4-H clubs and FFA exhibitors can post at fairs/exhibitions promoting public health prevention messages. |

- If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mschroeder@cste.org.

All materials are posted to the Basecamp site.

- Please list suggestions for CSTE and CDC for how we can best facilitate your progress.

Continued assistance in promoting the course at the national level would be valuable.

- Please complete the attached spreadsheet to indicate progress made towards project deliverables.

OPTIONAL

If you have a story or anecdotal example of how an individual, group, or community was positively impacted as a result of your YIA project’s interventions, either describe it here or just write ‘YES’ and we will follow up with you via phone or at a later date.  These ‘success’ stories combined with quantitative impact numbers will potentially be used on impact statements and to share project successes with leadership.

YES