Influenza and Zoonoses Education among Youth in Agriculture
Progress Report 


Please return completed Progress Report to CSTE at mschroeder@cste.org.  


1. Identify your top three achievements over the last quarter. 
· Ordered materials for Glo Germ and saliva swap demonstration kits
· Implemented Iowa’s Excellence in Exhibition training module into the NEW State 4-H Livestock Quiz Bowl Contest
· Intermediate & Seniors were to watch and study the first module, “Introduction to Influenza, Zoonosis and Disease Risks”
· The number of times questions from this module are answered correctly will be recorded to identify the effectiveness of this contest requirement
· Sent email invite to regional and state fair board directors

2. Please list the collaborators on this quarter’s achievements and briefly describe their role in the project (i.e. 4H, State PH, State Animal Health).
· 4-H (Dr. Leigh Ann Skurupey): She is working with us to develop hands on educational trainings for 4-H Animal Science Project participants to identify ways to reach/educate Extension agents/coaches/club leaders and 4-H members in order to implement tangible learning activities that directly apply to real-world agricultural situations. 
· ND Department of Agriculture, Animal Health Division: The State Veterinarian, Deputy State Veterinarian, and ND State Board of Animal Health members are acting as our liaisons with industry.
· ND Environmental Health Association: Environmental health practitioners from the state health department and LPHUs will help us distribute materials in their jurisdictions and notify us of possible educational opportunities. 
· ND Fair Boards: we have sent an email outlining our program and looking for a time that we can meet to discuss our plan.
· ND Dept of Health, Education and Technology: They will work with us to record and edit education videos (15-30 seconds long) highlighting barn safety and health and wellness among humans/animals.

3. Please describe areas of concern or challenges in meeting the objectives or providing deliverables.
· Recording videos of 4-H members giving health and wellness tips must be postponed until winter is closer to over due to weather concerns and travel conditions.




4. Please include an updated project timeline.

	[bookmark: RANGE!A1]Objective One – Collaborative Development

	
	Activity
	
	Completion Date
	
	Updated Timeline

	
	Hire Student Intern
	
	31-Jul-17
	
	1-Oct-17

	
	Meet with 4-H Youth Livestock Specialist
	
	31-Jul-17
	
	1-Aug-17

	
	Meet with FFA Leaders
	
	31-Jul-17
	
	30-Apr-18

	
	Develop stakeholder meeting
	
	16-Aug-17
	
	13-Apr-18

	
	
	
	
	
	

	[bookmark: RANGE!A13]Objective Two – Training Activities

	
	Activity
	
	Completion Date
	
	

	
	Iowa State University online training
	
	1-May-18
	
	1-May-18

	
	MN Fair posters/placards/postcards
	
	1-Jun-18
	
	1-Jun-18

	
	Georgia 4-H Friends Magazine
	
	1-Jun-18
	
	1-Jun-18

	
	NDSU Animal Biosecurity videos
	
	1-Jun-18
	
	       1-Jun-18

	[bookmark: RANGE!A24]
Objective Three – Summit
	
	
	
	

	
	Activity
	
	Completion Date
	
	

	
	Invite MT/SD/WY to Summit
	
	21-Jul-17
	
	15-Apr-18

	  
	Hold Summit
	
	29-Sep-17
	
	31-May-18

	
	Finalize minutes and initial summit report
	
	31-Oct-17
	
	30-Jun-18

	
	
	
	
	
	

	[bookmark: RANGE!A35]Objective Four – Evaluation
	
	
	
	

	
	Activity
	
	Completion Date
	
	

	
	In-person training evaluation survey
	
	31-Aug-17
	
	15-Mar-18

	
	Evaluation of online trainings and format
	
	20-Oct-17
	
	20-Mar-18

	
	Development of fair survey evaluation
	
	29-Dec-17
	
	29-Dec-17

	
	Evaluation of stakeholders’ strategic plan
	
	12-Jan-18
	
	15-Jun-18

	
	Finalize initial stakeholder report & send out
	
	9-Feb-18
	
	15-Jun-18


Evaluate results: State 4-H Livestock Quiz Bowl 	4-Mar-18		14-Apr-18

5. If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mschroeder@cste.org. 
· We have not distributed any products at this time; however, materials have been ordered.
· We drafted a newsletter to be sent out to 4-H and Extension agents throughout the state during the summer months. Our goal is to release the first issue in April.
· We drafted a presentation aimed at younger 4-H members. Our goal is to finalize the PowerPoint slides and script for presenters within the month.
· [bookmark: _GoBack]Additionally we have drafted a word circle and word scramble also aimed at the younger 4-H members.  

6. Please list suggestions for CSTE and CDC for how we can best facilitate your progress.
· The open forum discussion on our most recent call was very helpful, and all of the suggested prompts were relevant to our project. If possible, on the next call we’d like to hear about what other states have done to grow their contact networks for distribution of materials.
· Compiling a list of the states’ relevant social media contact information (e.g., Facebook pages, Twitter handles, Instagram names or tags, YouTube channels, etc.) would make it much faster and easier to find their social media content.

7. Please complete the attached spreadsheet to indicate progress made towards project deliverables.  


