## Sheet1
Please describe the progress made towards completion of the following project deliverables. | Summary of what was done (200 words or less). (What activities have taken place over the past 3 months? What materials were developed or produced as a result?) | Impact Statement (300 words or less) (How have these activities addressed one or more of the project objectives? Be sure to quantify impact as much as possible (i.e. How many educators and youth have been reached?)
Deliverable 1: Collaborative Development | Sent emails to regional and state fair boards. Working with Education Technology Dept to set up times to record education pieces. Leigh Ann has required all participants in the NEW State 4-H Livestock Quiz Bowl Contest to complete the "Introduction to Influenza, Zoonosis and Disease Risks" module in Iowa State University's "Excellence in Exhibition: Preventing Disease in Animals and People" series. | # of 4-H members participating in NEW State 4-H Livestock Quiz Bowl Contest : TBD - The Quiz Bowl takes place on March 4, 2018. # of fair board members contacted: 8-10; however 2 emails bounced back so we need to find another contact method. Have not filmed the education pieces yet, so this is unknown.
Deliverable 2: Training Activities | Participants in the NEW State 4-H Livestock Quiz Bowl Contest must complete the "Introduction to Influenza, Zoonosis and Disease Risks" module in Iowa State Univesity's "Excellence in Exhibition: Preventing Disease in Animals and People" series. Created a presentation for younger 4-H members using the idea of becoming a "Deputy Germ Buster." This is still going through the approval process, but should be ready within a month.
Deliverable 3: Summit | Internal group met to identify dates for this summit and to determine if utilizing in-person and video conferencing will be a better method.
Deliverable 4: Evaluation | This was previously reported; will do additional evaluation when fair season starts.