Influenza Education among Youth in Agriculture 2nd Quarter (Nov-Feb) Progress Report 


Please return completed Progress Report to CSTE at mschroeder@cste.org.  

1. Identify your top three achievements over the last quarter. 
a. Hosting the 2nd annual Emerging Issues Breakfast: 63 attendees from 30 different entities/agencies. As a result of this breakfast the Minnesota Board of Animal Health, in partnership with USDA APHIS VS, will begin hosting quarterly Minnesota One Health Network meetings for this same group of people. The Emerging Issues Breakfast will continue to be offered on an annual basis to cap off the end of the year. We are so pleased this breakfast has resulted in a spin-off event that will be paid for by other One Health partners. 
b. Successfully getting a sub-award to our 4-H partners in order for them to purchase materials to create the Zoonotic Disease Toolkits, and to host the Ag Career Day, among other things. Joe piloted these tool kits during an educators’ meeting and everyone was really excited about them.  
c. Safer FACEs is now live and so far we’ve had 23 people contact us to complete the training. These people have mostly come from Minnesota but we also have one person from Iowa and one person from Argentina. Members of FFA, 4-H, and the Miracle of Birth Barn from the state fair are among interested parties. Safer FACEs info page. 

2. Please list collaborators on this quarter’s achievements, and briefly describe roles of different organizations involved (i.e. 4H, State PH, State Animal Health)
a. MDH staff planned and hosted the Emerging Issues Breakfast itself. However, the Board of Animal Health and USDA APHIS VS are collaborating with us to continue these types of meetings on a quarterly basis. 
b. 4-H has been very active in organizing the Ag Career Day and planning the Zoonotic Disease Toolkits. Joe is writing the curriculum for two lessons right now and 4-H will be assembling and distributing the kits. Joe is also writing out the outline for the 4-H biosecurity educational video while I am writing out the outline for the 4-H food safety video. 
c. MDH is responsible for the development of Safer FACEs but 4-H and the Upper Midwest Agricultural Safety and Health (UMASH) center have been helping us promote the training program. 


3. Please describe any areas of concern or challenges to meeting the objectives or providing deliverables.
a. Time to work out these outreach activities due to competing interests (animal contact outbreaks, routine surveillance, rabies surveillance, etc.) at MDH and also competing interests for 4-H staff.
b. It took longer to get the sub-award worked out for 4-H than I would have liked. 

4. Please include an updated project timeline.
a. See attachment	

5. If you have materials you are already distributing, please include a sample PDF or link of those materials.
a. No new products to show from this quarter but we should have several by the next report. 


6. Please list any suggestions for CSTE and CDC for how we can help best facilitate your progress.
a. [bookmark: _GoBack]None

7. Please complete the attached spreadsheet, to indicate progress made towards project deliverables.  
a. See attachment


