Influenza and Zoonoses Education among Youth in Agriculture

Progress Report

Please return completed Progress Report to CSTE at mschroeder@cste.org.

- Identify your top three achievements over the last quarter.

  - A Certified Livestock Leader training event in Butler State Park Resort, KY,          December 2, 2017

  - A 4-H Leader workshop February 10, 2018, Lexington, Kentucky

  - Skillathon for 4-H youth February 17, 2018 with multiple choice questions for 3 different age groups

- Please list the collaborators on this quarter’s achievements and briefly describe their role in the project (i.e. 4H, State PH, State Animal Health).

  - 4-H: set up trainings and organized the Skillathon, printed and administered the Skillathon and questions, printed hand outs

  - UK Student: assisted with 1 of the trainings, created power point for food safety, created biosecurity bucket information, will do test analysis of Feb. 10 training

  - State Public Health: Ordered training and game supplies, created training power point, created the Skillathon questions, planned the “games” used during trainings, created the pre and post-test, printed handouts, Instructed at the trainings, pre and post-test analysis at Dec.. training

- Please describe areas of concern or challenges in meeting the objectives or providing deliverables.

  - All scheduled trainings are complete. We need to develop some new training time periods or start working with fair organizers for animal safety education and written materials such as posters, coloring sheets, etc.

- Please include an updated project timeline.

  - We need to develop a new one. We had one through the end of February.

  - April 26, 2018: Poster presentation at the Kentucky Public Health Conference about our participation in this project.

- If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mschroeder@cste.org.

  - Materials are posted.

- Please list suggestions for CSTE and CDC for how we can best facilitate your progress.

  - I appreciate the sharing of materials.

  - Continued guidance on fulfilling the grant

- Please complete the attached spreadsheet to indicate progress made towards project deliverables.