Influenza Education among Youth in Agriculture
Progress Report 


Please return completed Progress Report to CSTE at mschroeder@cste.org.  


1. Identify your top three achievements over the last quarter. 

1. Attended Indiana fair managers’ conference to share data regarding mitigation strategies to  decrease influenza A virus (IAV) transmission at county fairs. Animal Influenza Ecology and Epidemiology Research Program (AIEERP) staff also consulted with the Ohio State Veterinarian regarding similar topics, prior to the Ohio fair managers’ conference.
	2. Continued data analysis of evaluation tools used in the previous quarter to draft a 	manuscript entitled, “Can recommendations for reducing zoonotic transmission of 	influenza A viruses from swine impact human attitudes and behaviors?” 
[bookmark: _GoBack]3. Assembled a team of economists and anthropologists to develop qualitative research questions aimed at evaluating the economic burden of IAV outbreaks associated with agricultural exhibitions. In addition, we aim to gain better understanding of the decisions made by swine exhibitors and their families: whether or not to adopt any, some, or all of the risk reduction recommendations presented in the educational outreach activities and materials.
2. Please list the collaborators on this quarter’s achievements and briefly describe their role in the project (i.e. 4H, State PH, State Animal Health).

Ohio Department of Health:  
Ohio Department of Health partners provided technical support and human health expertise for all other collaborating entities. 
Department of Agricultural Communication, Education, and Leadership:  
Continued work toward producing the remaining three short videos to be disseminated through popular social media outlets. 
Animal Influenza Ecology and Epidemiology Research Program: 
Data supporting the recommendation to shorten swine exhibitions at fairs to 72 hours was shared with both the Ohio State Veterinarian prior to the Ohio Fair Manager’s Conference, and with attendees at the Indiana Fair Manager’s Conference.  The mucus swab activity was used in Indiana to visually represent the differences in disease transmission between 3 and 8 days of co-mingling.
In order to evaluate the effectiveness of recommendations in the “Measures to Minimize Influenza Transmission in Swine Exhibitions” document, a survey was developed and distributed to jackpot show participants. Data from this survey has been evaluated further and drafted into a manuscript to be submitted to American Journal of Health Promotion, following collaborator review.
In order to investigate research questions associated with the economic value of the exhibition swine industry and gain better understanding of the behaviors of swine exhibitors and their families, we have assembled a multidisciplinary team with senior-level leadership within the state of Ohio that is committed to evaluating the effectiveness of the educational interventions developed and implemented through the Influenza Education among Youth in Agriculture Project. 

3. Please describe areas of concern or challenges in meeting the objectives or providing deliverables.

We anticipate being able to meet all project objectives.
4. Please include an updated project timeline.

The project is on track with the proposed timeline and we foresee no major alterations.

5. If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mschroeder@cste.org. 

The only additional resource added to Basecamp this quarter was instructional document for conducting the “Mucus Swap” activity.
https://3.basecamp.com/3164497/buckets/2026830/uploads/843368189

6. Please list suggestions for CSTE and CDC for how we can best facilitate your progress.

We are appreciative of all the support you provide and have no suggestions for improvement.

7. Please complete the attached spreadsheet to indicate progress made towards project deliverables.
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