## Sheet1
Please describe the progress made towards completion of the following project deliverables. | Outputs (What activities have happened over the past 3 months? What materials have been developed or produced as a result?) | Outcomes (How have these activities addressed one or more of the project objectives? 1. Improve participant awareness and knowledge of zoonotic diseases, including zoonotic disease transmission and prevention, 2. Increase participant awareness and knowledge of careers in public and animal health, 3. Facilitate a better understanding among participants of the role public and animal health play in disease prevention, 4. Motivate participants to adopt behavior that can help prevent zoonotic disease transmission, 5. Develop relationships among stakeholders that could be used to facilitate more effective and efficient responses to important public and animal health issues (e.g., the response to infectious disease outbreaks or epidemics))
1. Conduct tabletop exercises/trainings at Ohio 4-H Conference and OSU Junior Swine Day | Completed during first quarter of project | Training materials improve participant awareness and knowledge of zoonotic diseases and encourage youth to adopt behavior to help prevent disease transmission by defining zoonotic diseases; demonstrating disease spread using a glittered pig; describing IAV in pigs and people; defining biosecurity allowing students to give examples; initiating discuss among participants through group activities; and providing 'what to do' before, during, and after agricultural exhibitions to minimize risk of disease transmission.
2. Social Media Campaign | Five social media messages, related to the information covered in onsite training modules, were developed and posted using both Facebook and Twitter. Messages were posted from the Ohio 4-H animal science account each day, Monday - Friday, the week before each individual Ohio fair starts on their respective pages. The last messages posted October 3-7, 2016. | The goal of these messages, once disseminated, is to improve participant awareness and knowledge of zoonotic diseases, including zoonotic disease transmission and prevention; and to motivate participants to adopt behavior that can help prevent zoonotic disease transmission. Sysmos software was used to quantify the reach and effectiveness of the social media campaign. Total reach of the messaging varied each day, with an average of 17,915 reaches. The number of reaches also varied by week. Increased weekly activity cooresponds to weeks associated with the county fairs where the study team conducted IAV surveillance in swine and/or piloted educational materials in 2015.
3. Development of zoonotic disease educational curriculum for youth in agricultural education programs | Coordination among partners has resulted in a Zoonotic Disease chapter for the Swine Resource Handbook and skill-a-thon cirriculum. The book chapter will be distributed statewide as a handout in 2017 and will be added to the next version of resouce handbook. | Materials were written to improve participant awareness and knowledge of zoonotic diseases, including zoonotic disease transmission and prevention; increase participant awareness and knowledge of careers in public and animal health; facilitate a better understanding among participants of the role public and animal health play in disease prevention; and to motivate participants to adopt behavior that can help prevent zoonotic disease transmission.