Influenza Education among Youth in Agriculture
Progress Report 


Please return completed Progress Report to CSTE at mschroeder@cste.org.  


1. Identify your top three achievements over the last quarter. 
a. Submitted Zoonotic Disease chapter to the 4-H curriculum office to be distributed as an addendum to the Swine Resource Handbook during the 2017 program year.
b. Compiled social media viewership data to gauge the reach of the messaging and the sentiment of the audience.
c. Began compiling supplies for to the zoonotic diseases skill-a-thon stations to be piloted during the 2017 program year.

2. Please list collaborators on this quarter’s achievements, and briefly describe roles of different organizations involved (i.e. 4H, State PH, State Animal Health)

Ohio Department of Health:  Provided support and expertise for all other partners.

Ohio 4-H Youth Development: Prepared the zoonotic diseases chapter of the Swine Resource Handbook for statewide distribution.

Department of Agricultural Communication, Education, and Leadership: Used SYSOMOS software to collect and analysis data to quantify social media effectiveness. 

Animal Influenza Ecology and Epidemiology Research Program: Coordinated with 4-H to develop the swine resource handbook zoonotic disease chapter, and compiled supplies for zoonotic disease skill-a-thon station to be piloted during  2017 program year.

3. Please describe any areas of concern or challenges to meeting the objectives or providing deliverables.
[bookmark: _GoBack]We have progressed according to the proposed timeline and all collaborators and stakeholders have been supportive.







4. Please include an updated project timeline.

  Feb-16	        Apr-16        Jun-16         Aug-16       Oct-16            Dec-16
































					

  Present education at state wide youth meetings


            Develop social media campaign

                         Implement social media campaign 

                Analyze Sysomos MAP data

        Develop content for zoonotic disease chapter

   Format, revise, edit zoonotic disease chapter 

                                          Develop skillathon station

   Present education materials to Extension Educators



5. If you have materials you are already distributing, please include a sample PDF or link of those materials. 
N/A                                        Develop skillathon station


6. Please list any suggestions for CSTE and CDC for how we can help best facilitate your progress.
N/A

7. Please complete the attached spreadsheet, to indicate progress made towards project deliverables.  

























