## Sheet1
Please describe the progress made towards completion of the following project deliverables. | Outputs (What activities have happened over the past 3 months? What materials have been developed or produced as a result?) | Outcomes (How have these activities addressed one or more of the project objectives? 1. Improve participant awareness and knowledge of zoonotic diseases, including zoonotic disease transmission and prevention, 2. Increase participant awareness and knowledge of careers in public and animal health, 3. Facilitate a better understanding among participants of the role public and animal health play in disease prevention, 4. Motivate participants to adopt behavior that can help prevent zoonotic disease transmission, 5. Develop relationships among stakeholders that could be used to facilitate more effective and efficient responses to important public and animal health issues (e.g., the response to infectious disease outbreaks or epidemics))
Develop new “Animal Science Anywhere” Curricula and distribute in the form of Zoonotic Disease Prevention Toolkits | Three new lesson plans have been developed one lesson focusing on influenza, one about careers in human and animal health, and one about the One Health initiative. The lesson plans and the supplies to teach all three lessons were combined in a kits and built for 4-H volunteers and leaders to utilize. 2,000 kits were built and thus far, 1,695 have been distributed. | 1. The curriculum features a lesson specifically about influenza, which focuses on influenza's role as a zoonotic pathogen. Additionally, the One Health lesson focuses on the tie between human and animal medicine, which discusses zoonosis. 2. One of the lessons focuses on careers in human and animal health. 3. All three lessons focus on the participants role in zoonotic diseases but primarily the influenza and One Health lessons focus on the preventative measures that participants can implement to reduce the impact of zoonosis with their own animals. 4. Each lesson provides a take home message, which focuses on motivating participants to utilize the techniques discussed in the lessons in their own lives. 5. Particularly the careers lesson work to strengthen the relationship between participants and agencies that work in human and animal health.
Design and develop additional educational materials/signage for zoonotic disease prevention | The 11 by 17 signs titled "Biosecurity is easy as 1,2,3" have been printed and assembled for each fair to receive at the annual fair convention. | 5. Increased communicate awareness of the opportunity to working together. 1. The signs are designed to motivate participants to utilize preventative measures in their own lives, from washing their hands to wearing the proper PPE the signs are improving community and participant knowledge about how to prevent zoonosis.